## Slide 1
FAST / IOTA Shutdown 2023-2024
IPI installation and commissioning is our highest priority. All hands on deck.
Electric: -IOTA Bake GFCI breakers (AD/Web 57570) (no movement)
-ESB Laser Lab electrical work complete. Need Interlocks!!!
ES&H: -LLSS in OSC Mode / New South Gate / IPI Interlock Install
IPI: -ESB 480/120VAC Electric Req “being generated” (T&M???)
  -Beamline under vacuum. DON’T TOUCH beamline stuff
Water: -Chiller repair POSTPONED (PO717353)
-NML sanitary line replacement to start Monday
AD Shutdown’24: Support groups are freeing up (PESD, LCW)
Inform FAST RunCo of any work on the accelerator—
FSO Walk-down today at 2:30pm. No work to be done during.

## Slide 2: ISD Updates for NML
Roll Up Door - In Progress (168986) assigned to the “Schedule Planner”.
Clean Y-Strainer – Hold (181072) due to Abatement??
High Bay Lighting LED Upgrade – In Progress (163677)
Catwalk Electrical Receptacle Changeouts – In Progress (189398)
Bathroom drains leaking – 2 week downtime to fix. In Progress
ESB HVAC – In Progress –pushed back to 01/27/2025.
Cleanup in mech rooms – Working with Clorica to clean up. DONE
Tire Marks from lift – Electrical group to pay for this? In Progress
Mechanical Checks on critical water connections – DONE
Window Cleaning - In Discussion. FY2025
Exterior Lights (both inground and canopy) - waiting on quote. On Hold
Lightbulbs: Bathroom, FCR, ESB, 9WX,… Being scheduled™

## Slide 3
FAST shutdown continues through this CY24 for the installation and commissioning of the IOTA Proton Injector (IPI)
  Thanks to support groups helping us (ES&H, HLRF, Instrumentation, MSD, ISD, PESD, etc...)
IPI beamline at UHV vacuum
HLRF build out is close™ to completion
  Build out resumed last week and continues this week
  Modulator & HV Pulse Transformer getting built out
IPI Source conditioned up to 51kV & 12mA of protons
Spectrometer & Allison Scanner analyzing species from IPI Source
IPI LCW work has resumed and continues
LCW chiller repair: contractor was on site but gone (PO 717353)
  Down 01/17/24 (eLog 252152). Started 10/17, & 11/6, but paused! (Morgan’s Law)
FSO Walk-down today at 2:30. No work during.
Thanks to OPS for being vigilant on ACNET alarms.
— Contact FAST Coordinator with any work or access requests
FAST / IOTA 9:00 Report