## Slide 1: Muon Campus Shutdown Report
Jim Morgan
Friday 09:00 Ops Meeting
November 15, 2024

## Slide 2: Muon Campus status
Study – Alternative M5 optics
Study – M1-M3 Optics
Electrostatic Septum ESS2 installation and new stand check-out for both septa
  ESS1 and ESS2 aligned to Delivery Ring centerline
  Vacuum connections made on ESS2 and pump-down initiated
  High voltage connections made on ESS2
  Motion-control check-out began on ESS1 & ESS2
Q205 rad hard quadrupole and modified vacuum pipe installation
  Special pipe was installed in magnet early in the week, final welding Thursday
  Profilometer Tee has been installed upstream of ELAM
Domestic water line repair north of AP-0 and over MI-8 Line
  Berm integrity needs to be checked after repairs
Miscellaneous LCW leaks repaired
Muon LCW resistivity continues to be poor
AP-0 A/C work paused, reasons unclear

## Slide 3: Domestic water line replacement north of AP-0

## Slide 4: Electrostatic septum

## Slide 5: Simulation of resonantly extracted beam trajectory
ELAM
ESS1
ESS2
Circulating Beam
Extracted Beam
Cathode
Cathode

## Slide 6: Simulation of resonantly extracted beam trajectory

## Slide 7: Upcoming work
D30 installation work
  ESS area vacuum pump-down continues, ion pumps have been turned on
  ESS vacuum needs to improve before high voltage conditioning can begin
  Q205 installation, vacuum connections and vacuum pump-down
Domestic water line repairs south of AP-0 may have compromised shielding
  Close to Transport berm, need to survey to understand if berm was disturbed
  Excavation for new water line crossed over MI-8 tunnel
Other upcoming work
  Install additional steel shielding above ECMAG
  Several survey & alignment tasks including Q205 & M4 WCM
  Continue ESS1 & ESS2 motion-control check-out and limit switch adjustments
  Repair Kirk Key hardware on disconnects, requires more modifications to disconnect
  Replace several power supply circuit breakers and some primary wiring
  Prepare to install Mu2e Extinction Monitor Collimator in Absorber area
  M4 Final Focus vacuum installation, A/C dipole installation
Hope to begin preparing for beam operation later this month
  Re-core Rings, Extraction and M4 Enclosures to operational cores next week
  Safety system testing afterwards