## Slide 1: Cryo Assembly, Cold Mass Status
A. Vouris
Cryo Assy L2 Meeting
Nov. 18, 2024

## Slide 2: Cold Mass Tooling & Design Status
WorkStation Equipment
  Status
    End Can
      Lead End – Pallet jack cart drawings and note for 2nd unit
      Order additional pallet jack w/ extended forks
    Cold Mass drawings
      Working through redlines for next batch of drawing mods
        dwg for revisions: Magnet Model updated in all drawings
          F10151260 – redlined updates needed to clear welding station saddles
          F10178090 – Capillary tube install update – Released & submitted revision ticket for missed corrections
          F10172809 – Pressure test drawing default updates from lower dwg
          Update Drawing tree - as needed after final revisions
    Additional tooling:
      Alignment Tooling Clamp ID’s (scheduling with Shop, VMS)
      HT-X alignment tooling (in procurement)

## Slide 3: Cold Mass Tooling & Design Status
Cold Mass
  Engr Analysis & Note:
    Shell shim sizing for CM-06

## Slide 4: Cold Mass Tooling & Design Status
Cold Mass
  CM-04 (MQXFA-08b & MQXFA-14b)
    UT Completed Friday Nov. 15 – received report this morning (verbal report confirmed no flaws/rejects).
    Electrical Checkout to begin next (start of Capillary work).
    N-Line welding in parallel with above
    HT-X Flare flanges – need to align HT-X for final welding (CERN tooling to arrive this week)
    Beam tube Flare welding – next
    Test Nozzle welding prep
  CM-05 Alignment Station set up (MQXFA07b & 15)
    Shell shim sizing review complete – Ok to weld
    Welding prep in progress – longitudinal welding scheduled for tomorrow (2 welders) Nov. 19-20
  CM-06 (MQXFA13b & MQXFA 18)
    Shells washing complete
    Metrology on Site to survey MQXFA13b
    Awaiting shell inspection: arc length in process (thickness completed)
  CM-07
    Shells at Machine shop – 1st of 2 is complete starting machining on 2nd this week… both shells projected to ship before Thanksgiving Week.

## Slide 5: Cold Mass Tooling & Design Status
Cold Mass (cont)
  Production Series
    Final procurements:
      Production N-lines - leak test 100% complete
      Formed Plates in stock at FNAL for -08, -09 and -10 (ready for machining)
      CM-05 – CM-10 & Spare Tack blocks – received and in stock
      Shell Plate Forming: CM-10 Picked up & back in storage
      Spare plates shipping from CERN – waiting for shipping confirmation
      CM-06 thru CM-10 & Spare Shell Plate Machining PO (REQ #355609)
        CM-07 Shells – final machining stage
        CM-08 shells swap approx. week of Dec. 2
      CM-05 – CM-10 Lower plates – Received all 30 pcs and QCR approved
        All threads being chased/checked for fit & reamed holes checked for fit up with pin

## Slide 6: Cold Mass Tooling & Design Status
Cold Mass (cont)
  Production Series
    Magnet 16
      In temp storage (ICB)
    Q1-Q3 Bus production
      Units up to CM-10 plus 1 spare are complete
      1 Spare Buss – housing parts received and inspected