## Slide 1: Mezzanine Flooring and Railing
Status
  Design note first draft complete
  Eng. Analysis of mounting bases in process
Walking surface and railings for mezzanines
Procurement plan
  Decking and railings are COTS
  Two types of custom railing mounts will be required
  Self install
Tech Spec. | N/A | Starting this week | 
3D Model | N/A | Complete | 11/1/24
Design Note | N/A | First Draft Complete | 11/8/24
Eng. Analysis | N/A | In Process | 11/20/24
CO Report | N/A | Empty | 
2D Drawings | N/A | Empty | 
Schedule Contact | N/A | Empty | 
Install Procedure | N/A | In Process | 
Install Activity:
Install flooring and railing onto detector, cryo, and ledge mezzanines
16-Sept-26
Store/Move 120d - 4mo
Fabrication
30d – 1mo
Procurement
90d – 3mo
Latest “Submit to Procurement”
16-Jan-26
PRR Target: Dec. 2024
Fabrication/delivery

## Slide 2: Last Week
Mezzanine Flooring and Railing
  Working on analysis of custom rail bases
  Adding in annex to design note covering the floor supports in the cavern wall
Condensation Prevention Piping
  Finished drawing packet for procurement/installation
Cryostat Shims
  Made 2D drawings for procurement