## Sheet1
Initial B185 CERN test planning Nov 11 2024
Campaign → Activity | Start | End | Comments/personell
Install small CRP SST row 1 | 2025-02-17 | 2025-02-28
Survey bare small SST |  |  | Complete early
Install TAD and SST hoist brackets & rods |  |  | Complete early
Survey all roof flanges |  |  | Complete early - Dirk needed for this
Install SST winches with gantry beam | 2025-02-17 | 2025-02-28 | Start Mid February -Filippo
Lift SST near floor and measure deflection
Load SST and measure deflection
Un-Load SST
Raise SST to location
Fix to roof flange
Final SST survey
Install Restraint Bars?
Install PDS fibers for Cathode PDS | 2025-02-17 | 2025-02-28
Install PDS roof cable tray on chimney flanges
Install PDF fibers in cable tray
Test Install Field cages | 2025-03-17 | 2025-03-21
Repeat PDS fiber installation
Install flanges on roof and adjust
Place gantry cranes on roof
Attach hoists to cranes and connect power
Place dummy frames on installation cart
Test assemble FC support beam
Test raise FC support beam and lower
Test assemble field cage
Install FC and route fibers into field cage.
Measure FC location
Test lateral shift and locking in postion on top
Test install floor stabilizer installaiotn
De-install FC
commission lift table | 2025-03-17 | 2025-03-21
Test lift table with cathode
Test lift table with CRP and hexapod
Install cathode row 1 | 2025-04-14 | 2025-04-25
Install scaffold before start
Place cathode cart on scaffold and secure
SST is already installed
Place cathode on lift table if available.
Raise cathode and attach to dynema ropes.
Move scaffold under cathode
Secure cathode to lift table.
connect fibers to cathode.
Set cathode height
Connect dyneema ropes to cathode and adjust
Make electrical connections to cathode.
Remove cathode and FC
Install roof cable trays and CRP cables | 2025-05-12 | 2025-05-16
Install dummy chimney flanges
Connect cables to chimney
Verify cable routing and labels.
Install CRP row 1 | 2025-06-02 | 2025-06-13
Install roof cable tray and cables
Place dummy CRP on hexapod
Verify linkage installation
Lift CRP to cabling height
Cable CRP
Lift to final height
Install linkages
Disconnect hexapod
Lower lift table
Survey
TCO closure (Wall Access and exiting) | 2025-07-07 | 2025-07-11
Install cleanish area
Mock up storage
Determine needed eqp for closure (lights pow)
Test exiting
Install row 20 FC bottom | 2025-07-14 | 2025-07-18
Install top endwall FC panels
Establish work area limitations (barriers)
Install lower FC panel
Install missing field shaping strips
Install floor support
Install CRP row 20 | 2025-09-01 | 2025-09-12
Assemble large SST
Install large SST
Install small SST
Survey
Test install cryogenic instrumentation
Install four dummy CRP
Install FC panels and check clearance
Install cathode row 20 | 2025-09-29 | 2025-10-03
Install scaffold before start
Place cathode cart on scaffold and secure
SST is already installed
Place cathode on lift table if available.
Raise cathode and attach to dynema ropes.
Move scaffold under cathode
Secure cathode to lift table.
connect fibers to cathode.
Set cathode height
Survey
Connect dyneema ropes to cathode and adjust
Make electrical connections to cathode.
remove lift table from area
Remove cathode and FC?
Test install wall cable trays and PDS | 2025-10-20 | 2025-10-25
Mount cable tray support
Test cable tray lifting
Test install PDS wall support structure
Test install cables on cable tray in reel.