## Slide 1: Week of 11/19/2024
    Condensation prevention PRR was held on 21st Nov.
    Concerns about fiberglass machining underground. Checking with the manufacturer to see if they could cut intake holes.
    Checking with Erik V about tolerances on the intake holes.
Week of 11/26/2024
Continue working on the condensation ducting comments.
Detector mezzanine
  Short perpendicular bracing solved the buckling issues on the long sections of the beams.
  Continue optimizing the short brace sizes.
  Tested suppressing cross bracing on detector side of the mezzanine.
Procurement document https://edms.cern.ch/document/3192084/1
Design report herehttps://edms.cern.ch/document/3192089/1
Drawings
https://edms.cern.ch/document/3192091/1

## Slide 2: HD/VD Detector Mezzanine
Status
  Working on engineering analysis and note on updated model
Procurement plan
  Railing and flooring off-the-shelf
  Stairs off-the-shelf with supports built into mezzanine structure.
  Installed by contractor.
Tech Spec. | 234809 | In work | 
3D Model | 234790 | In work | 
Eng. Analysis | 2822247 | In work | 
CO Report | 252309 | Empty | 
2D Drawings | 234790 | Empty | 
Schedule Contact | 252399 | Empty | 
Install Procedure | 252429 | Empty | 
Install Activity:
Installed one portal at a time.
06-June-26
Store/Move 120d - 4mo
Fabrication
60d – 3mo
Procurement
180d – 6mo
Latest “Submit to Procurement”
06-May-25
PRR Target: December 2024
Fabrication/installation