## Slide 1: Cryo Assembly, Cold Mass Status
A. Vouris
Cryo Assy L2 Meeting
Dec. 02, 2024

## Slide 2: Cold Mass Tooling & Design Status
WorkStation Equipment
  Status
    End Can
      Order additional pallet jack w/ extended forks
    Cold Mass drawings
      Working through redlines for next batch of drawing mods
        dwg for revisions: Magnet Model updated in all drawings
          F10151260 – redlined updates needed to clear welding station saddles
          F10178090 – Capillary tube install update – Released & submitted revision ticket for missed corrections
          F10172809 – Pressure test drawing default updates from lower dwg
          Update Drawing tree - as needed after final revisions
    Additional tooling:
      Alignment Tooling Clamp ID’s (scheduling with Shop, VMS) – Discuss drop off this week with Gary (VMS).
      HT-X alignment tooling (in procurement) – out for quotes TD Procurement Quote close: 3-Dec.-2024

## Slide 3: Cold Mass Tooling & Design Status
Cold Mass
  Engr Analysis:
    Herve response:
      Cold Mass OD correction to FRS: waiting on CERN reply?
      Triplet Flange Support Plate revision resolution: adding 2 stiffeners on CM-03 & CM-04
      Replace rod and add stiffeners from CM-05 on
    CM-02 OD measurements:
        LMQXFA Traveler: 24.957” – 24.979” avg OD after welding: 24.966”OD or 634.1 mm OD. Entered avg OD measurement above into traveler for CM-02

## Slide 4: Cold Mass Tooling & Design Status
Cold Mass
  CM-04 (MQXFA-08b & MQXFA-14b)
    UT Completed Friday Nov. 15 – confirmed passing welds
    HT-X Flare flanges – completed with CERN tooling & shipped to CERN (fastest method) Monday the 25th of Nov.
    Cryo piping brackets completed
    Electrical Checkout and capillary work continues this week
    N-Line welding (this week) – after gussets are welded
    Beam tube Flare welding (this week)
    Test Nozzle welding prep – next week into following
  CM-05 Alignment Station set up (MQXFA07b & 15)
    Shell shim sizing review complete – confirmed Ok to weld
    Welding of longitudinal seam welds complete Nov. 19-20.
    Will start dressing of welds as fill-in work
    Move back to Alignment station next week for post weld survey (next week)
  CM-06 (MQXFA13b & MQXFA 18)
    Metrology completed survey MQXFA13b
    MQXFA-18 (start receiving inspection later this week/ beginning next week)
  CM-07
    Shells at Vendor – complete, arranging shell pick up/swap for Dec. 5 or 6

## Slide 5: Cold Mass Tooling & Design Status
Cold Mass (cont)
  Production Series
    Final procurements:
      Production N-lines - leak test 100% complete
      Formed Plates in stock at FNAL for -08, -09 and -10 (ready for machining)
      CM-05 – CM-10 & Spare Tack blocks – received and in stock
      Shell Plate Forming: CM-10 Picked up & back in storage
      CM-05 – CM-10 Lower plates – Received all 30 pcs and QCR approved
        All threads being chased/checked for fit & reamed holes checked for fit up with pin
      Spare plates shipped from CERN – waiting for shipping confirmation
      CM-06 thru CM-10 & Spare Shell Plate Machining PO (REQ #355609)
        CM-07 Shells – final machining stage
        CM-08 shells swap approx. week of Dec. 9
      Measure 4 He shells in storage to document arc length (DL) dimensions:
        1 PL#
        2 PL#
        3 PL#
        4 PL#

## Slide 6: Cold Mass Tooling & Design Status
Cold Mass (cont)
  Production Series
    Q1-Q3 Bus production
      Units up to CM-10 plus 1 spare are complete
      1 Spare Buss – housing parts received and inspected