## Slide 1
FAST / IOTA Shutdown 2023-2024
IPI installation and commissioning is our highest priority. All hands on deck.
Electric: -IOTA Bake GFCI breakers (AD/Web 57570) (Done 12/4)
-ESB Laser Lab electrical work complete. Needs Interlocks.
ES&H: -LLSS in OSC Mode / New South Gate / IPI Interlock Installing
IPI: -ESB 480/120VAC Electric Req in queue with Paul (T&M???)
  -Fire Alarm testing through 12/13
  -I need rough schedule estimates from each “task manager”
  -Beamline under vacuum. DON’T TOUCH beamline stuff
Water: -Chiller repair POSTPONED (PO717353) HA approved.
NML: Asbestos removal in Chiller Room, next week
Inform FAST RunCo of any work on the accelerator—

## Slide 2: ISD Updates for NML
Roll Up Door - In Progress (168986)
Clean Y-Strainer – Hold (181072) due to Abatement??
Y-Strainer Asbestos abatement, 2nd try week of 12/9
High Bay Lighting LED Upgrade – In Progress (163677)
Catwalk Electrical Receptacle Changeouts – In Progress (189398)
ESB HVAC – In Progress –pushed back to 01/27/2025.
Window Cleaning - In Discussion. FY2025
Exterior Lights (both inground and canopy) - On Hold -waiting on quote.
Door 204-S closer – In Progress
Test Points on 600A disconnects. – In Progress
Exterior doors with gaps: letting in rain, cold, mice.
Lightbulbs: Bathroom, FCR, ESB, 9WX,… Being scheduled™

## Slide 3
FAST shutdown continues through this CY24 for the installation and commissioning of the IOTA Proton Injector (IPI)
  Thanks to support groups helping us (ES&H, HLRF, Instrumentation, MSD, ISD, PESD, etc...)
IPI beamline at UHV vacuum
HLRF build out is close™ to completion
  Build out resumed 11/04 and continues this week
  Modulator & HV Pulse Transformer getting built out
IPI Source conditioned up to 51kV & 12mA of protons
Spectrometer & Allison Scanner analyzing species from IPI Source
IPI LCW work has resumed and continues
LCW chiller repair: contractor was on site but gone (PO 717353)
  Down 01/17/24 (eLog 252152). Started 10/17, & 11/6, but paused! (Morgan’s Law)
Thanks to OPS for being vigilant on ACNET alarms.
— Contact FAST Coordinator with any work or access requests
FAST / IOTA 9:00 Report