## Slide 1
Greg Rakness (FNAL)
Friday 9am AD meeting
06-Dec-2024
Mu2e report
https://indico.fnal.gov/event/67294/

## Slide 2: Sundry stuff at Mu2e
Continuing leak detection of TSd Feedbox + transfer line + solenoid
  This is a long winding volume at 10–10 torr, which is hard to do
Electricians working…
  for beam enclosures at MC2
    (Mu2e experiment is in Muon Campus building #2)
  for full flow purifier at MC1
    (Muon g–2 experiment was in Muon Campus building #1)
Coordinating with ISD for replacement of Automatic Transfer Switch (for backup power) at MC1
  Note: cryo plant + air compressor for MC2 is at MC1
Coordinating work in Production Solenoid area
  Pour Extinction monitor collimator filter concrete
  Install Production Solenoid on stand and install Heat & Radiation Shield
Installed toe clamps to hold external stands in place
  To prevent movements in case they get accidentally bumped

## Slide 3: Detector Solenoid Endcap arrived at Mu2e
Endcap comprised of
  Vacuum Pump Spool Piece
    For pumping insulating vacuum & muon beamline
  Instrumentation Feedthrough Bulkhead
    For cables and optical fibers for detector train
Detector Solenoid
Vacuum Pump Spool Piece (VPSP)
Stopping Target + proton absorbers
Tracker
Calorimeter
Instrument Feedthrough Bulkhead (IFB)
External Stands
Muon Beam Stop
Was like this

## Slide 4: Prep work
Clear stand for VPSP
Move IFB wooden mock-up outside

## Slide 5: Step by step (1/2)
1. Here comes the truck
2. Bring VPSP into the high bay
3. Pick it up
4. Put it down

## Slide 6: Step by step (2/2)
5. Bring IFB into the high bay for staging
6. (to be done) receive hillman rollers, move around external stands, bring IFB downstairs…