## Slide 1: Cryoassembly Fabrication and Vacuum Components Status Update
Roger Rabehl (for Charles Orozco)
9 December 2024

## Slide 2: Status
CA02
  Basic Crating wrapped the assembly on Tuesday
  Loaded into shipping container on Wednesday
  Departed FNAL Thursday late morning
CA03
  Closed up for vacuum check and atmosphere to insulating vacuum leak test
  Permits submitted for second cold mass pressure test, expected ~today
  Pressure testing new end can thermal shield components
    Permitting in process for reservoir testing
  Vacuum vessel note submitted for review

## Slide 3: Vacuum Components
New vacuum carts
  Assembly complete
  ORC pending completion of recommendations from ORC walkthrough
    Compressed air pressure regulators and relief valves received
    Waiting on fuse holders
  Plan to fill with oil and run a short functional test to confirm correct polarity
  IB1 pump skid being used until the ORC is complete

## Slide 4: Vacuum Components
Purge with nitrogen after each pressurization with helium and vent outside of building. Standard practice moving forward.
  Tony, add steps to CM04, CM05, and (CM06 Adam) cold mass travelers.
  Charlie, add steps to CA03, and (CA04 Adam) cryoassembly traveler.
Scroll pump exhaust backflow
  Charlie/Sandor, develop design attaching to the KF exhaust port to supply nitrogen gas.
Replace CA03 HX flex line with SS tubing, Qb end can
  Tony, procure SS tubing
  Scott, form to usable shape
  Tony, weld assy
  Charlie, pressure leak check test (Roger)
O-ring length on cryo-vessel
  Roger, update spreadsheet used on CA01 - complete
Leak check end cans used on CA02
  Tony, design interface ring to seal IP/NIP end cans as a unit using plate in parking lot if possible.
  Tony, Scott, perform leak check on CA02 end cans by 17 Jan 2025.
Gas Analyzer
  Roger/Thomas use gas analyzer to measure ICBA helium
CA03 combination pressure/leak test
  Charlie/Roger, urgently obtain test permit signatures – in progress