## Slide 1: Mezzanine Flooring and Railing
Status
  Design note and calculation note uploaded to edms
    264185
Walking surface and railings for mezzanines
Procurement plan
  Decking and railings are COTS
  Two types of custom railing mounts will be required
  Self install
Tech Spec. | N/A | Starting this week | 
3D Model | N/A | Complete | 11/1/24
Design Note | N/A | First Draft Complete | 11/8/24
Eng. Analysis | N/A | First Draft Complete | 12/2/24
CO Report | N/A | Empty | 
2D Drawings | N/A | Empty | 
Schedule Contact | N/A | Empty | 
Install Procedure | N/A | In Process | 
Install Activity:
Install flooring and railing onto detector, cryo, and ledge mezzanines
16-Sept-26
Store/Move 120d - 4mo
Fabrication
30d – 1mo
Procurement
90d – 3mo
Latest “Submit to Procurement”
16-Jan-26
PRR Target: Dec. 2024
Fabrication/delivery

## Slide 2: Last Week
Mezzanine Railing
  Engineering note first draft complete
    Minor adjustments made from Justin’s feedback
    Uploaded to EDMS @ 264185 along with design note
DAQ
  Pulling together power draw from DAQ racks to begin specifying air handler
  Working on further development of DAQ rooms
Cryo Mezzanine Installation
  Working on updated installation plan for updated cryo mezzanine construction