## Slide 1
Maddie Schoell
12 December 2024
Status of Open USIs
https://fermipoint.fnal.gov/org/eshq/ASD/SitePages/Unreviewed-Safety-Issue-(USI)-Program.aspx?web=1
USI status is kept up-to-date on the Accelerator Safety SharePoint – USI Program Page

## Slide 2: All Open USIs
 | POC | Current Status (received, reviewed, out for signature) | Need before beam? | SAD/ASE Changes?
MI-20240702 MI218 Sump Discharge Drilling | Kyle Hazelwood | Received feedback from RAD, Maddie signed Pending signatures: Matt | Yes – MI/RR | No
P1P2-20240813 Change Rep Rate Limiter Input | Tom Kobilarcik | Ready to send to Lab Director with other associated USIs (M-20240723 & ALL-20240819) Will then need FSO | Yes – P1P2 | Yes
M-20240723 ArCS in MC7 | Evan Niner | Ready to send to Lab Director with other associated USIs (P1P2-20240813 & ALL-20240819) Will then need FSO | No for MCenter in general, Yes before beam for JGG/ArCS - MCenter | Yes
ALL-20240819 Adjust SY, Meson, and Neutrino Boundaries and update MCI Analyses | Tom K | Ready to send to Lab Director with other associated USIs (P1P2-20240819 & M-20240723) Will then need FSO | Yes – P3 Beamline | yes
8GeV-20241115 8 GeV Berm DWS Excavation, Valve Riser | Kyle Hazelwood | Complete/approved RSI  *need Screening form from Kyle with his double signature | Yes – 8 GEV | no
NuMI-20241203 NuMI Target Hall Shielding Door Removed During Shutdown | Phil Schlabach | Screening form received, need to complete evaluation | Yes – NuMI | no
ALL-20241206 PIP-II Linac Construction Work Near F3 | Tom Kob, Jerry Annala, Steve Dixon | Screening and evaluation forms complete, routed for signatures: Jerry Annala, Steve Dixon | No | no
VTS-20241127 Dust Control Curtains and VTS ODH Concerns | Mike White, Fumio Furuta | Complete/approved RSI  | No | no
ALL-20241210 Temporary Removal of Jersey Barrier Adjacent to WH W OOB |  | Screening and evaluation forms complete, being routed for signatures: Mary, Maddie, Marc | No | no
USI Screener Training: https://www-esh.fnal.gov/pls/cert/schedule.show_course_details?cid=14899
Classes Scheduled: 1/8, 2/11, 3/12, 4/10

## Slide 3: Open USIs – Lab Director/FSO Approval Needed
 | Description & Stage in the USI Process | Lab Director Approval Needed | FSO Approval Needed
P1P2-20240813 Change Rep Rate Limiter Input | Description: Change the magnet which is monitored by the repetition rate limiter to a magnet further upstream. Update the SAD & ASE to remove specifying which magnet is monitored, as the repetition rate itself is the Credited Control and it’s safety function does not depend on the specific magnet. The magnet will be specified in the OAD. SAD/ASE Revision: S03.C09 P1 P2 Beamline, ASE A.1. Review needed: xx | Yes | yes
M-20240723 ArCS in MC7 | Description: New experiment in MC7 that will introduce cryogens to the area, which will require new ODH Credited Controls. No change to the beamline. Credited Controls will be applicable once cryo is introduced, in the meantime MCenter beam can be delivered to other experiments with the ODH system locked off. SAD/ASE Revision: S04.C03 Meson Experimental, ASE A.1 Review needed: Experiment ORC. | Yes | yes
ALL-20240819 Adjust SY, Meson, and Neutrino Boundaries and update MCI Analyses | Description: New MCIs performed for the Switchyard P3 Beamline, Meson, and Neutrino to be within the Public Area Basis. Will require 2 new Credited Controls: both fencing for the Neutrino Muon beamline. SAD/ASE Revision: S03.C12 P3 Beamline, S03.C13 Meson, S03.C14 Neutrino, ASE A.1 Review needed: none – MCI currently under SRSO review | Yes | yes
All of these USIs have been signed through AD/ESH and ready to be submitted to Lab Director. What’s next:
MCIs submitted to SRSO for approval
ASD polishing up SAD/ASE updates based on updated MCIs, final review by Machine Owners
Once MCIs approved and Machine Owner final review complete, will route for Line/ALD signature
Once SAD Chapters and ASE approved through ALD and MCIs approved, will send full “package” of SAD Chapters, ASE, USIs to Lia