## Slide 1
Darren Crawford, PIP-II Beam Commissioning L3 Manager
13-Dec-24
AD Scheduling Meeting - PIP-II Report

## Slide 2: PIP-II Construction Site

## Slide 3: PIP-II Update
240 trucks
Linac Tunnel 54% complete
RF Trench 38% complete
Coldbox arrival 07-Jan-25
High Bay Building AUP 23-Jun-25
Linac Tunnel AUP 19-Sep-25

## Slide 4: Existing Machines + PIP-II
Booster
The current operational accelerator complex near the PIP-II project includes the Booster machine and the P3 beamline that delivers beam to the Switchyard beamlines and experiments
P3
To Switchyard

## Slide 5: PIP-II Shielding Assessments
Beam Transfer Line SA
Booster
SA
PIP-II Linac SA
SY120
SA
The PIP-II Project will be creating or altering 4 different Shielding Assessments through the life span of the Project.
The two operational machines along with…
Two additional SAs of our own
PIP-II broke up SAs based on the construction packages:
PIP-II Linac
Beam Transfer Line

## Slide 6: Enclosures - AD Complex Integration
The Project worked with the Accelerator Directorate/Beams Division/Proton Source Dept Head and associated group leaders for their input into the future enclosure Critical Device Controllers (CDCs). In general, the radiation simulations determine what devices can be considered a critical device. These devices are designed for a fail-safe manner, meaning positive control of this device allows beam to continue to enclosure its protecting.
PIP-II
Junction
Booster
Low Exposure Geelhoed (LEG) Bypass

## Slide 7: Enclosure CDCs – PIP-II Linac
WFE is a radiation area
HV Racks
Ion Sources
30 Bend Magnet

## Slide 8: Enclosure CDCs - Junction

## Slide 9: Enclosure CDCs - Booster
Arc 2 Dipole PS #1
Arc 2 Dipole PS #2

## Slide 10: Thank you

## Slide 11: PIP-II Construction Site

## Slide 12: PIP-II Construction Schedule
Starts
June 2027
Starts
Dec 2025
The Beam Transfer Line construction package is broken into two phases.
  Phase 2 turns beam off to the complex
  Phase 1 disables beam to the Muon Campus & NuMI via Main Injector
    These areas plan to operate during Phase 1 construction
    The P3 beamline (F Sector ESS) is a logical input to Main Injector Critical Device
  Since IPR 2023, PIP-II has developed a plan along with Accelerator Directorate
P3 beamline