## Slide 1: FD2 Cryostat Decking and Railings
Status
  Draft design note needs end floor support. Tech spec in drafting.
  Need analysis of railing and end floor support.
Walking surface on the cryostat roof
Procurement plan
  Decking and railings are COTS.
  Railing support clamp are COTS with two simple jet cut steel plates. Do we go for IDIQ for jet cutting and powder coating?
  Do we order the steel support beams with the stairs and walkways or the flooring?
Tech Spec. | 0000252216 | Early Draft | 1/1/25
3D Model | 0000252246 | Empty | Done
Eng. Analysis | 0000252276 | Empty | mm/dd/yy
CO Report | 0000252309 | Empty | mm/dd/yy
2D Drawings | 0000252339 | Empty | Draft Ready
Schedule Contact | 0000252399 | Empty | Need vendors
Install Procedure | 0000252429 | Not Needed | Not Needed
https://edms.cern.ch/project/CERN-0000252185
Install Activity:
Install the false floor and the fall prevention barriers on the top of the cryostat in the South Cavern
25-June-26
Store/Move 120d - 4mo
Fabrication
60d – 3mo
Procurement
180d – 6mo
Latest “Submit to Procurement”
30-June-25
PRR Target: January 2025