## Slide 1: Mezzanine Flooring and Railing
Status
  Design note and calculation note uploaded to edms
    264185
Walking surface and railings for mezzanines
Procurement plan
  Decking and railings are COTS
  Two types of custom railing mounts will be required
  Self install
Tech Spec. | N/A | Empty | 
3D Model | N/A | Complete | 11/1/24
Design Note | N/A | First Draft Complete | 11/8/24
Eng. Analysis | N/A | First Draft Complete | 12/2/24
CO Report | N/A | Empty | 
2D Drawings | N/A | Empty | 
Schedule Contact | N/A | Empty | 
Install Procedure | N/A | In Process | 
Install Activity:
Install flooring and railing onto detector, cryo, and ledge mezzanines
16-Sept-26
Store/Move 120d - 4mo
Fabrication
30d – 1mo
Procurement
90d – 3mo
Latest “Submit to Procurement”
16-Jan-26
PRR Target: Dec. 2024
Fabrication/delivery

## Slide 2: Last Week
DAQ AHU
  Began looking into available options for AHU
    CRAC/CRAH units
      Purpose built for computing rooms
      Tighter temperature control
      Temp sensors integrated into racks
      Must be installed in the computing room
    Standard AHU
      General use AHU
      Considerably larger then CRAH units
      Installed external to computing room
Condensation prevention piping
  Generated manufacturing drawings
Underground Material Movement
  Working with Jace to perform motion studies on mobile cranes for cryostat installation