## Slide 1
Dean Still
0900 Meeting Update
Dec 20, 2024
F Sector Reconfiguration Task Force -

## Slide 2: F Sector Reconfiguration Task Force:
Initiated in October 2024 by Mary Convery with 11 members.
Assess the impacts of PIP-II phased construction on Accelerator Operations.
Deliver an impact report by March 2025.
Task Force discovered impacts that were time sensitive with the start of PIP-II Linac Construction in Jan 2025.
Main impacts center around the excavation of the MR road which under the road carry the main power feeder duct and central communication duct.
Preliminary Report recommends feeder experts assess alternate power backfeed paths or alternate means of power impacted areas.
Preliminary Report can be found at (Beams-doc-10412)
Phase 2
Starts June 2028
Phase 1
Starts Dec 2026
BTL Construction
LINAC Construction
Phase 0
Starts Jan 2025

## Slide 3: Lab Projected Schedule

## Slide 4: PIP-ll Linac Construction Overview
4
Ductbank Location
F4
A0
Main Ring Road
F4
F4
Main Ring Road View looking South where excavation will begin Jan 6, 2025 - 18DEC24
(Courtesy : Steve Dixon)
F3

## Slide 5: Feeder and Communication Duct Overview
5
Ductbank Location
A0
Main Ring Road
F4
F4
GIS Overview showing buried power feeders and communication ducts
Screenshot from drawing C-14
BTL Enclosure
(Courtesy : Steve Dixon)
Communication duct will have a backup fiber pulled to mitigate any issues.

## Slide 6: Subcontractor’s Feeders Support Plan
6
F4
F4
(Courtesy : Steve Dixon)

## Slide 7: Subcontractor’s Current Schedule Plan
7
F4
Daily Power Outages
Potential impacted areas due to daily power outages:
  A0 Building
  All of F sector (potentially all Tevatron service buildings)
  E4R
  AP0
  AP10
  AP30
  AP50
  Mu2e Building (MC-2)
  MC-1
  It is believed this work will not impact beam to BNB
(Courtesy : Steve Dixon)
This plan is being discussed to try to
minimize the impact to loss of power.
It looks like there is at least a back feed
path to Muon Campus feeder 24

## Slide 8: Road Impacts
There will be a change in road access during construction between F3 and F4.
Booster Road to Main Ring road will remain open at times with limited travel.
This section of the Main Ring Road will be closed.