## Slide 1: Cryo Assembly, Cold Mass Status
A. Vouris
Cryo Assy L2 Meeting
Jan. 6, 2024

## Slide 2: Cold Mass Tooling & Design Status
WorkStation Equipment
  Status
    End Can
      Order additional pallet jack w/ extended forks
    Cold Mass drawings
      Working through redlines for next batch of drawing mods
        dwg for revisions: Magnet Model updated in all drawings
          F10138327 – Update Triple flange gussets work ticket
          F10151260 – redlined updates added to clear welding station saddles – starting work ticket
          F10178090 – Capillary tube install update – Work ticket for missed corrections and model updates for triple flange
          F10172809 – Pressure test drawing default updates from lower dwg
          Update Drawing tree - as needed after final revisions
    Additional tooling:
      Alignment Tooling Clamps at VMS – All complete for station 1. Station 2 to start after CM-05 is off (Mach ID’s to fit cm)
      HT-X alignment tooling – WPA Works LLC PO# 720341 due Jan. 10, 2025 – Mat’l ordered expecting to start machining next week (12/23) and on schedule to be shipping by Jan. 10 (Will update status today)
      Test Blank for End Cans at shop for Machining – to be completed week of Jan. 13

## Slide 3: Cold Mass Tooling & Design Status
Cold Mass
  Engr Analysis:
    CERN updates:
      Cold Mass OD correction FRS?
      Triplet Flange Support Plate revision resolution: adding 2 stiffeners on
        CM-03 completed both ends
        CM-04 completed both ends
        CM-05 thru CM-10 will get all 3 rev. gussets
      Buss Lead spyder revisions/modifications
    CM-02 OD measurements:
        LMQXFA Traveler: 24.957” – 24.979” avg OD after welding: 24.966”OD or 634.1 mm OD. Entered avg OD measurement above into traveler for CM-02

## Slide 4: Cold Mass Tooling & Design Status
Cold Mass
  CM-04 (MQXFA-08b & MQXFA-14b)
    UT Completed Friday Nov. 15 – confirmed passing welds
    Cryo piping brackets completed
    N-Line welding – complete
    Beam tube Flare welding both sides complete
    Electrical Checkout pre-capillary bending complete. Tube bending in process
    Test Blanks/Nozzle welding prep – in process (& CERN provided parts rec’vd)
  CM-05 Alignment Station set up (MQXFA07b & 15)
    Shell shim sizing review complete – confirmed Ok to weld
    Welding of longitudinal seam welds complete Nov. 19-20.
    Dressing of welds – complete
    Back on Alignment station & post weld survey is complete (over Holidays)
    SSW complete and reviewed (exceptional results)
  CM-06 (MQXFA13b & MQXFA 18)
    Metrology completed survey MQXFA13b
    MQXFA-18 - receiving inspection survey in process
    Weld Station prepped/ surveyed for next weld sequence (over Holidays)
  CM-07
    Shells – receiving inspection next and then clean

## Slide 5: Cold Mass Tooling & Design Status
Cold Mass (cont)
  Production Series
    Final procurements:
      Production N-lines - leak test 100% complete
      Formed Plates in stock at FNAL for -08, -09 and -10 (ready for machining)
      CM-05 – CM-10 & Spare Tack blocks – received and in stock
      Shell Plate Forming: CM-10 Picked up & back in storage
      CM-05 – CM-10 Lower plates – Received all 30 pcs and QCR approved
        All threads being chased/checked for fit & reamed holes checked for fit up with pin
      Spare plates shipped from CERN – waiting for shipping confirmation
      CM-06 thru CM-10 & Spare Shell Plate Machining PO (REQ #355609)
        CM-08 shells dropped off 12/9/2024 – checking for updates this week
      Measured 4 He shells in storage (old rev) prepare for shipment to CERN

## Slide 6: Cold Mass Tooling & Design Status
Cold Mass (cont)
  Production Series
    Q1-Q3 Bus production
      Units up to CM-10 plus 1 spare are complete
      1 Spare Buss – assembly complete & tested (ready for storage