## Slide 1: Mezzanine Flooring and Railing
Status
  Design note and calculation note uploaded to edms
    264185
  Working on updates from CO
Walking surface and railings for mezzanines
Procurement plan
  Decking and railings are COTS
  Two types of custom railing mounts will be required
  Self install
Tech Spec. | N/A | Empty | 
3D Model | N/A | Complete | 11/1/24
Design Note | N/A | First Draft Complete | 11/8/24
Eng. Analysis | N/A | First Draft Complete | 12/2/24
CO Report | N/A | Empty | 
2D Drawings | N/A | Empty | 
Schedule Contact | N/A | Empty | 
Install Procedure | N/A | In Process | 
Install Activity:
Install flooring and railing onto detector, cryo, and ledge mezzanines
16-Sept-26
Store/Move 120d - 4mo
Fabrication
30d – 1mo
Procurement
90d – 3mo
Latest “Submit to Procurement”
16-Jan-26
PRR Target: Dec. 2024
Fabrication/delivery

## Slide 2: Last Week(s)
Railing Base Analysis
  Received feedback from CO
  Working through revisions to analysis
    Changed materials of the tube section of the base to allow for higher stresses
  Waiting on clarification from CO on bolt analysis
Cavern Material Handling
  Working through various material movements through caverns
    Checking load charts, movement paths, and physical clearances to rock