## PAW
Milestone # | Milestone | Baseline Date | Actual/Estimated Completion Date | Milestone Status | Comments | Responsible Person(s)

## SOP
Milestone # | Milestone | Baseline Date | Actual/Estimated Completion Date | Milestone Status | Comments | Responsible Person(s)
3.1-1 | Add to Darshan features needed to monitor HEP workflows: aggregation and visualization across multiple logs and testing on LCF/NERSC | 2024-09-30 |  | in progress |  | Saba, Shane Snyder
3.1-2 | Develop a prototype for accelerator-friendly data model | 2024-09-30 | 2024-09-30 | completed |  | Peter, Amit Bashyal
3.1-3 | Demonstrate direct mapping of accelerator-friendly data models to disk storage (HDF5 and RNTuple) | 2024-09-30 | 2026-03-31 | postponed | Will depend on 4 | Peter, Amit Bashyal
New | Evaluate Accelerator friendliness of CAF data model | 2025-09-30 |  | new
New | Develop Accelerator friendly data model in support of upstream processing for one experiment | 2026-09-30 |  | new
...
3.5.1-1 | Identify the feature set (data model, tools) needed to store experiments reconstruction and simulation output data in RNTuple | 2024-06-30 | 2024-06-30 | complete | Both ATLAS and CMS data is storable in RNTuple, CMS using 'unsplit' storage feature. | Peter, Chris Jones, Marcin Nowak
3.5.1-2 | At the request of ROOT team, provide RNTuple API Interface review process | 2024-06-30 | 2024-12-31 | complete |  | Peter, Matti Kortelaien, Peter van Gemmeren
3.5.1-3 | Demonstrate RNTuple storage for CAFAna format data | 2024-09-30 | 2024-12-31 | complete |  | Peter, Amit Bashyal
3.5.1-4 | Provide guidelines for experiments to store reconstruction and simulation output data with agreed on feature set (data model, tools) in RNTuple | 2026-09-30 |  |  |  | Peter, Chris Jones, Marcin Nowak
New | Use Darshan to monitor HEP workflows on HPC comparing TTree and RNTuple I/O behavior | 2025-09-30 |  | new |  | Peter, Rui Wang, Patrick
New | Enable Performance benchmarking of experiments' workflows using RNTuple | 2025-09-30 |  | new |  | Peter, Chris Jones, Marcin Nowak, Amit Bashyal
New | Develop guidelines for reducing resource needs for RNTuple I/O | 2026-03-31 |  | new |  | Peter, Chris Jones, Marcin Nowak
New | Collaborate with ROOT team in development of advances RNTuple functionality: Indexing, Caching, Metadata | 2026-09-30 |  | new |  | Peter, Matti Kortelaien, Peter van Gemmeren
...
3.5.2-1 | Develop infrastructure to apply at least one intelligent compression algorithm to HEP production data streams | 2024-09-30 |  | complete | ANL-LDRD project with Emma Weiler working with synthetic and DUNE-inspired waveforms to study feasibility for intelligent compression in downstrem (non-RAW) data | Peter, Amit Bashyal
3.5.2-2 | Develop validation methods for intelligent compression algorithm to HEP production data | 2027-09-30
New | Benchmark reconstruction/analysis performance on intelligently compressed data for at least one experiment | 2025-09-30 |  | new |  | Peter, Amit Bashyal
New | Enhance intelligent compression algorithm of HEP production data streams by utilizing 2 dimensions | 2026-03-31 |  | new |  | Peter, Amit Bashyal
...
3.5.3-1 | Instrument ROOT RNTuple DAOS I/O libraries and testing on LCF/NERSC | 2024-09-30 | 2025-03-30 | in progress | delayed deployment of Aurora | Saba, Shane Snyder, Rob Latham
New | Add to Darshan features needed to monitor HEP workflows: | 2025-09-30 |  |  | depends on 3.5.3-1
3.5.3-2 | Prototype examples for upstream references, fine-grained versioning and event sample augmentation to ROOT data in experiment agnostic way, in preparation to using object store technologies. | 2024-09-30 | TBD | postponed | effort availability | Saba, Peter van Gemmeren
3.5.3-3 | Prototype examples for upstream references, fine-grained versioning and event sample augmentation to ROOT data in experiment agnostic way using object store technologies. | 2025-09-30 | TBD | postponed |  | Saba, Peter van Gemmeren
...
3.5.4-1 | TBD: Identify HEP experiments (e.g. DUNE) need for HDF5 data streaming, including HPC, and determing blueprint for technology solution. | 2025-09-30 |  |  | Includes SLAC for xrootd experts | Saba, Marco Mambelli, SLAC
New | Using Globus for data transfer for neutrino experiments | 2026-03-30 |  |  |  | Saba, Marco Mambelli

## SML
Milestone # | Milestone | Baseline Date | Actual/Estimated Completion Date | Milestone Status | Comments | Responsible Person(s)

## HEPSims
Milestone # | Milestone | Baseline Date | Actual/Estimated Completion Date | Milestone Status | Comments | Responsible Person(s)