## Slide 1: 302.4.04 – Cryo-assemblies Horizontal Test Weekly status report
S. Stoynev / G. Chlachidze
Jan. 13th, 2025

## Slide 2: LQXFA/B03 test preparations
LQXFA/B02 Test Traveler is closed
LQXFA/B02 Test Report released, DocDB #5392-v2
Helium lines & N2 vent line insulation work - Done
Construction work is complete in IB1
Update/Improve the controlled cooldown and warmup procedures for cryo-operators – Will meet with the cryo-operations group soon
Faulty GHe flow-meter for Stand 4 power lead #1 has been replaced
  Diagnostic report received from Control Plus Inc. regarding the faulty flow meter by Brooks Instrument. They suspect a damage due to liquid corrosion.
  Need to improve the condensation guard above the flow meters