## Slide 1: OTE Building PMG Report April 29, 2013

## Slide 2: Agenda
CDF D&D: J. Lewis
OTE Building Project: R. Merchut
  Coordination
  State Activities
  Schedule
  Fiscal
  Summary Action Items

## Slide 3: OTE Outfitting GPP G13-211
FY 13: $2M for VoIP/networking & Contingency.
  Develop Plan for moving ahead with VoIP/Networking w/out tenant layouts.
    Discussions with CD to incorporate independent network underway.

## Slide 4
IASU Update (IGPP)
Phase 2 scope approximately 85% complete.
CDF Coordination
Schedule coordination required for CDF west ramp replacement with D&D.
  Approx 3 weeks required for demo & replacement.
  Cure time dependent on anticipated CDF loads (steel plates from detector demo). 7-30 days

## Slide 5: OTE Project Status:
Shop drawing review continues. Expect to be substantially complete in the next 4 weeks.
250 RFI’s rec’d from contractor have been responded to. (15 RFI’s last month).
Schedule Oversight on-going. Continue to work with contractor to provide coordinated information.
Financial Oversight on-going.
Safety procedures continue to be expanded as more subs come onto the project.

## Slide 6: OTE Project Status:
LEED procedures & Action Plan implemented.
  Contractor reporting 99% construction waste has been recycled.
  On track to meet goal of 20% (by cost) of regionally manufactured materials.
  On track to meet goal of 20% (by cost) of recycled content in materials used.

## Slide 7
15-35 workers daily in the past month (rain)
  Exterior enclosure
    Corrugated Metal Panels - 2nd & 3rd floor
    1st floor framing, densglass, & weather barrier
  Window framing & glazing 1st, 2nd, & 3rd floors
  High roofing substantially complete. Low roofing underway.
  Above ceiling MEP & FP pipe, raceways & ductwork hanging substantially complete 2nd & 3rd floors.
  In-wall MEP underway.
  Interior Studs underway.
  Geothermal field: work has resumed after 1 month delay due to equipment breakdown.
OTE Construction Status:

## Slide 8: Exterior Enclosure

## Slide 9
Lunch Room Enclosure

## Slide 10
Low Roofs
High Roof

## Slide 11
OTE/CDF Elevator Pit & Stair
Roof Access
West Stair

## Slide 12: Interior Fit-up

## Slide 13: MEP

## Slide 14: Two Week Look Ahead
Roofing on low roofs
Detail gazing 2nd & 3rd floors.
Exterior panels 2nd & 3rd floors.
1st floor storefront installation
MEP, FP equipment & in-wall pipe runs
Geothermal
Interior partitions

## Slide 15: State DCEO Activities
DCEO quarterly report to State for quarter ending 2/28/13 submitted.
  $8,434,758 Total Grant Expense
Project on schedule for grants to be 100% costed by 5/31/14 grant requirement.

## Slide 16: Contractual Schedule Adjustments
MS 1 Bldg Shell Complete: 6/19/13*
MS 2 Substantial Completion: 11/5/13
  (Project is fully costed at MS 2, retention remains)
MS 3, Project Complete: 1/29/14
  *MS-1 (only) extended due to change order work requiring long lead times.

## Slide 17: BMC Schedule

## Slide 18: Schedule
Weather Impact

## Slide 19: Schedule

## Slide 20: Project Plan Tracking Milestones
Project is fully costed at MS 2, retention remains

## Slide 21: Pacing Milestones & Contractual Milestones

## Slide 22
BMC Construction BCWS & ACWP

## Slide 23
BMC Monthly Costing
Monthly Average to date: $1,069,885.63
Required Monthly Average to complete: $896,757.52
Weather Impact

## Slide 24
BMC Monthly Costing Weather Impact
Weather Impact: 10 rain days out of 20 work days
Roofing
Siding

## Slide 25
601 TSR Budget Balance
ALL Grant Costing w/ BMC Projection

## Slide 26: Financial
Project 601 |  | Reallocated Baseline Budget (obligates full grants) 12/31/12 |  |  | Budget to Complete as of 3/31/13 (SA 19) |  |  | Project Budget Balance to Complete
 |  | Indirect Baseline Direct Budget Budget BAC |  |  | ITD Obl ITD Obligations Indirect Costs Total |  |  | 
1.0 | EDI |  |  |  |  |  |  | 
1.1 | Grant 1 Design ED | $1,120,958 | $86,261 | $1,207,218 | $1,120,958 | $82,671 | $1,203,629 | $3,589
1.2 | Grant 1 Design Contingency | $0 | $0 | $0 | $0 | $0 | $0 | $0
1.3 | Grant 2 Construction Support I | $764,532 | $121,507 | $886,039 | $764,532 | $105,565 | $870,097 | $15,942
2.0 | Construction |  |  |  |  |  |  | 
2.1.1 | Fixed Price Construction | $17,550,249 | $90,193 | $17,640,442 | $17,514,466 | $90,193 | $17,604,659 | $35,783
2.2.1 | T&M Construction | $65,983 | $11,851 | $77,834 | $65,983 | $11,851 | $77,834 | $0
2.3.1 | Adv Procurement | $157,495 | $30,971 | $188,467 | $157,495 | $30,971 | $188,467 | $0
Project G13-211 Contingency |  |  |  |  |  |  |  | 
2.1 | Fixed Price Const Contingency | $950,000 | $0 | $950,000 | $299,281 | $0 | $299,281 | $650,719
2.2 | T&M Const Contingency | $40,683 | $9,317 | $50,000 | $0 | $0 | $0 | $50,000
 |  |  |  |  | $0 | $0 | $0 | $0
TOTALS |  | $20,649,900 $350,099 $21,000,000 |  |  | $19,922,715 $321,251 $20,243,967 |  |  | $756,033
OTE Grant Costs with FY13 GPP Contingency
(Does Not Include FY13 Equipment & Furnishings or IGPP)
Projected Cost Analysis

## Slide 27: Financial – Estimated at Completion

## Slide 28: Financial – Available Contingency
March ’13:
55% based on Cost
57% based on Time

## Slide 29: Contingency Management
Sources available to fund change orders:
  IGPP;
  De-scope from anticipated T&M work;
  De-scope from A/E support work;
  DOE backstop (GPP Outfitting project);
  De-scope from main construction work (will not recover all funds);
  Value engineering main construction work

## Slide 30: Summary Action Items
Continue shop drawing & change order review, RFI responses
Continue construction coordination & oversight.
Continue schedule oversight
Continue financial oversight
Initiate plan for engineering design Outfitting GPP.
Continue discussions with CD for VoIP, networking.