## Slide 1
Darren Crawford, PIP-II Beam Commissioning L3 Manager
17-Jan-25
AD Scheduling Meeting - PIP-II Report

## Slide 2: PIP-II Update
240 trucks
Linac Tunnel 59% complete
RF Trench 43% complete
Coldbox arrival 15-Jan-25
High Bay Building AUP 23-Jun-25
Linac Tunnel AUP 19-Sep-25

## Slide 3: PIP-II Construction Site

## Slide 4: Thank you

## Slide 5: PIP-II Construction Site