## Slide 1: HD/VD engineering update – 1/21/2025
Air handling equipment for cryostat installation
  Fermi ventilation engineer has green light and is preparing unit specification by end of this week, no response yet
Cryostat external ladder/guardrail cable (fall protection system)
  Analysis completed, working on writing up analysis documents
Cryogenic mezzanine structure
  Submitted all documentation to compliance office
  Received feedback on engineering note, will be working to address comments and update analysis documents as needed
Working on BOE updates for HD cryo infrastructure/Roof gas systems
  Mostly completed, outstanding quote from vendors (roof decking mcnichols, low pressure line regulator)
  Meeting setup with cryogenics team to review nitrogen purge system of cryostat insulation (Jan. 22)
VD roof decking support beams
  Will analyze beam configuration once cryo mezzanine feedback is reviewed
Cryogenic pipe support structures
  Will start working on pipe rack structure design and analysis for cryogenic pipes through the drifts and detector cavern

## Slide 2: HD Coldbox
Status
  Documents released
  PRR held Oct. 28, 2024
  PRR panel questions answered, final report due Nov. 25
  QC requirements checklist received, added documents to procurement specification
  Working on critical lift plan
  PRR Recommendation tracker responses submitted 12/27/24
Procurement plan
  LPTA
  Fabrication drawings send to vendor
  Final subassemblies delivered to SDWF
Tech Spec. | 252224 | Released | 10/17/2024
3D Model | 252254 | Released | 
Eng. Analysis | 252285 | Released | 
CO Report | 252317 | Released | 
2D Drawings | 252347 | Released | 
Schedule Contact | 252407 | Empty | 
Install Procedure | 252437 | Released | 
https://edms.cern.ch/project/CERN-0000252193
Install Activity:
Assemble the cold boxes for the HD detector
8-Jun-26
Store/Move 120d - 4mo
Fabrication
180d – 6mo
Procurement
180d – 6mo
Latest “Submit to Procurement”
15-Dec-24
PRR Target: October 2024
Fabrication/delivery

## Slide 3: VD Temporary AHU
Status
  Procurement specification, 2D drawings created
  Awaiting additional information from ventilation engineering
Procurement plan
  Best Bid Value
  Installed by vendor
Tech Spec. | 252218 | Eng. Check | 10/17/24
3D Model |  | n/a | 
Eng. Analysis | 252278 | Released | 04/13/23
CO Report |  | n/a | 
2D Drawings | 252341 | In work | 10/17/24
Schedule Contact |  | Empty | 
Install Procedure |  | n/a | 
https://edms.cern.ch/project/CERN-0000252187
Install Activity:
Install the air units and filters on the manholes of the cryostat in the South Cavern 24-Jan-26
Store/Move 120d - 4mo
Fabrication
90d – 3mo
Procurement
120d – 4mo
Latest “Submit to Procurement”
30-Mar-25
PRR Target: ISD/ESH document review Oct 2024 (fulfills PRR)
Fabrication/installation

## Slide 4: VD Cryostat Fall Protection (Ladders/Guardrails)
Status
  Procurement specification drafted, reviewing by ES&H
  2D drawings created, with interfaces
  Installation to be self-performed
  Need loads for analysis plan (OSHA 1926.502, OSHA 1910.28)
    Provided by c.o. 12/17/24
Procurement plan
  LPTA
  Fabrication drawings send to vendor
  Final subassemblies delivered to SDWF
Tech Spec. | 252217 | In work | 10/17/24
3D Model |  | Empty | 
Eng. Analysis |  | Empty | 
CO Report |  | Empty | 
2D Drawings | 252340 | In work | 11/11/24
Schedule Contact |  | Empty | 
Install Procedure |  | Empty | 
https://edms.cern.ch/project/CERN-0000252186
Install Activity:
Install the ladders and the access system for the side walls of the cryostat in the South Cavern
24-Jul-26
Store/Move 120d - 4mo
Fabrication
180d – 6mo
Procurement
180d – 6mo
Latest “Submit to Procurement”
30-Apr-25
PRR Target: November 2024
Fabrication/delivery

## Slide 5: HD/VD Cryogenic Mezzanines
Status
  Revising model and engineering note for accommodating updated assembly plan and beam profiles
  Documents submitted to c.o.
Procurement plan
  LPTA
  Fabrication drawings send to vendor
  Structural components delivered to SDWF
  Installed by contractor
Tech Spec. | 252213 | Empty | 
3D Model | 252243 | Eng. Check | 12/18/2024
Eng. Analysis | 252273 | Eng. Check | 12/18/2024
CO Report | 252306 | In work | 
2D Drawings | 252336 | Eng. Check | 12/18/2024
Schedule Contact | 252396 | Empty | 
Install Procedure | 252426 | Empty | 
https://edms.cern.ch/project/CERN-0000252179
Install Activity:
Install cryogenic Mezzanine level 1 for cryostat #1 - FNAL personnel 28-Jul-26
Store/Move 90d - 3mo
Fabrication
150d – 5mo
Procurement
180d – 6mo
Latest “Submit to Procurement”
3-Jun-25
PRR Target: December 2024
Fabrication/installation