## Sheet1
| PRR | Planned PRR Date | Latest PRR Date | PRR process | PALT procurement processing | FAB | Storage | Install date DEC P6 | Install activity ID | Install activity name
1 | VD Cryostat roof-decking , railings, ladders, cryostat access walkway, and cryostat fall protection | 2025-04-01 | 2025-09-29 | 30 | 180 | 180 | 90 | 2027-01-22 | FDS.CT1.A1110 | Install the false floor and the fall prevention barriers on the top of the cryostat in the South Cavern
2 | South Cavern AC power on cryostat | 2025-11-28 | 2025-11-28 | 30 | 180 | 120 | 90 | 2027-01-22 | FDS.CT1.A1140 | Install the final light and power distribution system on top of the cryostat in the South Cavern
3 | VD Detector and cryogenic Mezzanines | 2025-03-10 | 2025-08-06 | 30 | 180 | 150 | 90 | 2026-10-30 | FDS.CT1.A1050 | Install the detector mezzanine on top of the cryostat in the South Cavern
4 | VD DAQ barracks with AC, HVAC, fire … | 2026-03-01 | 2026-07-24 | 30 | 60 | 30 | 90 | 2027-02-19 | FDS.CT1.A1100 | Install the DAQ barrack and its internal infrastructure in the South Cavern
5 | Stairs? Is a PRR needed as this will have the engineering check by the company?
6 | Electroncis Racks (incl. fans, PDU misc.) |  | 2025-11-17 | 30 | 60 | 200 | 90 | 2026-12-02 | FDS.CT1.A1070 | Install the racks on the detector mezzanine in the South Cavern | PDU may have long lead time
7 | UPS CUC and surface |  | 2024-11-26 | 30 | 129 | 150 | 90 | 2025-12-30 | 13141.A87100 | Install Surface DAQ UPS (note: A87210 CUC install is 10/19/26 suspect schedule logic bad)
8 | VD Cryostat roof feedthrough |  | 2025-05-03 | 30 | 180 | 180 | 90 | 2026-08-26 | FDS.WC1.A1210 | Install the manholes for the South Cavern cryostat
9 | VD Cleanroom changing room and outfitting |  | 2026-05-20 | 30 | 80 | 120 | 90 | 2027-04-05 | FDS.CT1.A1150 | Install the clean tent in the South Cavern
10 | VD Cryostat roof cable trays and argon recovery piping from feedthroughs |  | 2026-01-04 | 30 | 180 | 90 | 90 | 2027-01-29 | FDS.VDT.A1010 | Install all the cable trays in the South Cavern and on its cryostat
11 | VD Access hatch ventillation |  | 2025-08-22 | 30 | 120 | 180 | 90 | 2026-10-16 | FDS.CT1.A1130 | Install the air units and filters on the manholes of the cryostat in the South Cavern
12 | VD TCO beam, and platform |  | 2025-02-02 | 30 | 180 | 90 | 90 | 2026-02-27 | FDS.WC1.A1230 | Install the TCO beam and the corresponding crane for the South Cavern cryostat
13 | VD Cryostat false floor |  | 2026-05-14 | 30 | 120 | 180 | 90 | 2027-07-08 | FDS.CS1.A1200 | Install the temporary floor inside the South Cavern cryostat
14 | N-Cavern Bridge and walkways |  | 2026-01-24 | 30 | 180 | 150 | 90 | 2027-04-19 | FDS.CT2.A1050 | Install the central bridge in front of the cryostat in the North Cavern
15 | N-Cavern Cleanroom |  | 2026-04-12 | 30 | 240 | 120 | 90 | 2027-08-05 | FDS.CT2.A1190 | Install the APA towers and the main beams of the clean room in the North Cavern
16 | HD DSS and ground planes |  | 2026-07-14 | 30 | 180 | 240 | 90 | 2028-01-05 | FDS.CS2.A1210 | Install the detector support system rails inside the North Cavern cryostat
17 | Cold box GN2 system | [8 empty] | Cannot find installation activities
18 | HD Cryostat roof-decking , railings, ladders, cryostat access walkway, and cryostat fall protection |  | 2026-07-09 | 30 | 180 | 120 | 90 | 2027-09-02 | FDS.CT2.A1150 | Install the false floor and the fall prevention barriers on the top of the cryostat in the North Cavern
19 | North Cavern AC power on cryostat |  | 2026-10-11 | 30 | 120 | 30 | 90 | 2027-07-08 | FDS.CT2.A1180 | Install the final light and power distribution system on top of the cryostat in the North Cavern
20 | HD Detector and cryogenic Mezzanines |  | 2026-02-21 | 30 | 180 | 150 | 90 | 2027-05-17 | FDS.CT2.A1090 | Install the detector mezzanine on top of the cryostat in the North Cavern
21 | HD DAQ barracks with AC, HVAC, fire … |  | 2027-01-07 | 30 | 60 | 30 | 90 | 2027-08-05 | FDS.CT2.A1140 | Install the DAQ barrack and its internal infrastructure in the North Cavern
22 | Stairs? Is a PRR needed as this will have the engineering check by the company?
23 | HD Cryostat roof feedthrough |  | 2025-05-03 | 0 | 30 | 180 | 90 | 2027-02-05 | FDS.WC2.A1200 | Install the manholes for the North Cavern cryostat
24 | HD Cleanroom changing room and outfitting |  | 2026-05-20 | 30 | 180 | 120 | 90 | 2027-09-21 | FDS.CT2.A1200 | Complete the clean room infrastructure for the clean room in the North Cavern
25 | HD Cryostat roof cable trays and argon recovery piping from feedthroughs |  | 2026-01-04 | 30 | 180 | 120 | 90 | 2027-09-02 | FDS.HDT.A1020 | Install the sytem of gas pipes on the top of the North Cavern cryostat used to recycle the Ar gas
26 | VD Access hatch ventillation |  | 2025-08-22 | 30 | 120 | 180 | 90 | 2027-04-05 | FDS.CT2.A1170 | Install the air units and filters on the manholes of the cryostat in the North Cavern
27 | HD TCO beam, and platform (Assume part of DSS) | [6 empty] | 2027-01-22 | FDS.WC2.A1220 | Install the TCO beam and the corresponding crane for the North Cavern cryostat
28 | HD Cryostat false floor |  | 2026-05-14 | 30 | 180 | 120 | 90 | 2027-12-17 | FDS.CS2.A1200 | Install the temporary floor inside the North Cavern cryostat
Cables and fibers?
2027-01-07
2024-11-26
25.7333
Formulas:
Latest PRR Date = [Install date DEC P6]-[Storage]-[FAB]-[PALT procurement processing]-[PRR process]