## Slide 1: Week of 1/28/2025
    Condensation prevention duct.
      A draft of bill of planning, (Work activity plan) is ready.
      Duct will be pre-cut to length and will also include intake slots. Minor adjustment in length will still be needed during installation. Meeting with ESH to understand fiberglass machining requirements and constraints.
      Meeting with Steve to review the web req.
    Detector Mezzanine
      Working through compliance office comments on the engineering note.

## Slide 2: Week of 1/28/2025
    L-beam sled
      3D models for the sled and floor plates have been updated as per the lessons learned during the test.
      Draft for procurement specification for the production sled is ready

## Slide 3: HD/VD Detector Mezzanine
Status
  Working on engineering analysis and note on updated model
Procurement plan
  Railing and flooring off-the-shelf
  Stairs off-the-shelf with supports built into mezzanine structure.
  Installed by contractor.
Tech Spec. | 234809 |  | 
3D Model | 234790 | Submitted | 
Eng. Analysis | 2822247 | Submitted | 
CO Report | 252309 | Empty | 
2D Drawings | 234790 | Empty | 
Schedule Contact | 252399 | Empty | 
Install Procedure | 252429 | Empty | 
Install Activity:
Installed one portal at a time.
06-June-26
Store/Move 120d - 4mo
Fabrication
60d – 3mo
Procurement
180d – 6mo
Latest “Submit to Procurement”
06-May-25
PRR Target: December 2024