## Slide 1
Project Activities for MSD
Mayling Wong-Squires
AD Operations Friday 9am Meeting
31 January 2025

## Slide 2: LBNF Primary Vacuum and Magnet Installation Kevin Duel, Ty Funk, Scott Oplt, Will Derylo, Dan Vrbos, Jason Kubinski, Dirk Hurd, Parth Gandhi
Primary Vacuum
  Kicker ceramic beam tube titanium nitride (TiN) coating
    Vendor working out some equipment issues before applying to 12” beam tube samples
  Work on drawings and models for relocation of MI/RR components continues
Magnet Installation
  PO issued for corrector magnet stand prototype fabrication with estimated delivery in March
  Spare stand parts sent out for plating for testing low friction tungsten disulfide coating
  Primary Beam Enclosure dipole stand design continues with modeling and drawings, structural engineering note under review
    Prototype screw jacks arrived and QC’d
    Working out plans for testing under load
  Toroid, RWCM and BPM instrumentation stand design continues
Dipole Stand Screw Jack

## Slide 3: PIP-II Fluid Systems Update Maurice Ball, Michael Geelhoed, Michael Hanson, Jason Grischkat, Monika Sadowski, Frank Rios, Amos Horton
Process Clean Water(PCW) Piping System Installation
  Contract deliveries continue/stored onsite
    PCW Heat Exchanger arrived on flat bed lowboy trailer (plate/frame)
    Dissolved Oxygen Skid
    Particulate filter
  Strategy meetings held with contractor/procurement to plan rigging and transport of heat exchanger to Utility Plant (UP)
  Installation activity in UP scheduled to begin in Spring
“Goldilocks” and compressed air manifold assemblies underway by MSD techs
Procurement for HBB/WFE systems continue
  Ion Source, LEBT, MEBT manifold bid procurement underway
  RFQ intermediate skid bids under review
Absorber Cooling Skid Bid Procurement
  25 KW RAW skid – out for bid
  25 KW and 2 KW air cooling skids preparing bid packages
PCW Heat Exchanger arrived from Mfr on semi-truck flatbed (Top image)
Dissolved Oxygen skid for PCW system in MDB (Bottom left image)
Particulate filter for PCW system (Bottom center image)
“Goldilocks” LCW valve manifold assemblies, Courtesy MSD techs (Bottom right image)

## Slide 4: PIP-II Instrumentation Update Dakota Krokosz, Amadon Faul, Eric Pirtle
Wirescanners
  BTL and diagnostic cart linear actuators bid awarded to Thermionics.
  Established polishing process of poor-quality frames from CERcuits on-site with glass shot.
  Reverse electroplating / Chemical stripping of wirescanner gold plating to begin, pending ES&H review.
  Still waiting on a few machined components.
Emittance Scanners
  LEBT construction delayed due to machined parts being late.
  Assembly girder and vacuum chamber at NWA. Chamber is being cleaned.
  Dry assembly of the MEBT AES is in progress. Waiting on new faraday cup as braze material leaked into the cavity.
  Test station estimated to be ready by end of February.
Diagnostic Cart
  85% of orders are currently placed. 35% or parts have been received.
BPM’s
  Mechanical development of the model / concept for the elliptical shoebox split plane BPM is in progress. Plate shape pending final beam tube size selection.
  2” BPM testing ongoing.
Laserwire
  Faraday cup design complete.
  Updating magnet drawings and will send out for bid again by March.
Faraday Cup
Type-N Feedthrough
PIP-II Laserwire Faraday Cup
CF Flange
Glass shot polish (Top) Provided finish (Bottom)