## Slide 1: Muon Campus Shutdown Report
Jim Morgan
Friday 09:00 Ops Meeting
February 7, 2025

## Slide 2: Recovery from loss of LCW on January 26
Study – Alternative M5 optics
Study – M1-M3 Optics
Continued investigation into sequence of events and magnet assessment
  Three MDC’s damaged, believe all other magnets are okay
  Some magnets are more vulnerable depending on type and dissipated power
  Vacuum in V906 area recovered okay, don’t believe there was a leak
  MC-1 fire alarm at 02:42 was from MC-1 Hall VESDA, not “Protectowire”
  Fire techs provided detailed information about timing sequence of alarms
  Have created a document of our findings
Magnet damage checks
  Have performed several visual inspections of all magnets that were powered
  No signs of heat damage on other magnets
  Tested 29 magnets that had high dissipated power and/or a long period without cooling water, all check out okay
Preparing to replace MDC dipoles V742, V743 & V906
  Hazard Analysis was submitted last week, approved this morning
  Alignment did “as found” of both existing and replacement magnets
  Still need to remove power leads on damaged and replacement magnets
Put fans with filters in tunnel to reduce eye and throat irritation from smoke
LCW system restarted on Monday in 1-pump (shutdown) mode for now
  Conductivity recovered, make-up rate is low

## Slide 3: Location of damaged and replacement MDC dipoles
V742
V743
V906
Delivery Ring Enclosure
D30 straight section
Replacement magnets from M5 Line

## Slide 4: Muon Campus fire protection
Illustration from
Mark Kujawa, ISD
Very Early Smoke Detection Apparatus
(VESDA)
V906

## Slide 5: Magnet dissipated power and time without LCW
Current
Current
Power
Power
Time
Time
Minutes
Minutes
Power*Time
Power*Time

## Slide 6: Total power loss in Muon Campus magnets
V906
V742 & V743

## Slide 7: Moving forward
The path ahead
  Need to replace three failed dipoles, believe other magnets are okay
  Three M5 Left Bend dipoles H005, H008 and H011 will replace damaged magnets
  May need to open two hatches to get lifting equipment properly staged
  M5 dipoles have special vacuum pipes, MSD has located three standard pipes
  The V906 magnet hanger may need new parts due to the difference in MDC types
Check magnet thermal protection on power supplies with PLC for interlocks
Did not get beam sign-offs completed prior to January 26 incident
Continue to improve tunnel air filtering effort
Repair a few lingering LCW leaks
PIP-II 6-week pause began last week
Expect Main Injector heat exchanger issues will cause delay beyond PIP-II pause
Hope to address warm power supply circuit breakers during 6-week pause
  Replace several circuit breakers identified as running warm (especially V907)
  Increase wire size on a few circuits to improve margin