## Slide 1: LARP Crab Cavities Project Plans, Cost and Schedule
Ratti
LBNL

## Slide 2: Overview
Scope of work
Plans
  Two phases, LARP + Construction
Cost estimate
  Basis of estimate
  Contingency analysis
  Comparative analysis
Schedule
Sleepless nights
Conclusions

## Slide 3: Scope of US Contribution
LARP funds R&D until the SPS test
  Deliver one cryomodule for testing in the SPS during the 2016-17 runs and possibly in Pt-4 in the LHC
    2 cavities, He vessels, tuners, HOM mode dampers
    RF couplers provided by CERN
    Cryogenics, RF power, local installation provided by CERN
US Construction Project funds production
  Deliver 10 cryomodules of 3 cavities each
    Contain cavities, He vessels, tuners, HOM mode dampers
    Cryogenics, RF power, local installation provided by CERN
    8 CM needed in pts 1 and 5, 2 spares (one per IP)
Feedback from DOE reminds that the effort on crab cavities should be carried through construction and not be limited to the SPS test

## Slide 4: Plans overview
SPS Validation Tests
  2 cavities, one plane only (H or V)
  Crab concept with proton beams
  Machine protection aspects
  Beam measurements (noise, heat loads..)
Essential to finalize LHC design
  CERN will make a final decision on crab cavity system only after a successful SPS test
Build a prototype cryomodule for LHC
  3 cavities, new dimensions and interfaces
Production Run

## Slide 5: Basis of Estimate
Bottoms up - Resource loaded schedule using average rates for broad categories at each lab
  Scientist/Engineer, Designer, Technician, PostDoc
Checked against top-down comparisons
Fully burdened, including materials and travel
Salaries and material costs escalated through 2022
Schedule details are still high level
  Plan to refine towards CD-1

## Slide 6: Estimated budget highlights
LARP –> SPS demonstration
  3 years, $4.5M, 35% contingency
  Big challenge – more later
Construction –> LHC prototype CM
  3 years, $5.6M, 30% contingency
Construction –> 10 Production CM
  ~3.5 years, $25M, >25% contingency
  Up to one year schedule float

## Slide 7: Spending profile
LARP to Construction transition point could be modified as needed
FY18 jump due to material procurement
  Purchase order for cavities
Chart: US Contribution to the HL-LHC Crab Cavities
| FY13 | FY14 | FY15 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22
LARP | 0.64329 | 1.2451 | 1.2539 | 0.15141 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Construction | 0 | 0 | 0.14937 | 2.5851 | 2.9249 | 10.1837 | 10.4492 | 6.2524 | 2.9013 | 1.7885 | 0

## Slide 8: LARP R&D – Spending profile
Challenge:
  External contributions are needed to meet SPS test goals
LARP contributes to less than 1/2 of the cost:
  Not all commitments are finalized
    FTEs estimated using LARP cost
Chart: 
| FY13 | FY14 | FY15 | FY16
LARP | 0.64329 | 1.2451 | 1.2539 | 0.15141
GARD | 0.4 | 0.4 | 0.4
STFC | 0.4 | 0.4
CERN | 0.5 | 0.5 | 0.5
SBIR | 0.5 | 0.5
Construction | 0 | 0 | 0.14937 | 2.5851

## Slide 9: LARP R&D – External Resources
External Resources:
  CERN ME committed >0.5 FTE/yr in support of CM development and integration in SPS test
  Niowave
    Received in April 2013 a Phase II SBIR – ready to support LARP’s deliverable
  STFC
    Requesting funding for 2014-17 for 2 FTE for CM design
  GARD
    FNAL’s GARD committed $0.4M for FY14 and 15
  LARP Management (Toohig Fellows and Oversight) accounted separately
CERN available to pick up some difference in case of shortfall
  But there are restrictions and requires planning

## Slide 10: Cost estimate Top-Down
Production estimate is ~$2.5M per CM in quantity 10
  Plus ~30% contingency
JLAB cost analysis helps getting another perspective
  JLAB upgrade recent reference for a production run of 10 cryomodules
  Very different, yet relevant

## Slide 11: Jlab Cryomodule Cost History
Data taken from closed projects, C100 is estimated
Engineering costs included
Overhead Rates lowered for C100,SNS,CEBAF projects
XFEL estimate ~$1.7M?
ILC estimate ~$1M?
A. McEwen
From. J. Mammosser (JLAB)

## Slide 12: Schedule Highlights

## Slide 13: Schedule Details – R&D

## Slide 14
Production Cost and Schedule Assumptions
CD-3 in FY2017. CD-0,1,2 schedule unclear, but assume that CD-like readiness is required on timeline consistent with CD-3
Production window is FY2017-2021
  Goal is ~1 year schedule contingency relative to CERN schedule. Deliver production cryomodules by end of 2021.
LARP and external funding allow for a timely SPS test
CERN Hi-Lumi TDR is complete in 2015.
Consistent with the Magnet plan

## Slide 15: Schedule Details - Production

## Slide 16: Risks and Concerns
Scope
  While the CC system is the only way to substantially increase luminosity, CERN’s decision on implementing CCs depends upon the SPS test.
  System requirements for LHC not yet finalized.
Budget and Schedule
  Spending profile does not match LARP’s available funds
  LARP R&D Schedule is very aggressive for a 2015 delivery
    Even with all funding committed
Resources
  Many preferred resources already committed to several other projects.

## Slide 17: Scope Risk
Final decision on HL-LHC installation in 2016
LHC configuration to be determined
  Could be 6 (3+3) interleaved cavities in a single CM (total of 4 + spares needed) to using 3 CM with two interleaved cavities each (total of 12 + spares needed)
  LHC details to be studied- impacts effort and spares plan)
    LH vs. RH side
    H vs V crossing
External contributions hard to manage and in some cases still awaiting funding

## Slide 18: Schedule Risk
The short term schedule (LARP R&D) depends upon a spending profile that is beyond LARP’s financial capabilities
External contributions are needed to meet the goal of shipping one cryomodule to CERN at the end of 2015
  We will gain one year of LARP funding if schedule slips
We have some control over some external resources…
  Toohig, GARD (somewhat)
…and NO control over others
  CERN, UK, SBIR

## Slide 19: Risk Mitigation
LARP
  Schedule: While we are aiming at shipping at the end of 2015, LS2 is not scheduled until 2017
  Budget: CERN is committed to the project and could provide additional resources if needed
Construction
  Experience with R&D will help production
  Have ~30% cost contingency and ~ 1 yr. schedule float

## Slide 20: Organization
CERN leads the global collaboration
  Directly responsible for several tasks
    RF power and controls, local installation, cryogenics, machine protection…
US contributes well defined part of the project
  Cavities and cryomodules
Defined roles within LARP collaboration:
  BNL, ODU – cavity development with aux systems
    tuners, mode dampers….
  FNAL - cryomodule design and integration
  SLAC – Leads and coordinates EM modeling support
  FNAL, LBNL - beam dynamics studies
  Points of contacts defined at each lab
Welcome Niowave
  Built all three prototype cavities to date
  Funded by DOE SBIR program to build one cryostat

## Slide 21: External (non LARP) Contributions
UK (STFC) are requesting funding for 2014-17
  This would fund ~2 FTE/year towards CC design and testing
    Limited hardware budget, well below what we want
CERN committed to many aspects of the project
  Offered to help when and where needed and possible by EU rules
    IE. Niobium procurement
Phase II SBIR awarded to NioWave can be applied towards the goals of this collaboration

## Slide 22: Building a team
Multiple in person meetings
  LARP CM in November 2012
  Cryomdule integration meeting at FNAL in December 2012
  LARP CM in Napa in April 2013
  Cryomodule integration meeting with Niowave at FNAL in May 2013
Web + Audio conferences in between
  Plan to establish regular schedule

## Slide 23: Final Comments
Extremely talented team
  Important to allocate funding AND securing availability of key resources
Challenge of managing contributions outside LARP’s funding
    But everyone is committed to the common goals
Technical results are very encouraging
We are ready to continue working towards our goals
On track for CD-0

## Slide 24: Questions

## Slide 25: Cryostat Integration Meeting May 30, 2013 Results
The SBIR cryostat is going to be designed to be capable of going to the SPS test
  Will house two cavities
The Cryostat for the SPS test will NOT be the one for the final installation in the LHC.
  It *may* be compatible with a test in IP4, but this should not come at a big cost in time and money
  We’re only planning a test with a kick in one plane
  Will have two cavities
The current plan for the SPS is to run until the end of 2017
  We will still try to hold the delivery to CERN by the end of 2015
We don’t need external approval for the pressure vessel
  But need all traceable documentation
We need a more precise plan on who is doing the cryostat mechanical integration and H/V testing

## Slide 26: More Results
Should plan for an intermediate step of the dressed prototype cavities in a Vertical Test
  ANL may be a good place to test
We carry both design to a dressed cavity test

## Slide 27: Proposed Plan – 3 months
RFD + DQW modeling studies will continue
Models ready by the end of summer
RFD needs one test of prototype cavity
Niowave will support development of models, fabrication concepts…
FNAL will start developing 3D model of cryostat
  Same mount points?
CERN and FNAL will provide mechanical analysis support
SLAC will continue coordinating the CAD EM design

## Slide 28: Action Items
Beam Dynamics to tell us if and how much can the beampipe diameter change.
Resolve ASME vs. EU standards to simplify requirements on cryostat.
Finalize position of dummy beampipe.
  Can it go outside? Yes for US designs
  Can we reduce distance from cavity axis to edge of cryostat to 255 mm? If not, how much can we reduce?
Schedule next readytalk meeting

## Slide 29
End-loaded Cryostat Cost
Cryomodule cost roughly driven by cavity string
From. J. Mammosser (JLAB)