## Slide 1: IR Quadrupole Production Plan
Mike Anerella
LARP Review
June 10, 2013

## Slide 2
Scope
Assemble 20 (16 + 4 spares) Q1/Q3 quadrupole structures:
“structure” = coils clamped radially in aluminum shells, axially with stainless steel rods and end plates
  4.5 coils per quad = 90 coils total
Cold test all 20 quads
  Demonstrate 140 T/m Operation
  Field measurements
Satisfy CERN production delivery requirements with suitable margin
(4/2022 1st unit, 12/2022 16th unit)

## Slide 3
Work Breakdown
Superconductor cabling
Coil pack assembly
Coil pack assembly
Coil structure assembly
Coil structure assembly
He vessel, cryostat installation (temporary)
Horizontal Test facility installation & test
Vertical Test facility installation & test
Yoke / aluminum shell subassemblies
LBNL
FNAL (10)
BNL (10)
(Alternate breakdowns being discussed (single assembly site, single test site), but are not addressed herein)

## Slide 4
Coil Plan
 | Time (days) |  | 
Operation | BNL | FNAL | Production
React | 20.25 | 23 | 24
Impregnate | 30.75 | 26 | 30
Prep for cold mass assembly | 4 | 9 | 5
Coil fabrication is a dominant cost and schedule element in the program
→ prompted detailed review
After independent BNL & FNAL estimates & subsequent meetings to review:
Example of added benefit of meetings: realization that FARO Arms for cmm inspection must be budgeted for each location; more efficient operation, standardized inspection, etc.

## Slide 5
Resulting Coil Schedule
1 coil every 15 days
Excludes measurement & midplane ground insulation (covered later)
(details next slide)
Series reactions=1 oven needed
Parallel effort:
(cure OL/wind IL
Parallel effort:
2 impregnation lines (but 1 station)
Reaction fxt use = 3 needed

## Slide 6
Coil schedule details
Resources per location:
Operation | Techs | Comments
Wind / cure | 2.5 | 2 techs wind/cure inner, wind outer - 0.5 tech cures outer*
React | 2 | 1 line
Impregnate | 4 | 2 lines in parallel
Prep for cm assy | 0.5 | *Same tech as outer layer cure
Total Tooling per location:
Item | Qty | Comments
Winding mandrel assy | 2 | Includes pushers, spacers, segments, etc.
Reaction oven | 1 | 
Reaction tooling | 3 | Prep occurs in parallel w/reaction, + reaction tool is occupied during 1st ~ 10 days of impregnation
Impregnation station | 1 | Actual install/impreg/remove takes only ~ 1/3 of duration
Impregnation tooling | 2 | 
→ 7 coil techs total (excludes supervision)
Note that 1 of each are available from R&D

## Slide 7
Complete Coil schedule
(1/2 production x 2 locations)
1st 2 coils with 2x duration (new tools)
9/10/20 finish
3/15/17 start
(after last R&D coil)

## Slide 8
Coil Prep schedule
(1/2 production x 2 locations)
Cmm inspection
Install midplane ground insulation
Part time use of 3rd coil winder

## Slide 9
Yoke / Shell Subassembly
(1/2 production shown x 2 parallel lines)
Parallel effort to production
Early start due to (slightly) longer task duration
Assembly (2 x 2 Techs), Strain Gauge Installation (1 Tech) performed in parallel
→All subassemblies available for production, including shipping time
Need date
10/3/18
3/11/19
1/7/21

## Slide 10
Quadrupole Assembly & Test
(1/2 production x 2 locations)
Coil Pack
Coil Structure
1st assy with 2x duration
1st test with 1.5x duration
Test time based on FNAL
(BNL test time TBD)
Test setup in parallel w/ He vessel , cryostat assy
(2nd set of vessels req’d)
(2 testing techs,
4 assy/disassy techs)
Coil Pack (2 techs) in parallel w/ Structure (2 techs)
NOT Optimized yet
Coil 5 done
Coil 15 done

## Slide 11
Complete Production Schedule
(1/2 production x 2 locations)
April 2022 CERN need date (30 months float)
December 2022 CERN need date (18 months float)

## Slide 12: Summary
Detailed estimates in support of overall plan
Efficiencies beyond R&D achieved through the use of multiple tooling sets
Plan meets CERN delivery requirements with adequate schedule float
Resources, i.e. staffing levels are manageable
Some optimization is still needed