## Slide 1: HL-LHC IR Quadrupole Magnet Project Overview
GianLuca Sabbi
Internal Review of proposed US contributions to HL-LHC
Fermilab, June 10, 2013

## Slide 2
Agenda and Presentation Outline
Presentation outline:
LARP magnet program goals and technical milestones
Status of HiLumi design study
Prototype development plan, CERN/GARD contributions
Construction project plans
  Deliverables, schedule and funding profile
Specific challenges and risk factors (near/medium term)

## Slide 3
LARP Magnet Program
Goal: Develop Nb3Sn quadrupoles for the LHC luminosity upgrade
Operate at higher field (larger aperture) and temperature margin
R&D phases:
  2005-2010: technology development: conductor, coil, structure
  2007-2012: length scale-up from 1 to 4 meters
  2009-2014: incorporation of accelerator quality features
Program achievements to date:
  TQ models (90 mm aperture, 1 m length) reached 240 T/m gradient
  LQ models (90 mm aperture, 4 m length) reached 220 T/m gradient
  HQ models (120 mm aperture, 1 m length) reached 184 T/m gradient
Current activities:
  Optimization of HQ: full demonstration of accelerator quality
  Fabrication of 4-meter Long HQ (LHQ) coils and test in mirror
  Design and planning of the MQXF IR Quadrupole development

## Slide 4
LARP R&D Milestones
2004-2006 SQ models:
        Conductor/structure performance in simplified configuration
2006-2008 LR models
        Racetrack coil & shell structure scale-up from 0.3 m to 4 m
2006-2010 TQ models
        Technology for cos2q coils, new conductors, high stress test
2007-2012 LQ models
        Scale up of cos2q quadrupole configuration to 4 m length
2008-2014 HQ models
        Aperture scale-up, stress/protection limits, accelerator quality
2010-2014 LHQ models
        Scale-up of optimized coil technology to 4 m length

## Slide 5
Current activities
Design of “QXF” 150 mm short models and prototypes (LARP+CERN)
  Main focus on cable R&D and tooling design
  Forward look at other aspects to ensure compatibility with requirements
Completing R&D in support of QXF and HL-LHC design
  HQ02 test underway, with very positive results
    Testing up to 15kA, 170 T/m (82% SSL at 1.9K, 91% SSL at 4.5K)
    Fast training to 80% operating level: 1-2 quenches
    Flat ramp rate dependence up to 150-200 A/s
    Large reduction (x10-20) of eddy current harmonics with core
  LHQ coil fabrication in process, first mirror test by the end of the year
  HQ03 starting (with GARD support): uniform coils, reproducibility

## Slide 6
HiLumi Design Study Progress
07/12: Choice of aperture and technology,150 mm aperture Nb3Sn
03/13: Defined baseline IR layout (aperture, length, gradient)
Critical new information is continuously being provided:
  Cooling options and corresponding channel sizes
  Shielding options and corresponding radiation doses
  Field quality tables and limits on individual effects
Main outcome: we have sufficient flexibility in the overall design to find solutions compatible with available magnet technology
  Interfacing with work packages on optics, layout/correctors, energy deposition/shielding, cooling, powering & quench protection
  Performance provided by current conductors, epoxy resins, coil technology, support structures, is acceptable for HL-LHC
  Additional improvements will benefit the project but are not a precondition to Nb3Sn IR Quadrupoles implementation

## Slide 7
Prototype Development Plan
Aperture selection (July 2012) triggered a revision of the LARP plan:
  Initial proposal: continuation of 120 mm program in parallel with 150 mm short models, then scale up (first long prototype test ~2017)
  DOE guidance: curtail 120 mm program and increase QXF resources to test a long prototype ASAP (by end of 2015)
Current strategy: work with CERN and GARD to augment resources
  Preserve critical elements of 120 mm program (w/GARD support)
  Strong (~2/3) CERN role in short model program (SQXF)
  4-m long prototypes (LQXF) entirely under US responsibility
Key milestones of prototype development program:
  SQXF01 tested 4/15 (LARP+CERN); 2 more in 8/16, 2/17 (CERN)
  LQXF01 tested 3/16; LQXF02 in 4/17, LQXF03 in 9/17 (all LARP)

## Slide 8
GARD Contributions
Four GARD program in the superconductor and magnet areas
  Conductor/materials: BNL, CDP (supports development in industry)
  Full materials/technology/magnet capabilities: FNAL, LBNL
Discussions of possible contributions started last October: several video-meetings and one meeting at CM20 with CERN participation
A LARP document was issued to explain program needs
Updated GARD proposals were recently delivered:
  CDP: conductor procurement and process improvements for production, conductor development
  BNL: strand/cable QA, conductor studies
  FNAL: test facility upgrade, mirror structure, conductor development
  LBNL: HQ03, design/analysis, conductor development, rad-hard epoxy
Key elements provisionally incorporated in plans presented at project review
Discussions toward an integrated plan to be resumed in the coming weeks

## Slide 9
Construction Project Proposal
Prepared in response to DOE request following the 2012 review
Funding envelope: 200 M$ construction + 4 more years of LARP at constant funding level (12.4M$)
Planning group formed with contributors from all Labs
“Scope selection” proposal submitted to DOE in December
Magnet plan includes:
  Completion of R&D on 120 mm aperture models
  Development of 150 mm “QXF” prototypes (with CERN)
  Infrastructure upgrades for magnet production
  Fabrication of cold masses for Q1 and Q3 elements:
    4 m long; 2 pre-series, 16 cold masses and 2 spares
    2 production lines for coils and assembly
    All magnets tested in the US before shipping to CERN

## Slide 10
Project schedule
FY
CD0
2
CD3
1
18 month
18 month

## Slide 11
Funding Profile
Total IR Quad R&D, prototype and production: 172M$
Production includes 35% contingency (design, labor, materials)
External contributions (CERN, GARD) not included
Project management not included
M$

## Slide 12
Assumed external contributions
Prototype development phase
  CERN: HQ testing; QXF short model program (tooling, coils, structure, testing); 250kg of conductor ordered in FY14 (under discussion)
  CDP: Conductor procurements for about 500kg in FY13-14
  LBNL: Labor for HQ03 coil fabrication, magnet assembly, first test
  FNAL: Labor for QXF mirror and LQXF test stand
Production phase
  CERN: Half of the cold masses, integration in cryostat and final testing of US cold masses
External contributions are not included in LARP budget tables presented at the review
Additional contributions proposed by GARD (supporting studies, characterization and qualification of new conductors) are less critical and were not included in the baseline plan, pending further discussion

## Slide 13
Challenges and risk factors
Transitions from R&D to project-like to project
  Several aspects: technical, organization, funding (e.g. FY15-16)
Expanded collaboration to augment resources in prototype phase
  LARP deliverables critically depend on external contributions
  So far, tentative agreements but no formal framework/commitments
  Differences in design approaches, goals, organization, time zones…
Distribution of work among labs during production
  LARP was directed and evolved into an integrated “virtual-lab” model
  Critical to R&D success, but less efficient in production
  Key expertise and infrastructure is distributed across labs
Plans for magnet testing prior to shipping to CERN
  No facility available for LQXF; proposals from FNAL & BNL
  Consider test goals, cost/schedule for facility upgrade and operations
  More analysis is needed - planning a dedicated review later this year

## Slide 14
Summary
Successful R&D leading to selection of Nb3Sn as baseline for HL-LHC
Integrated design approach by HiLumi DS work packages: global optimization to exploit advantages of Nb3Sn and cope with limitations
DOE guidance following the 2012 review led to scope selection proposal and reorganization of the magnet program
Baseline plans, schedule and budget were developed as part of the scope selection proposal and have been refined in recent months
Schedule: task durations are realistic but prototype development has overlapping steps
Budget: Funding is tight especially at the start; significant contributions from CERN and GARD programs have been assumed based on tentative agreements and will need to be formalized in the coming months