## Slide 1: Crab Cavity Cryomodule Design and Integration
Tom Peterson (FNAL) LARP Internal Project Review
10 June 2013

## Slide 2: Outline
References
Project goals
  Dec 2012 meeting summary
  Niowave SBIR
  CERN Functional Requirements Specification
Pressure code
Dressed cavity concepts
Near term plans
Schedule and longer term plans
Collaborators and organization

## Slide 3: References – we have several sources of important information for the design
Presentations at the 13-14 December 2012, LHC Crab Cavity Engineering Meeting at Fermilabhttp://indico.cern.ch/conferenceDisplay.py?confId=136807 and summary report (CERN-ATS-2013-033)
Presentations at the 9 April 2013, Crab Cavity session of the LARP meeting in Napahttps://indico.fnal.gov/conferenceOtherViews.py?view=standard&confId=6164
Presentations at the 30 May 2013, Crab Cavity meeting at Fermilab https://indico.fnal.gov/conferenceDisplay.py?confId=6859
“Functional Specifications of the LHC Prototype Crab Cavity System” https://cds.cern.ch/record/1520896

## Slide 4: EXECUTIVE SUMMARY (Dec 2012 mtg) Rama Calaga, Erk Jensen
1. Crab cavity tests with SPS beams are a mandatory validation step before any installation in the LHC. All RF, cryogenic, vacuum operation should be comprehensively tested with the SPS installation along with all relevant beam experiments to determine the effects on hadrons and machine protection.
2. A two-cavity cryomodule with identical cavities is seen as the best option for an SPS test of the crab cavity system.
3. All features compatible with and relevant for the final LHC system should be retained in the SPS cryomodule to the extent feasible. Therefore, the design of the SPS cryomodule can deviate to adapt to its environmental constraints.
4. All RF and cryogenic interfaces should be placed on the top with vertical mounting of the coupler and cryogenic feeds.

## Slide 5: EXECUTIVE SUMMARY Rama Calaga, Erk Jensen (continued)
5. The choice of the power coupler dimensions and heat load limitations will be fixed as soon as possible.
6. The bypass beam standard beam pipe will be placed outside the cryostat vacuum by redesigning the Y-chamber for a larger separation. This allows for easier swapping of cryomodules and limits the risk of vacuum and cavity failures on SPS operation.
7. A dummy beam pipe at 194 mm like in the LHC should be foreseen and be placed in the liquid Helium volume if necessary. It can additionally be used to reinforce the cavity.
8. Tuning requirements from the beam of approximately 60 kHz with a resolution of 40-200 Hz depending on the cavity bandwidth should be foreseen. In addition, cavity specific frequency tuning to compensate Lorentz force detuning, cool-down and microphonics should be accounted for in the tuner design.

## Slide 6: Niowave SBIR supports another major center of effort

## Slide 7: Functional Specification from CERN

## Slide 8: General plan for test
Two cavities in a horizontal cryostat
Test first at SM18
Then test in SPS

## Slide 9: Location for Test in SPS

## Slide 10: Crab Cavity Test Location Elevation View

## Slide 11: Crab Cavity Cryostat Envelope

## Slide 12: Satisfy European Pressure Directive for Helium Vessel MAWP = 1.8 bar
MAWP = 1.8 bar implies 30 liters
to 110 liters for Category I

## Slide 13: Pressure code
We will discuss whether the ASME code may satisfy CERN as an equivalent standard for pressure vessels
  Our final focus magnet collaboration with CERN essentially accepted ASME (but with some additional requirements)
  We have built vessels to the European Pressure Directive with assistance of agents in the US who are authorized to make the inspections and approvals, but it is expensive
ASME piping code or equivalent also be required for cryostat piping

## Slide 14: Helium vessel and cryostat concepts
The following slides provide views of some of the helium vessel and cryostat work done so far
The concepts are quite different in terms of coupler, tuner, and helium vessel configurations
How can we best accommodate all cavity options, given the lack of a cavity down-selection?
It is doubtful that we can design a single test cryostat with features to install and remove RF cavities of different designs and also satisfy the SPS constraints
However, we will first investigate that option for any two of the three designs

## Slide 18
STFC Daresbury concept for reference

## Slide 19
STFC Daresbury concept for reference

## Slide 20: Resource (personnel) requirements and tasks for the next 6 months
We plan about 1 full FTE over the next 6 months
  Engineering and scientist time (~1/2)
  Designer time (~1/2)
For example, a designer could take 3-D models of cavities and under our direction at Fermilab start building cryostats around them. We would follow the groundwork laid by the cavity designers and by STFC Daresbury, begin by considering all the cavity configurations, and also work with Niowave to remain consistent with SBIR goals.

## Slide 21: Longer term work plan for the SPS cryostat
In the longer run, we need to work with at most two of the three cavity designs for the SPS test
  We should have a down selection by early 2014 from three to two cavity designs
We propose that STFC and Fermilab divide the cryostat design work, both with help from CERN
  STFC will develop the cryomodule design for either their 4-rod cavity or one of the two US cavities
  Fermilab with assistance from CERN will create the cryomodule design for the other cavity ( a US cavity)
STFC, Fermilab, and CERN will collaborate on common features in the two cryostat designs
Niowave will focus on working out from the cavity to a dressed cavity design, working with all three types

## Slide 22: Overall SPS cryostat cost and schedule estimate
For the SPS prototype cryostat we estimate
2 yrs x 3 FTE
  ~3 FTE-yr engineer/scientist +
  ~3 FTE-yr designer
Fermilab – 1 to 2 FTE
CERN – 1 to 2 FTE
STFC will design the other cryostat, but we will take advantage of some of their design features, incorporating some of their design effort into our cryostat

## Slide 23
From Alex, April 2013 LARP meeting

## Slide 24: Schedule comment
Design process for new cryostat or cryogenic box is typically 2 to 3 years
  After a complete definition of requirements is known
    Details of associated components (e.g., tuner, input coupler)
    Which is the first year or more of conceptual design work, then . . .
  ~1 yr engineering and design/drafting
  ~1 yr procurement and fabrication
Given the uncertainties regarding final cavity selection and the new work involved, it would be very challenging to meet the previously shown 2015 completion time frame

## Slide 25: Next meetings
We will plan a visit to CERN
  Cannot be in the next few months due to various prior commitments
Meanwhile – ReadyTalk meetings to help communication between face-to-face meetings (plus the usual e-mail, phone calls, etc., of course)
Suggestions for our collaboration are welcome now and at any time – communication will be most important for success