## Slide 1: Technology Development MAP Friday Meeting
Harold Kirk
Brookhaven National Laboratory
July 12, 2013

## Slide 2: Outline
TD Highlights
L2 Summary reports
Topical Report - Modular Cavity Status , C. Adolphsen, SLAC

## Slide 3: Technology Development Highlights for June, 2013
RF Studies
  Modular 805MHz Cavity on track for delivery by end of FY13 (SLAC, LBNL)
  All-season cavity re-measurement on hold
Targets
  Studies for 1MW, 3GeV proton target
Magnets
  Repairs of YBCO coils for high-field solenoid
  BISCCO 2212 coil tested at 4.20 K
12 TD related abstracts submitted to NA-PAC

## Slide 4
Modular cavity (collaboration with SLAC)
  Cavity fabrication in progress and will be delivered to Fermilab by end of FY13
  Test plan is being developed
  Interface document between LBNL and FNAL nearly ready
201 MHz MICE prototype cavity
  RF coupler fabrication at LBNL
  Some material and parts received
  TiN-coating setup at LBNL
Modular cavity
  Fabrication at SLAC continues
  Ready for PO of the Be plates
  Bi-weekly meetings at SLAC to monitor/oversee fabrication progress
Support the single cavity installation at MTA, Fermilab
Fabrication of 201-MHz coupler at LBNL
Cryostat (vacuum vessel) fabrication for MICE CC magnet at LBNL continues
Sign-off of the interface document between LBNL and Fermilab
Continue the fabrication of the modular cavity at SLAC
Support of the 201 MHz installation at MTA, Fermilab
Oversee 201-MHz cavity coupler fabrication at LBNL
TiN-coating of the coupler setup preparation at LBNL
Oversee the CC cryostat fabrication at LBNL
Continue the modular cavity fabrication
EP of the remaining MICE cavities at LBNL
Development of the modular cavity testing plan
Data analysis of previous 805 MHz testing results
MP simulation studies of the MICE cavity and coupler with external magnetic fields and explore other possible solutions
Fabrication of two 201 MHz RF couplers for the first MICE cavity in preparation for the testing at MTA
Support MTA RF testing programs
PO of Be plates for the modular cavity
MICE magnets: SS and CC
Oversight of the fabrication of RF couplers for MICE prototype cavity
July 12, 2013
03 01: Normal Conducting RF
Derun Li

## Slide 5
Begun examining stored energy issues for both 325MHz and 650MHz SRF cavities
Progress for the SRF program reported at the MAP Collaboration meeting at FNAL
500MHz cavity preparations by Research Instruments
Study of electroforming Cu on Nb process
Testing of 500 MHz explosion-bonded cavities expected in late summer. Testing to be completed end of FY13
Preparation of Cu on Nb electroformed 1.3GHz cavity by end of FY13
Research Instruments shipment of 500 MHz cavities expected by end of FY13
.
12 July, 2013
3.2 – Superconducting RF
Don Hartill

## Slide 6
Rapid Cycling Magnets /HTS : Completed engineering design of Rapid Cycling HTS Magnet test system to be assembled at E4R enclosure
Summary of Previous Month
HTS (2212) Program - The 2212 coil under development was instrumented and installed on coil probe. It was tested at 77 K and will be tested in 4.2 K up to 14 T on 07/11/13. A new acoustic emission sensor system has been set up for diagnosing coils and also for quench detection.
HTS Magnets / ReBCO - ReBCO The repair procedure described earlier has now been applied to all 24 pancakes of 100 mm midsert. 14 of 24 of those pancakes have been re-tested at 77 K. This includes testing of all of those 6 pancakes whose performance changed noticeably during a 77 K test. Test results show that 3 of those 6 pancakes have been fully repaired; the rest only partially.
Helical Solenoid (HCC) – Mechanical support simulations have been carried out; preliminary work on the prototype manufacturing process; consensus developed on the support structure concept and material to be used (Stainless steel 316 or similar non-magnetic)
General Magnet Design – No activity this month.
Rapid Cycling Magnets / Conv – We are working on the design of an ultra low carbon steel 1.8 Tesla dipole with 15mm gap.
Rapid Cycling Magnets / HTS -Presented at MAP Collaboration meeting the HTS-based magnet concept for Muon Accelerator. Fabrication of magnet and leads cryostat components partially completed
Upcoming Work (Next Month)
HTS (2212) Program – Coil test results will be analyzed. A new coil will be wound, reacted, and tested to verify the result obtained. It will also be prepared to quench characteristics tests.
HTS Magnets / ReBCO – A decision to wind more coils or to build midsert with 20 pancakes (it has to be an even number) instead of 24 will be made. Performance of half-midsert and insert during previous 4 K tests (they were able to operate at significant higher current than initially designed) and budget (tight) will play a role
Helical Solenoid (HCC) – Design of the support structure (mechanical drawings) ; manufacturing of the support structure to begin (2 months); design of the external shell
General Magnet Design – Discussions with machine design and modeling group will determine focus and level of effort
Rapid Cycling Magnets / Conv – Working on the next planned prototype. Pole shaping will be needed if a uniform field is to be achieved.
Rapid Cycling Magnets /HTS – Proceed with splicing of HTS strands to power lead; completed fabrication of magnet and leads cryostat components at VMS; continue studies of HTS-based rapid cycling magnet technology for Muon Accelerator
HTS (2212 ) Program – Continue work to develop tooling and Rutherford cable from the improved conductor; wind, react, and test coil using 1.2 mm single strand using overpressure processing; 4.2K testing is next.
HTS Magnets/ReBCO – ReBCO Solenoid – Prepare for 4 K test of 100 mm midsert solenoid.
Helical Solenoid (HCC) – Begin fabricating first model: winding and reaction of a short model (40 turns per layer, 2 layers)
General Magnet Design – continued collaboration on development of CR/IR magnets: cross-sections, field characteristics, heat loads, etc. with CR Group (Mokhov) on requirements, as needed
Rapid Cycling Magnets – HTS Perform splicing of HTS strands to copper blocks connecting with leads; Fabricate cryostats for magnet and leads; continue study of HTS-based rapid cycling magnet technology for Muon Accelerator; Write a APC Note on feasibility of Muon Accelerator with HTS-based rapid-cycling magnet technology
Rapid Cycling Magnets – Conv Develop procedure for transposed Cu strands; test and compare to calculations
[….]
July 12, 2013
J. Tompkins
Magnets – 03-03

## Slide 7
Ding: Pion-production calculations for 3 GeV proton beam exhibit peculiarities that require clarifcation.
Weggel: Magnetic shielding of final-focus quads from the 15-20 T target solenoid would require ~ 300 tons of iron
Pasternak: Switch to superconducting final-focus quads which won’t need magnetic shielding
Sayed: Target-System “taper” optimization for a ~325-MHz Buncher/Rotator.
Zhan: Switch emphasis to code development of level-set method for ANSYS-FLUENT to model free jet.
McDonald: Contributions to Target section of the IDS-RDR.
Extend target system conceptual design up to start of buncher (including chicane in decay/drift region).
A big new effort, to continue over several quarters, is to evaluate Target-System options for staging scenarios, with initial emphasis on 3-GeV proton energy, 1-MW power. Reconsider a toroidal-horn option, as well as the (baseline) solenoid- capture option.
Must validate particle production at 3 GeV before can proceed with staging studies.
12 July, 2013
03.04 Targets and Absorbers
Kirk T. McDonald

## Slide 8
201-MHz vacuum RF: assembly work about to start
Infrastructure – on track but late: beamline upgrade, RF switch re-commissioning, station-2 vacuum system
Data analysis: HPRF beam test PRL in final editing (B. Freemire, K. Yonehara, A. Tollestrup, M. Chung); all-season cavity data under review
All-season cavity: disassembly, testing
Modular cavity: vacuum and instrumentation parts ordered
201-MHz Single-Cavity Module: coupler parts/materials ordered (A. DeMello, YT); progress on instrumentation (L. Somaschini, D. Peterson, R. Pasquinelli, A. Moretti); assembly procedure prepared (J. Volk); more parts moved to Lab-6
805-MHz all-season cavity: operation in B>3T?
DL-HPRF cavity: retesting with dielectric rod
Old pillbox cavity: install grid windows
201-MHz Single-Cavity module: RF control system upgrade, instrumentation tests, mount cavity in Lab-6, start LLRF measurements
Modular cavity: instrumentation and inspection setup
Data analysis/publication
magnetic insulation
Be-Cu buttons
HPRF beam test
Current program
All-season cavity in magnetic field
B > 3T
Dielectric-loaded HPRF
Next on the list
Grid windows on pillbox cavity
201-MHz Single-Cavity Module
New 805-MHz modular cavity
Other
Beamline commissioning
Single-Cavity Module assembly, installation
Pillbox with grid windows, all-season cavity high-B run
Beamline commissioning
Mechanical support for RF program
Electrical support for beamline upgrade
12 July, 2013
MuCool Test Area
Yağmur Torun