## CoverSheet
g-2 Project Office
Basis of Estimate Form (BoE)
Document Information
Document Number | GM2-doc-712
Date Created | 2013-07-17
Prepared by | Brian Drendel
Contributing Authors | Nathan Eddy, Peter Prieto
WBS Category Number | 476.02.04.03.05
WBS Category Name | Instrumentation: Wall Current Monitors
Control Account | To be provided by project management
Supporting Documents:
1
2
3
4
5
6
7
8
9
10
Dictionary Description
Description/Technical Objective/Scope: This L5 element includes design, repurposing, fabrication and installation of Wall Current Monitors and associated electronics used to measure low intensity secondary beam currents downstream of the target starting in the M2 line and ending in the g-2 line. Deliverables: Electronics, hardware Interfaces/Relationships: Beamlines
Please insert a hyperlink for each listed source.
1. Right-click on cell in the second column
2. Select Hyperlink
3. Insert the hyperlink in the Address field on the bottom of the page
4. Click OK

## PreliminaryDesign
Preliminary Design for Instrumentation: Wall Current Monitors
Dictionary Description:
The priliminary design will explore the viability of using the Mu2e M4 line design Wall Current Monitor for g-2 operations.
Activities and Dependences:
Activity # | P6 Activity # | Activity Name | Activity Description | [6 empty] | Not Used | Estimate Type (Use pull-down list) | Not Used | Alternate Funding? (use pull-down list) (if none, leave blank) | Source Documentation # (s) from CoverSheet (1, 2, 3, etc...) | Predecessor Activity # (s) within this BoE (100, 110, 120, etc...) | Duration (working days) | Notes (List steps for each activity here):
100 |  | Project Oversight | (ACD) Coordination and oversight of activities associated with the preliminary design | [7 empty] | Engineering Estimate III (50%) |  |  |  | Start of Preliminary Design | 66 | Estimate 50 hours of Peter's time
110 |  | Install Prototype | (ACD) Install prototype detector in pbar - detector, stand, cables | [7 empty] | Engineering Estimate III (50%) |  |  |  | Start of Preliminary Design | 22
120 |  | Develop Prototype Electronics | (ACD) Develop and install prototype readout system - electronics and software | [7 empty] | Engineering Estimate III (50%) |  |  |  | Start of Preliminary Design | 44 | 2months programmer, 2 months
130 |  | Perform Beam Tests | (ACD) Coordination and oversight of activities associated with the preliminary design Peform dedicated beam tests to evaluate system performance | [7 empty] | Engineering Estimate III (50%) |  |  |  | 110, 120 | 44 | 2 months
140
150
160
170
180
190
200
210
220
230
240
250
260
270
280
290
None
Hourly Labor Estimates (Some of these labor types could be assessed as M&S from the project perspective):
Activity # from above table (Use pull-down list) | P6 Activity # | Activity Name | Resource ID Category Prefix (Use pull-down list) | Indirect reference to fix cut and paste error | Resource ID Category Suffix (Use pull-down list) | Indirect reference to fix cut and paste error | Resource ID Validity Check (Populated Automatically) | Not used | Base Estimate (hours) (Enter without any units) | Indirect reference to fix cut and paste error | BoE Pay Rate (FY13 $/hr) (From lookup table) | Not used | BoE Base Estimate (K$) (Auto Populated) | Estimate Type (Populated from Activities Table) | Contingency (%) (Auto Populated) | Base + Contingency (hours) {Calculated} | On-project costs Base + Contingency BoE(K$) {Calculated FY13} | Notes
100 | TBD | Project Oversight | FNAD | FNAD | ELEC_DESIGN_SR | ELEC_DESIGN_SR | FNAD_ELEC_DESIGN_SR |  | 50 | 50 | 194 |  | 9.7 | Engineering Estimate III (50%) | 50% | 75 | 14.55
100 | TBD | Project Oversight | FNAD | FNAD | ENGNRING_PHYST | ENGNRING_PHYST | FNAD_ENGNRING_PHYST |  | 20 | 20 | 170 |  | 3.4 | Engineering Estimate III (50%) | 50% | 30 | 5.1
110 | TBD | Install Prototype | FNAD | FNAD | MECH_DESIGN_EN | MECH_DESIGN_EN | FNAD_MECH_DESIGN_EN |  | 40 | 40 | 157 |  | 6.28 | Engineering Estimate III (50%) | 50% | 60 | 9.42
110 | TBD | Install Prototype | FNAD | FNAD | MECH_ASMBY_TECH | MECH_ASMBY_TECH | FNAD_MECH_ASMBY_TECH |  | 20 | 20 | 97 |  | 1.94 | Engineering Estimate III (50%) | 50% | 30 | 2.91
110 | TBD | Install Prototype | FNAD | FNAD | ELEC_TECH | ELEC_TECH | FNAD_ELEC_TECH |  | 20 | 20 | 97 |  | 1.94 | Engineering Estimate III (50%) | 50% | 30 | 2.91
120 | TBD | Develop Prototype Electronics | FNAD | FNAD | ELTN_DESIGN_EN | ELTN_DESIGN_EN | FNAD_ELTN_DESIGN_EN |  | 160 | 160 | 159 |  | 25.44 | Engineering Estimate III (50%) | 50% | 240 | 38.16
120 | TBD | Develop Prototype Electronics | FNAD | FNAD | CTRL_SYSTM_EN | CTRL_SYSTM_EN | FNAD_CTRL_SYSTM_EN |  | 160 | 160 | 163 |  | 26.08 | Engineering Estimate III (50%) | 50% | 240 | 39.12
130 | TBD | Perform Beam Tests | FNAD | FNAD | ELTN_DESIGN_SR | ELTN_DESIGN_SR | FNAD_ELTN_DESIGN_SR |  | 80 | 80 | 205 |  | 16.4 | Engineering Estimate III (50%) | 50% | 120 | 24.6
[9 empty] | 550 |  |  |  | 91.18 |  |  | 825 | 136.77
M&S Cost Estimate (Do not double-enter any labor M&S reported in above table):
Activity # from above table (Use pull-down list) | P6 Activirty # | Activity Name | Item Purchased | Not used | Resource ID (Use pull-down list) | Indirect reference to fix cut and paste error | Overhead multiplier (Automatically populated) | N ot Used | Base Estimate (FY13 $K) {Enter without $ or K} | Indirect for Base Estimate | Estimate Type (Populated from Activities Table) | Not Used | Contingency (%) (Auto Populated) | On-project Costs Base + Contingency + Overhead (FY13 $K) {Calculated} | Notes
[9 empty] | 0 |  |  |  |  | 0
Date Scheduler Authorized to Enter Activities into RLS (change log begins):
Change Log: All changes need to be tracked after the scheduler has been authorized to enter data from this sheet into the RLS
Activity # from above table (Use pull-down list) | P6 Activity # | Activity Name | Description (added activity, activity no longer used, added 20 hours of <resource ID> labor to activity, added <Item Description> M&S item to activity, added/deleted predecessor to activity, changed estimat type for activity, changed funding source, etc.) | [6 empty] | Estimate Type (Populated from Activities Table) | Date of Change to BoE |  | Date Entered into Schedule

## FinalDesign
Final Design for Instrumentation: Wall Current Monitors
Dictionary Description:
The final design will make the final determination on the viability of using the Mu2e M4 line Wall Current Monitor design for g-2 operations.
Activities and Dependences:
Activity # | P6 Activity # | Activity Name | Activity Description | [6 empty] | Not Used | Estimate Type (Use pull-down list) | Not Used | Alternate Funding? (use pull-down list) (if none, leave blank) | Source Documentation # (s) from CoverSheet (1, 2, 3, etc...) | Predecessor Activity # (s) within this BoE (100, 110, 120, etc...) | Duration (working days) | Notes (List steps for each activity here):
300 |  | Project Oversight | Coordination and oversight of activities associated with the final design | [7 empty] | Engineering Estimate III (50%) |  |  |  | Start of Final Design | 88 | 20 hours of Peter's time
310 |  | Analyze Prototype Performance | Analyze the performance of system - hardware, electronics, & software | [7 empty] | Engineering Estimate III (50%) |  |  |  | Start of Final Design | 44 | 2 months - Peter (80 hours), Ning (120 hours), Programmer (120 hours)
320 |  | Model detector changes | Perform Microwave Studio analysis to improve detector performance | [7 empty] | Engineering Estimate III (50%) |  |  |  | Start of Final Design | 44 | 2 months - Randy (320 hours)
330 |  | Finalize Design | Make any necessary changes to system design - hardware, electronics, & software | [7 empty] | Engineering Estimate III (50%) |  |  |  | 310, 320 | 44 | 2 months - MechE (40 hours), drafter (80 hours), Ning (40), Programmer (160)
340
350
360
370
380
390
400
410
420
430
440
450
460
470
480
490
None
Hourly Labor Estimates (Some of these labor types could be assessed as M&S from the project perspective):
Activity # from above table (Use pull-down list) | P6 Activity # | Activity Name | Resource ID Category Prefix (Use pull-down list) | Indirect reference to fix cut and paste error | Resource ID Category Suffix (Use pull-down list) | Indirect reference to fix cut and paste error | Resource ID Validity Check (Populated Automatically) | Not used | Base Estimate (hours) (Enter without any units) | Indirect reference to fix cut and paste error | BoE Pay Rate (FY14 $/hr) (From lookup table) | Not used | BoE Base Estimate (K$) (Auto Populated) | Estimate Type (Populated from Activities Table) | Contingency (%) (Auto Populated) | Base + Contingency (hours) {Calculated} | On-project costs Base + Contingency BoE(K$) {Calculated FY14} | Notes
300 | TBD | Project Oversight | FNAD | FNAD | ELEC_DESIGN_SR | ELEC_DESIGN_SR | FNAD_ELEC_DESIGN_SR |  | 20 | 20 | 198 |  | 3.96 | Engineering Estimate III (50%) | 50% | 30 | 5.94
300 | TBD | Project Oversight | FNAD | FNAD | ENGNRING_PHYST | ENGNRING_PHYST | FNAD_ENGNRING_PHYST |  | 20 | 20 | 173 |  | 3.46 | Engineering Estimate III (50%) | 50% | 30 | 5.19
310 | TBD | Analyze Prototype Performance | FNAD | FNAD | ELEC_DESIGN_SR | ELEC_DESIGN_SR | FNAD_ELEC_DESIGN_SR |  | 80 | 80 | 198 |  | 15.84 | Engineering Estimate III (50%) | 50% | 120 | 23.76
310 | TBD | Analyze Prototype Performance | FNAD | FNAD | ELEC_DESIGN_EN | ELEC_DESIGN_EN | FNAD_ELEC_DESIGN_EN |  | 120 | 120 | 158 |  | 18.96 | Engineering Estimate III (50%) | 50% | 180 | 28.44
310 | TBD | Analyze Prototype Performance | FNAD | FNAD | CTRL_SYSTM_EN | CTRL_SYSTM_EN | FNAD_CTRL_SYSTM_EN |  | 120 | 120 | 167 |  | 20.04 | Engineering Estimate III (50%) | 50% | 180 | 30.06
320 | TBD | Model detector changes | FNAD | FNAD | AC_EXP_PHYST | AC_EXP_PHYST | FNAD_AC_EXP_PHYST |  | 320 | 320 | 172 |  | 55.04 | Engineering Estimate III (50%) | 50% | 480 | 82.56
330 | TBD | Finalize Design | FNAD | FNAD | MECH_DESIGN_EN | MECH_DESIGN_EN | FNAD_MECH_DESIGN_EN |  | 40 | 40 | 160 |  | 6.4 | Engineering Estimate III (50%) | 50% | 60 | 9.6
330 | TBD | Finalize Design | FNAD | FNAD | MECH_DRAFTER | MECH_DRAFTER | FNAD_MECH_DRAFTER |  | 80 | 80 | 70 |  | 5.6 | Engineering Estimate III (50%) | 50% | 120 | 8.4
330 | TBD | Finalize Design | FNAD | FNAD | ELEC_DESIGN_EN | ELEC_DESIGN_EN | FNAD_ELEC_DESIGN_EN |  | 40 | 40 | 158 |  | 6.32 | Engineering Estimate III (50%) | 50% | 60 | 9.48
330 | TBD | Finalize Design | FNAD | FNAD | CTRL_SYSTM_EN | CTRL_SYSTM_EN | FNAD_CTRL_SYSTM_EN |  | 160 | 160 | 167 |  | 26.72 | Engineering Estimate III (50%) | 50% | 240 | 40.08
[9 empty] | 1000 |  |  |  | 162.34 |  |  | 1500 | 243.51
M&S Cost Estimate (Do not double-enter any labor M&S reported in above table):
Activity # from above table (Use pull-down list) | P6 Activirty # | Activity Name | Item Purchased | Not used | Resource ID (Use pull-down list) | Indirect reference to fix cut and paste error | Overhead multiplier (Automatically populated) | N ot Used | Base Estimate (FY13 $K) {Enter without $ or K} | Indirect for Base Estimate | Estimate Type (Populated from Activities Table) | Not Used | Contingency (%) (Auto Populated) | On-project Costs Base + Contingency + Overhead (FY14 $K) {Calculated} | Notes
[9 empty] | 0 |  |  |  |  | 0
Date Scheduler Authorized to Enter Activities into RLS (change log begins):
Change Log: All changes need to be tracked after the scheduler has been authorized to enter data from this sheet into the RLS
Activity # from above table (Use pull-down list) | P6 Activity # | Activity Name | Description (added activity, activity no longer used, added 20 hours of <resource ID> labor to activity, added <Item Description> M&S item to activity, added/deleted predecessor to activity, changed estimat type for activity, changed funding source, etc.) | [6 empty] | Estimate Type (Populated from Activities Table) | Date of Change to BoE |  | Date Entered into Schedule

## Implementation
Implementation for Instrumentation: Wall Current Monitors
Dictionary Description:
Implemenation includes building and installing the wall current monitors.
Activities and Dependences:
Activity # | P6 Activity # | Activity Name | Activity Description | [6 empty] | Not Used | Estimate Type (Use pull-down list) | Not Used | Alternate Funding? (use pull-down list) (if none, leave blank) | Source Documentation # (s) from CoverSheet (1, 2, 3, etc...) | Predecessor Activity # (s) within this BoE (100, 110, 120, etc...) | Duration (working days) | Notes (List steps for each activity here):
500 |  | Project Oversight | Coordination and oversight of activities associated implementation | [7 empty] | Engineering Estimate III (50%) |  |  |  | Start of Implementation | 88 | 20 hours (Peter)
510 |  | Procure Wall Current Monitors | Procure all necessary components | [7 empty] | Engineering Estimate III (50%) |  |  |  | Start of Implementation | 44 | 6 months - procure parts (tech 60hrs, $40k per detector), machine shop (360 hours per detector), stands ($2k per detector), pcb ($1k per detector)
520 |  | Assemble Wall Current Monitors | Assemble each detector | [7 empty] | Engineering Estimate III (50%) |  |  |  | 510 | 44 | assembly (40 hours per detector tech)
530 |  | Procure cables | Procure controls and signal cables. | [7 empty] | Engineering Estimate III (50%) |  |  |  | Start of Implementation | 20 | $8 per foot, 2 cables per detector
540 |  | Build Readout Electronics | Procure and build front-end readout and necessary infrastructure (crate, cpu, etc) | [7 empty] | Engineering Estimate III (50%) |  |  |  | Start of Implementation | 44 | (crate, cpu, digitizer - $15k per location), testing (80 hours tech, 40 hours ee)
550 |  | install Wall Current Monitors | Install Wall Current Monitors in final locations. | [7 empty] | Engineering Estimate III (50%) |  |  |  | 510 | 44 | Vacuum Certification (? Vacuum tech), Install (mech tech - 8hrs?), Alignment (tech - 8 hrs?), Cable termination (4 hours - tech) all per detector
560 |  | Install Front End | Install the service building front end that interfaces the WCM to the control system. | [7 empty] | Engineering Estimate III (50%) |  |  |  | 530 | 44 | tech (16 hours per detector) - install and cable up system
570 |  | Finalize Control Software | Finalize controls software that interface hardware. | [7 empty] | Engineering Estimate III (50%) |  |  |  | 540, 550 | 44 | Programmer (20 hours per installation) - verify system operation
580
590
600
610
620
630
640
650
660
670
680
690
None
Hourly Labor Estimates (Some of these labor types could be assessed as M&S from the project perspective):
Activity # from above table (Use pull-down list) | P6 Activity # | Activity Name | Resource ID Category Prefix (Use pull-down list) | Indirect reference to fix cut and paste error | Resource ID Category Suffix (Use pull-down list) | Indirect reference to fix cut and paste error | Resource ID Validity Check (Populated Automatically) | Not used | Base Estimate (hours) (Enter without any units) | Indirect reference to fix cut and paste error | BoE Pay Rate (FY15 $/hr) (From lookup table) | Not used | BoE Base Estimate (K$) (Auto Populated) | Estimate Type (Populated from Activities Table) | Contingency (%) (Auto Populated) | Base + Contingency (hours) {Calculated} | On-project costs Base + Contingency BoE(K$) {Calculated FY15} | Notes
500 | TBD | Project Oversight | FNAD | FNAD | ELEC_DESIGN_SR | ELEC_DESIGN_SR | FNAD_ELEC_DESIGN_SR |  | 20 | 20 | 203 |  | 4.06 | Engineering Estimate III (50%) | 50% | 30 | 6.09
500 | TBD | Project Oversight | FNAD | FNAD | ENGNRING_PHYST | ENGNRING_PHYST | FNAD_ENGNRING_PHYST |  | 20 | 20 | 177 |  | 3.54 | Engineering Estimate III (50%) | 50% | 30 | 5.31
510 | TBD | Procure Wall Current Monitors | FNAD | FNAD | ELEC_TECH | ELEC_TECH | FNAD_ELEC_TECH |  | 60 | 60 | 102 |  | 6.12 | Engineering Estimate III (50%) | 50% | 90 | 9.18
520 | TBD | Assemble Wall Current Monitors | FNAD | FNAD | ELEC_TECH | ELEC_TECH | FNAD_ELEC_TECH |  | 80 | 80 | 102 |  | 8.16 | Engineering Estimate III (50%) | 50% | 120 | 12.24 | Assume 2 detectors
540 | TBD | Build Readout Electronics | FNAD | FNAD | ELEC_DESIGN_EN | ELEC_DESIGN_EN | FNAD_ELEC_DESIGN_EN |  | 40 | 40 | 162 |  | 6.48 | Engineering Estimate III (50%) | 50% | 60 | 9.72
540 | TBD | Build Readout Electronics | FNAD | FNAD | ELEC_TECH | ELEC_TECH | FNAD_ELEC_TECH |  | 80 | 80 | 102 |  | 8.16 | Engineering Estimate III (50%) | 50% | 120 | 12.24
550 | TBD | install Wall Current Monitors | FNTD | FNTD | MECH_ASMBY_TECH | MECH_ASMBY_TECH | FNTD_MECH_ASMBY_TECH |  | 40 | 40 | 96 |  | 3.84 | Engineering Estimate III (50%) | 50% | 60 | 5.76
550 | TBD | install Wall Current Monitors | FNAD | FNAD | MECH_SYSTM_TECH | MECH_SYSTM_TECH | FNAD_MECH_SYSTM_TECH |  | 16 | 16 | 87 |  | 1.392 | Engineering Estimate III (50%) | 50% | 24 | 2.088 | Alignment?
550 | TBD | install Wall Current Monitors | FNAD | FNAD | ELEC_TECH | ELEC_TECH | FNAD_ELEC_TECH |  | 8 | 8 | 102 |  | 0.816 | Engineering Estimate III (50%) | 50% | 12 | 1.224
560 | TBD | Install Front End | FNAD | FNAD | ELEC_TECH | ELEC_TECH | FNAD_ELEC_TECH |  | 32 | 32 | 102 |  | 3.264 | Engineering Estimate III (50%) | 50% | 48 | 4.896
570 | TBD | Finalize Control Software | FNAD | FNAD | CTRL_SYSTM_EN | CTRL_SYSTM_EN | FNAD_CTRL_SYSTM_EN |  | 40 | 40 | 171 |  | 6.84 | Engineering Estimate III (50%) | 50% | 60 | 10.26
[9 empty] | 436 |  |  |  | 52.672 |  |  | 654 | 79.008
M&S Cost Estimate (Do not double-enter any labor M&S reported in above table):
Activity # from above table (Use pull-down list) | P6 Activirty # | Activity Name | Item Purchased | Not used | Resource ID (Use pull-down list) | Indirect reference to fix cut and paste error | Overhead multiplier (Automatically populated) | N ot Used | Base Estimate (FY13 $K) {Enter without $ or K} | Indirect for Base Estimate | Estimate Type (Populated from Activities Table) | Not Used | Contingency (%) (Auto Populated) | On-project Costs Base + Contingency + Overhead (FY15 $K) {Calculated} | Notes
510 | TBD | Procure Wall Current Monitors | Pickup components |  | FN_MS_STND | FN_MS_STND | 1.23 |  | 80 | 80 | Engineering Estimate III (50%) |  | 50% | 155.678
510 | TBD | Procure Wall Current Monitors | Printed Circuit Boards |  | FN_MS_STND | FN_MS_STND | 1.23 |  | 1 | 1 | Engineering Estimate III (50%) |  | 50% | 1.946
510 | TBD | Procure Wall Current Monitors | Stands |  | FN_MS_STND | FN_MS_STND | 1.23 |  | 2 | 2 | Engineering Estimate III (50%) |  | 50% | 3.892
530 | TBD | Procure cables | Cables |  | FN_MS_STND | FN_MS_STND | 1.23 |  | 4.8 | 4.8 | Engineering Estimate III (50%) |  | 50% | 9.3407 | Assume 4 cables at 150' each
540 | TBD | Build Readout Electronics | Crate, Cpu, Digitizer |  | FN_MS_STND | FN_MS_STND | 1.23 |  | 30 | 30 | Engineering Estimate III (50%) |  | 50% | 58.3793 | Assume 2 crates
510 | TBD | Procure Wall Current Monitors | Machine Shop | [11 empty] | 360 hours?
[9 empty] | 117.8 |  |  |  |  | 229.2359
Date Scheduler Authorized to Enter Activities into RLS (change log begins):
Change Log: All changes need to be tracked after the scheduler has been authorized to enter data from this sheet into the RLS
Activity # from above table (Use pull-down list) | P6 Activity # | Activity Name | Description (added activity, activity no longer used, added 20 hours of <resource ID> labor to activity, added <Item Description> M&S item to activity, added/deleted predecessor to activity, changed estimat type for activity, changed funding source, etc.) | [7 empty] | Date of Change to BoE |  | Date Entered into Schedule

## Totals
| Base Labor (Hours) | Base Labor ($K) | Base + Contingecy Labor (Hours) | On-Project Base + Contingecy Labor ($K) | Base M&S (K$) | Base + Contingecy M&S ($K) | Base Labor & M&S ($K) | On-Project Base + Contingency Labor & M&S ($K)
Preliminary Design | 550 | 91.18 | 825 | 136.77 | 0 | 0 | 91.18 | 136.77
Final Design | 1000 | 162.34 | 1500 | 243.51 | 0 | 0 | 162.34 | 243.51
Implementation | 436 | 52.672 | 654 | 79.008 | 117.8 | 229.2359 | 170.472 | 308.2439
Totals | 1986 | 306.192 | 2979 | 459.288 | 117.8 | 229.2359 | 423.992 | 688.5239

## Additional Information
Additional Background Information:
Provide additional information useful for reviewers to understand the scope, the costing and justifications. (Alt-Enter or Command-Alt-Enter for carriage return in cell)

## Alternatives
Alternatives: Describe other options that were considered as part of the value engineering and why they were rejected. Also describe alternatives that are still under consideration. (Alt-Enter or Command-Alt-Enter for carriage return in cell)
Ion Chambers are the alternative intensity measuring device. WCM is preferred as it is less destructive to the beam; however, the cost is greater.

## KnownDependencies
Known Dependencies from other WBS Entries: Use this area to indicate important dependencies from other WBS elements. (Alt-Enter or Command-Alt-Enter for carriage return in cell)
Predecessors: None
Successors: Completed before beam is sent to g-2.

## OpportunitiesRisks
Opportunties & Risks
WBS (Auto populated) | WBS Description (Auto populated) | Type (Use pull-down menu) | Potential Problem/Opportunity (short description) | Cause | Consequence (longer description of Column D item) | Category (use pull-down menu) | Owner | Mitigation Action | Probability (Use pull-down menu) | Impact (Use pull-down menu - See Risk Matrix Worksheet) | Severity (use pull-down menu - See Risk Matrix Worksheet) | Cost Impact ($K) | Schedule Impact (months)
476.02.04.03.05 | Instrumentation: Wall Current Monitors | Risk | WCM cannot measure secondary beam. | New prototype Mu2e WCM, used to measure M4 line spill, should be able to measure 2e7 g-2 secondary beam, but this has to be verified with beam studies. | The newly designed WCM cannot measure the g-2 secondary beam intensity. | Technical | Brian Drendel | Do not implement WCM's in the M3 line and Delivery Ring. Instead rely on ion chambers to obtain beam intensity information. | Low (10%-25%) | Low | Low | $0K | None
476.02.04.03.05 | Instrumentation: Wall Current Monitors | Opportunity | WCM provides a non-destructive option for measuring beam intensity. | If we can get the cost of the WCM monitor down to the range of the ion chamber and if we can measure beam down to the 2e7 range, then the WCM would be a viable replacement for the more disruptive ion chamber. | WCM replaces the ion chamber for measuring low intensity secondary beam in g-2 operations. | Technical | Brian Drendel | Implement WCM instead of IC. | Low (10%-25%) | Low | Low | $0K | None
476.02.04.03.05 | Instrumentation: Wall Current Monitors
476.02.04.03.05 | Instrumentation: Wall Current Monitors
476.02.04.03.05 | Instrumentation: Wall Current Monitors
476.02.04.03.05 | Instrumentation: Wall Current Monitors
476.02.04.03.05 | Instrumentation: Wall Current Monitors
476.02.04.03.05 | Instrumentation: Wall Current Monitors

## RiskMatrix (hidden)
Use this table to determine the Risk Impact in the OpportunitesRisks Workbook
Impact | Very Low | Low | Moderate | High | Very High
Risk
Cost | < $50K | $50K - $100K | $100K - $250K | $250K - $500K | > $500K
ES&H | Negligible | Minimal | Concern | Significant risk | High risk
Schedule | Delays Level 3 milestone or Project critical path by < 1 month | Delays Level 3 milestone or Project critical path by 1 - 3 months | Delays Level 3 milestone or Project critical path by 3 - 6 months | Delays level 3 milestone or Project critical path by 6 – 9 months | Delays Level 3 milestone or Project critical path by > 9 months
Technical | Negligible | Negligible, if any, degradation. | Technical degradation leading to moderately compromised physics objectives. | Technical degradation leading to severely compromised physics objectives. | Technical degradation leading to severely compromised and unrecoverable physics objectives.
Use this table to determine the Risk Severity (Risk Severity is calcualted from the Risk Impact and Risk Probability in the below table)
Impact
Probability | Very Low | Low | Moderate | High | Very High
Very High (> 90%) | Low | Moderate | High | High | High
High (75% – 90%) | Low | Moderate | Moderate | High | High
Moderate (25% - 75%) | Low | Low | Moderate | High | High
Low (10% - 25%) | Low | Low | Moderate | Moderate | High
Very Low (< 10%) | Low | Low | Low | Low | Moderate

## ContingenciesAndRisks
Contingency Lists |  | Risk Type | Risk Probability
Work Complete (0%) | 0% | Risk | Very Low (<10%)
Existing Purchase Order (5%) | 5% | Opportunity | Low (10%-25%)
Catalog List/Ind Database (10%) | 10% |  | Moderate (25%-75%)
Vendor Estimate (25%) | 25% |  | High (75%-90%)
Engineering Estimate I (30%) | 30% |  | Very High (>90%)
Engineering Estimate II (40%) | 40%
Engineering Estimate III (50%) | 50%
Expert Opinion (40% - justify) | 40% | Risk Category | Risk Impact
Expert Opinion (60%) | 60% | Cost | Very Low
Expert Opinion (80% - justify) | 80% | ES&H | Low
|  | Schedule | Moderate
|  | Technical | High
Very High

## ResourceLabor
Resource IDs (labor) | [10 empty] | Unique Task Names | Rows | Start Row | End Row | Cell Range
Task Code | Prefix | Suffix |  | FY12 | FY13 | FY14 | FY15 | FY16 | FY17 | FY18
FN_S_PRJ_CTRL_ENTRY | FN | S_PRJ_CTRL_ENTRY | Project Controls Entry | 114 | 115 | 117 | 120 | 123 | 127 | 130 | FN | 3 | 3 | 5 | ResourceLabor!$C$3:$C$5
FN_S_PRJ_CTRL_MID | FN | S_PRJ_CTRL_MID | Project Controls Mid | 146 | 147 | 150 | 154 | 158 | 162 | 166 | FNAD | 107 | 6 | 112 | ResourceLabor!$C$6:$C$112
FN_S_PRJ_CTRL_SR | FN | S_PRJ_CTRL_SR | Project Controls Sr | 178 | 179 | 183 | 187 | 192 | 197 | 202 | FNAP | 36 | 113 | 148 | ResourceLabor!$C$113:$C$148
FNAD_AC_EXP_PHYST | FNAD | AC_EXP_PHYST | Accelerator Physicist Experimental | 168 | 169 | 172 | 177 | 181 | 186 | 190 | FNCD | 85 | 149 | 233 | ResourceLabor!$C$149:$C$233
FNAD_AC_EXP_RA | FNAD | AC_EXP_RA | Accelerator Experimental Research Associate | 102 | 102 | 104 | 107 | 110 | 113 | 115 | FNES | 34 | 234 | 267 | ResourceLabor!$C$234:$C$267
FNAD_AC_OPERATOR | FNAD | AC_OPERATOR | Accelerator Operator | 96 | 96 | 98 | 101 | 103 | 106 | 108 | FNFE | 2 | 268 | 269 | ResourceLabor!$C$268:$C$269
FNAD_AC_SYSTM_SPCLST | FNAD | AC_SYSTM_SPCLST | Accelerator Systems Specialist | 142 | 144 | 146 | 150 | 154 | 158 | 162 | FNOF | 14 | 270 | 283 | ResourceLabor!$C$270:$C$283
FNAD_AC_THY_PHYST | FNAD | AC_THY_PHYST | Accelerator Physicist Theory | 184 | 185 | 189 | 194 | 198 | 203 | 209 | FNPD | 93 | 284 | 376 | ResourceLabor!$C$284:$C$376
FNAD_AC_THY_RA | FNAD | AC_THY_RA | Accelerator Theory Research Associate | 102 | 102 | 104 | 107 | 110 | 113 | 115 | FNTD | 99 | 377 | 475 | ResourceLabor!$C$377:$C$475
FNAD_ACCOUNTANT | FNAD | ACCOUNTANT | Accountant | 135 | 136 | 139 | 142 | 146 | 149 | 153 | GM2ANL | 37 | 476 | 512 | ResourceLabor!$C$476:$C$512
FNAD_ADMIN_SPPRT | FNAD | ADMIN_SPPRT | Administrative Support | 83 | 83 | 85 | 87 | 89 | 92 | 94 | GM2BNL | 37 | 513 | 549 | ResourceLabor!$C$513:$C$549
FNAD_APDEV_SYSTMAYST | FNAD | APDEV_SYSTMAYST | Applications Development & Systems Analyst | 154 | 155 | 158 | 162 | 166 | 170 | 174 | GM2UNI | 20 | 550 | 569 | ResourceLabor!$C$550:$C$569
FNAD_ASIC_DESIGN_EN | FNAD | ASIC_DESIGN_EN | ASIC Design Engineer | 154 | 155 | 158 | 162 | 166 | 170 | 175 | TM | 18 | 570 | 587 | ResourceLabor!$C$570:$C$587
FNAD_ASIC_DESIGN_SR | FNAD | ASIC_DESIGN_SR | ASIC Design Engineer Sr | 216 | 218 | 222 | 228 | 234 | 240 | 246 | X | 30 | 588 | 617 | ResourceLabor!$C$588:$C$617
FNAD_CLERICAL | FNAD | CLERICAL | Clerical | 74 | 75 | 76 | 78 | 80 | 82 | 84
FNAD_CONST_COORDNATR | FNAD | CONST_COORDNATR | Construction Coordinator | 143 | 144 | 147 | 151 | 155 | 159 | 163
FNAD_CONST_SAFETY | FNAD | CONST_SAFETY | Construction Safety | 142 | 143 | 146 | 150 | 154 | 157 | 161
FNAD_CRYO_DESIGNER | FNAD | CRYO_DESIGNER | Cryo Designer | 109 | 110 | 112 | 115 | 118 | 121 | 124
FNAD_CRYO_EN | FNAD | CRYO_EN | Cryogenics Engineer | 158 | 160 | 163 | 167 | 171 | 175 | 180
FNAD_CRYO_SR | FNAD | CRYO_SR | Cryogenics Engineer Sr | 217 | 219 | 224 | 229 | 235 | 241 | 247
FNAD_CRYO_TECH | FNAD | CRYO_TECH | Cryo Technician | 91 | 92 | 94 | 96 | 99 | 101 | 104
FNAD_CT_SRVCS_SPCLST | FNAD | CT_SRVCS_SPCLST | Computing Services Specialist | 167 | 168 | 171 | 176 | 180 | 185 | 189
FNAD_CTRL_SYSTM_EN | FNAD | CTRL_SYSTM_EN | Control System Engineer | 162 | 163 | 167 | 171 | 175 | 179 | 184
FNAD_CTRL_SYSTM_SR | FNAD | CTRL_SYSTM_SR | Control System Engineer Sr | 198 | 199 | 203 | 208 | 214 | 219 | 224
FNAD_DATABASE_AYST | FNAD | DATABASE_AYST | Database Administration Analyst | 152 | 153 | 156 | 160 | 164 | 168 | 172
FNAD_ELEC_ASMBY_TECH | FNAD | ELEC_ASMBY_TECH | Electrical Assembly Technician | 84 | 85 | 87 | 89 | 91 | 93 | 96
FNAD_ELEC_DESIGN_EN | FNAD | ELEC_DESIGN_EN | Electrical Design Engineer | 154 | 155 | 158 | 162 | 166 | 170 | 175
FNAD_ELEC_DESIGN_SR | FNAD | ELEC_DESIGN_SR | Electrical Design Engineer Sr | 193 | 194 | 198 | 203 | 208 | 213 | 219
FNAD_ELEC_DESIGNER | FNAD | ELEC_DESIGNER | Electrical Designer | 118 | 119 | 122 | 125 | 128 | 131 | 134
FNAD_ELEC_DRAFTER | FNAD | ELEC_DRAFTER | Electrical Drafter | 83 | 83 | 85 | 87 | 89 | 92 | 94
FNAD_ELEC_TASK_MNGR | FNAD | ELEC_TASK_MNGR | Electrical Task Manager | 144 | 145 | 148 | 152 | 156 | 159 | 163
FNAD_ELEC_TECH | FNAD | ELEC_TECH | Electrical Technician | 97 | 97 | 99 | 102 | 104 | 107 | 110
FNAD_ELEC_TECH_MNGR | FNAD | ELEC_TECH_MNGR | Electrical Technical Manager | 233 | 235 | 240 | 246 | 252 | 258 | 265
FNAD_ELEC_TECH_SPVSR | FNAD | ELEC_TECH_SPVSR | Electrical Technician Supervisor | 136 | 137 | 140 | 143 | 147 | 150 | 154
FNAD_ELTN_DESIGN_EN | FNAD | ELTN_DESIGN_EN | Electronics Design Engineer | 158 | 159 | 162 | 166 | 170 | 175 | 179
FNAD_ELTN_DESIGN_SR | FNAD | ELTN_DESIGN_SR | Electronics Design Engineer Sr | 203 | 205 | 209 | 214 | 220 | 225 | 231
FNAD_ELTN_TECH | FNAD | ELTN_TECH | Electronics Technician | 105 | 105 | 108 | 110 | 113 | 116 | 119
FNAD_ENGNRING_PHYST | FNAD | ENGNRING_PHYST | Engineering Physicist | 168 | 170 | 173 | 177 | 182 | 186 | 191
FNAD_FACILITIES_MGMT | FNAD | FACILITIES_MGMT | Facilities Management | 142 | 143 | 146 | 150 | 153 | 157 | 161
FNAD_GENERAL_ADMIN | FNAD | GENERAL_ADMIN | General Administrative | 103 | 104 | 106 | 109 | 111 | 114 | 117
FNAD_GENERAL_ESH | FNAD | GENERAL_ESH | General ES&H | 163 | 164 | 167 | 171 | 176 | 180 | 185
FNAD_HIGH_VAC_TECH | FNAD | HIGH_VAC_TECH | High Vac Technician | 93 | 94 | 96 | 98 | 101 | 103 | 106
FNAD_INTERLOCK_EN | FNAD | INTERLOCK_EN | Interlock Engineer | 153 | 155 | 158 | 162 | 166 | 170 | 174
FNAD_INTERLOCK_SR | FNAD | INTERLOCK_SR | Interlock Engineer Sr | 191 | 192 | 196 | 201 | 206 | 211 | 216
FNAD_INTERLOCK_TECH | FNAD | INTERLOCK_TECH | Electrical Interlock Technician | 116 | 117 | 119 | 122 | 126 | 129 | 132
FNAD_MAGNT_DESIGN_EN | FNAD | MAGNT_DESIGN_EN | Magnet Design Engineer | 178 | 180 | 183 | 188 | 193 | 197 | 202
FNAD_MAGNT_DESIGN_SR | FNAD | MAGNT_DESIGN_SR | Magnet Design Engineer Sr | 196 | 198 | 202 | 207 | 212 | 217 | 223
FNAD_MAGNT_DESIGNER | FNAD | MAGNT_DESIGNER | Magnet Designer | 115 | 116 | 118 | 121 | 124 | 127 | 131
FNAD_MAGNT_RA | FNAD | MAGNT_RA | Magnet Research Associate | 102 | 102 | 104 | 107 | 110 | 113 | 115
FNAD_MAGNT_SCIENTIST | FNAD | MAGNT_SCIENTIST | Magnet Scientist | 172 | 173 | 177 | 181 | 186 | 190 | 195
FNAD_MATRL_EN | FNAD | MATRL_EN | Materials Engineer | 98 | 99 | 101 | 104 | 106 | 109 | 112
FNAD_MATRL_SR | FNAD | MATRL_SR | Materials Engineer Sr | 98 | 99 | 101 | 104 | 106 | 109 | 112
FNAD_MECH_ANLYSIS_EN | FNAD | MECH_ANLYSIS_EN | Mechanical Analysis Engineer | 150 | 151 | 154 | 158 | 162 | 166 | 170
FNAD_MECH_ANLYSIS_SR | FNAD | MECH_ANLYSIS_SR | Mechanical Analysis Engineer Sr | 188 | 190 | 194 | 199 | 204 | 209 | 214
FNAD_MECH_ASMBY_TECH | FNAD | MECH_ASMBY_TECH | Mechanical Assembly Technician | 96 | 97 | 99 | 101 | 104 | 106 | 109
FNAD_MECH_DESIGN_EN | FNAD | MECH_DESIGN_EN | Mechanical Design Engineer | 156 | 157 | 160 | 164 | 168 | 173 | 177
FNAD_MECH_DESIGN_SR | FNAD | MECH_DESIGN_SR | Mechanical Design Engineer Sr | 197 | 199 | 203 | 208 | 213 | 218 | 224
FNAD_MECH_DESIGNER | FNAD | MECH_DESIGNER | Mechanical Designer | 114 | 115 | 117 | 120 | 123 | 126 | 130
FNAD_MECH_DRAFTER | FNAD | MECH_DRAFTER | Mechanical Drafter | 68 | 68 | 70 | 71 | 73 | 75 | 77
FNAD_MECH_SYSTM_TECH | FNAD | MECH_SYSTM_TECH | Mechanical Systems Technician | 83 | 84 | 85 | 87 | 90 | 92 | 94
FNAD_MECH_TASK_MNGR | FNAD | MECH_TASK_MNGR | Mechanical Task Manager | 81 | 81 | 83 | 85 | 87 | 89 | 92
FNAD_MECH_TECH_MNGR | FNAD | MECH_TECH_MNGR | Mechanical Technical Manager | 203 | 205 | 209 | 214 | 220 | 225 | 231
FNAD_MECH_TECH_SPVSR | FNAD | MECH_TECH_SPVSR | Mechanical Technician Supervisor | 136 | 137 | 140 | 144 | 147 | 151 | 155
FNAD_NETWORK_AYST | FNAD | NETWORK_AYST | Network Analyst | 157 | 158 | 161 | 166 | 170 | 174 | 178
FNAD_OPERTNS_FINANCE | FNAD | OPERTNS_FINANCE | Operations Finance | 148 | 150 | 153 | 156 | 160 | 164 | 168
FNAD_OPERTNS_MNGR | FNAD | OPERTNS_MNGR | Operations Manager | 189 | 191 | 195 | 200 | 205 | 210 | 215
FNAD_OPERTNS_SPCLST | FNAD | OPERTNS_SPCLST | Operations Specialist | 140 | 141 | 144 | 147 | 151 | 155 | 158
FNAD_PA_EXP_RA | FNAD | PA_EXP_RA | Particle-Astro Experimental Research Associate | 102 | 102 | 104 | 107 | 110 | 113 | 115
FNAD_PA_THY_RA | FNAD | PA_THY_RA | Particle-Astro Theory Research Associate | 102 | 102 | 104 | 107 | 110 | 113 | 115
FNAD_PC_CUSTM_SPPRT | FNAD | PC_CUSTM_SPPRT | Computer Customer Support | 107 | 108 | 110 | 113 | 116 | 119 | 122
FNAD_PC_SECURTY_AYST | FNAD | PC_SECURTY_AYST | Computer Security Analyst | 177 | 178 | 182 | 186 | 191 | 196 | 201
FNAD_PC_SPPRT_ASSOCT | FNAD | PC_SPPRT_ASSOCT | PC Support Associate | 100 | 101 | 103 | 106 | 108 | 111 | 114
FNAD_PRCESS_CTRL_EN | FNAD | PRCESS_CTRL_EN | Process/Controls Engineer | 122 | 123 | 125 | 128 | 132 | 135 | 138
FNAD_PRCESS_CTRL_SR | FNAD | PRCESS_CTRL_SR | Process/Controls Engineer Sr | 166 | 167 | 171 | 175 | 179 | 184 | 189
FNAD_PRJ_CTRL_LEAD | FNAD | PRJ_CTRL_LEAD | Project Controls Lead | 152 | 153 | 156 | 160 | 164 | 168 | 172
FNAD_PRJ_CTRL_MNGR | FNAD | PRJ_CTRL_MNGR | Project Controls Manager | 207 | 208 | 212 | 218 | 223 | 229 | 234
FNAD_PRJ_CTRL_SPCLST | FNAD | PRJ_CTRL_SPCLST | Project Controls Specialist | 128 | 129 | 131 | 135 | 138 | 142 | 145
FNAD_PRJ_FINANCE | FNAD | PRJ_FINANCE | Project Finance | 147 | 148 | 151 | 155 | 159 | 163 | 167
FNAD_PRJ_MNGR | FNAD | PRJ_MNGR | Project Manager | 174 | 175 | 179 | 183 | 188 | 193 | 197
FNAD_PRJ_MNGR_EXC | FNAD | PRJ_MNGR_EXC | Project Manager Exec | 328 | 330 | 337 | 346 | 354 | 363 | 372
FNAD_PRJ_MNGR_SR | FNAD | PRJ_MNGR_SR | Project Manager Sr | 262 | 264 | 270 | 276 | 283 | 290 | 298
FNAD_PRJ_SPPRT | FNAD | PRJ_SPPRT | Project Support | 152 | 153 | 156 | 160 | 164 | 168 | 172
FNAD_PROCUREMENT | FNAD | PROCUREMENT | Procurement | 125 | 127 | 129 | 132 | 136 | 139 | 142
FNAD_PT_EXP_PHYST | FNAD | PT_EXP_PHYST | Particle Physicist Experimental | 153 | 155 | 158 | 162 | 166 | 170 | 174
FNAD_PT_EXP_RA | FNAD | PT_EXP_RA | Particle Physics Experimental Research Associate | 102 | 102 | 104 | 107 | 110 | 113 | 115
FNAD_PT_THY_RA | FNAD | PT_THY_RA | Particle Physics Theory Research Associate | 102 | 102 | 104 | 107 | 110 | 113 | 115
FNAD_QLTY_ASSRANCE | FNAD | QLTY_ASSRANCE | Quality Assurance | 167 | 168 | 172 | 176 | 181 | 185 | 190
FNAD_RAD_PRTECTON | FNAD | RAD_PRTECTON | Radiation Protection | 135 | 136 | 138 | 142 | 145 | 149 | 153
FNAD_RF_DESIGN_EN | FNAD | RF_DESIGN_EN | RF Design Engineer | 165 | 166 | 170 | 174 | 178 | 183 | 187
FNAD_RF_DESIGN_SR | FNAD | RF_DESIGN_SR | RF Design Engineer Sr | 203 | 205 | 209 | 214 | 219 | 225 | 231
FNAD_RF_RA | FNAD | RF_RA | RF Research Associate | 102 | 102 | 104 | 107 | 110 | 113 | 115
FNAD_RF_SCIENTIST | FNAD | RF_SCIENTIST | RF Scientist | 189 | 191 | 195 | 200 | 205 | 210 | 215
FNAD_SAFETY | FNAD | SAFETY | Safety | 145 | 146 | 149 | 153 | 157 | 161 | 165
FNAD_SRF_TECH | FNAD | SRF_TECH | Mechanical SRF Technician | 84 | 85 | 87 | 89 | 91 | 93 | 96
FNAD_SYSTM_ADMIN | FNAD | SYSTM_ADMIN | Systems Administrator | 130 | 131 | 134 | 137 | 141 | 144 | 148
FNAD_TRAINING | FNAD | TRAINING | Training | 136 | 137 | 140 | 144 | 147 | 151 | 155
FNAD_U_CONST_SAFETY | FNAD | U_CONST_SAFETY | Construction Safety Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNAD_U_GENERAL_ESH | FNAD | U_GENERAL_ESH | General ES&H Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNAD_U_PA_EXP_PHYST | FNAD | U_PA_EXP_PHYST | Particle-Astro Physicist Experimental Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNAD_U_PA_EXP_RA | FNAD | U_PA_EXP_RA | Particle-Astro Experimental Research Associate Uncost | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNAD_U_PA_THY_RA | FNAD | U_PA_THY_RA | Particle-Astro Theory Research Associate Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNAD_U_PROCUREMENT | FNAD | U_PROCUREMENT | Procurement Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNAD_U_PT_EXP_PHYST | FNAD | U_PT_EXP_PHYST | Particle Physicist Experimental Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNAD_U_PT_EXP_RA | FNAD | U_PT_EXP_RA | Particle Physics Experimental Research Associate Unco | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNAD_U_PT_THY_RA | FNAD | U_PT_THY_RA | Particle Physics Theory Research Associate Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNAD_U_RAD_PRTECTON | FNAD | U_RAD_PRTECTON | Radiation Protection Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNAD_U_RF_RA | FNAD | U_RF_RA | RF Research Associate Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNAD_U_RF_SCIENTIST | FNAD | U_RF_SCIENTIST | RF Scientist Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNAD_U_SAFETY | FNAD | U_SAFETY | Safety Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNAD_WEB_APPS_DEVLPR | FNAD | WEB_APPS_DEVLPR | Web Applications Developer | 105 | 106 | 108 | 111 | 114 | 117 | 120
FNAP_AC_EXP_PHYST | FNAP | AC_EXP_PHYST | Accelerator Physicist Experimental | 168 | 169 | 172 | 177 | 181 | 186 | 190
FNAP_AC_EXP_RA | FNAP | AC_EXP_RA | Accelerator Experimental Research Associate | 102 | 102 | 104 | 107 | 110 | 113 | 115
FNAP_AC_THY_PHYST | FNAP | AC_THY_PHYST | Accelerator Physicist Theory | 184 | 185 | 189 | 194 | 198 | 203 | 209
FNAP_AC_THY_RA | FNAP | AC_THY_RA | Accelerator Theory Research Associate | 102 | 102 | 104 | 107 | 110 | 113 | 115
FNAP_ADMIN_SPPRT | FNAP | ADMIN_SPPRT | Administrative Support | 83 | 83 | 85 | 87 | 89 | 92 | 94
FNAP_ELEC_TECH_MNGR | FNAP | ELEC_TECH_MNGR | Electrical Technical Manager | 233 | 235 | 240 | 246 | 252 | 258 | 265
FNAP_ELTN_DESIGN_EN | FNAP | ELTN_DESIGN_EN | Electronics Design Engineer | 158 | 159 | 162 | 166 | 170 | 175 | 179
FNAP_ELTN_DESIGN_SR | FNAP | ELTN_DESIGN_SR | Electronics Design Engineer Sr | 203 | 205 | 209 | 214 | 220 | 225 | 231
FNAP_ENGNRING_PHYST | FNAP | ENGNRING_PHYST | Engineering Physicist | 168 | 170 | 173 | 177 | 182 | 186 | 191
FNAP_FACILITIES_MGMT | FNAP | FACILITIES_MGMT | Facilities Management | 142 | 143 | 146 | 150 | 153 | 157 | 161
FNAP_GENERAL_ADMIN | FNAP | GENERAL_ADMIN | General Administrative | 103 | 104 | 106 | 109 | 111 | 114 | 117
FNAP_MAGNT_SCIENTIST | FNAP | MAGNT_SCIENTIST | Magnet Scientist | 172 | 173 | 177 | 181 | 186 | 190 | 195
FNAP_MECH_ASMBY_TECH | FNAP | MECH_ASMBY_TECH | Mechanical Assembly Technician | 96 | 97 | 99 | 101 | 104 | 106 | 109
FNAP_MECH_DESIGN_EN | FNAP | MECH_DESIGN_EN | Mechanical Design Engineer | 156 | 157 | 160 | 164 | 168 | 173 | 177
FNAP_MECH_DESIGN_SR | FNAP | MECH_DESIGN_SR | Mechanical Design Engineer Sr | 197 | 199 | 203 | 208 | 213 | 218 | 224
FNAP_PA_EXP_RA | FNAP | PA_EXP_RA | Particle-Astro Experimental Research Associate | 102 | 102 | 104 | 107 | 110 | 113 | 115
FNAP_PA_THY_RA | FNAP | PA_THY_RA | Particle-Astro Theory Research Associate | 102 | 102 | 104 | 107 | 110 | 113 | 115
FNAP_PRJ_MNGR | FNAP | PRJ_MNGR | Project Manager | 174 | 175 | 179 | 183 | 188 | 193 | 197
FNAP_PRJ_MNGR_EXC | FNAP | PRJ_MNGR_EXC | Project Manager Exec | 328 | 330 | 337 | 346 | 354 | 363 | 372
FNAP_PRJ_MNGR_SR | FNAP | PRJ_MNGR_SR | Project Manager Sr | 262 | 264 | 270 | 276 | 283 | 290 | 298
FNAP_PT_EXP_PHYST | FNAP | PT_EXP_PHYST | Particle Physicist Experimental | 153 | 155 | 158 | 162 | 166 | 170 | 174
FNAP_PT_EXP_RA | FNAP | PT_EXP_RA | Particle Physics Experimental Research Associate | 102 | 102 | 104 | 107 | 110 | 113 | 115
FNAP_PT_THY_RA | FNAP | PT_THY_RA | Particle Physics Theory Research Associate | 102 | 102 | 104 | 107 | 110 | 113 | 115
FNAP_RF_DESIGN_EN | FNAP | RF_DESIGN_EN | RF Design Engineer | 165 | 166 | 170 | 174 | 178 | 183 | 187
FNAP_RF_DESIGN_SR | FNAP | RF_DESIGN_SR | RF Design Engineer Sr | 203 | 205 | 209 | 214 | 219 | 225 | 231
FNAP_RF_RA | FNAP | RF_RA | RF Research Associate | 102 | 102 | 104 | 107 | 110 | 113 | 115
FNAP_RF_SCIENTIST | FNAP | RF_SCIENTIST | RF Scientist | 189 | 191 | 195 | 200 | 205 | 210 | 215
FNAP_SYSTM_ADMIN | FNAP | SYSTM_ADMIN | Systems Administrator | 130 | 131 | 134 | 137 | 141 | 144 | 148
FNAP_U_PA_EXP_PHYST | FNAP | U_PA_EXP_PHYST | Particle-Astro Physicist Experimental Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNAP_U_PA_EXP_RA | FNAP | U_PA_EXP_RA | Particle-Astro Experimental Research Associate Uncost | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNAP_U_PA_THY_RA | FNAP | U_PA_THY_RA | Particle-Astro Theory Research Associate Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNAP_U_PT_EXP_PHYST | FNAP | U_PT_EXP_PHYST | Particle Physicist Experimental Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNAP_U_PT_EXP_RA | FNAP | U_PT_EXP_RA | Particle Physics Experimental Research Associate Unco | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNAP_U_PT_THY_RA | FNAP | U_PT_THY_RA | Particle Physics Theory Research Associate Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNAP_U_RF_RA | FNAP | U_RF_RA | RF Research Associate Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNAP_U_RF_SCIENTIST | FNAP | U_RF_SCIENTIST | RF Scientist Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNCD_AC_EXP_RA | FNCD | AC_EXP_RA | Accelerator Experimental Research Associate | 87 | 87 | 89 | 91 | 94 | 96 | 98
FNCD_AC_THY_PHYST | FNCD | AC_THY_PHYST | Accelerator Physicist Theory | 157 | 158 | 161 | 165 | 169 | 174 | 178
FNCD_AC_THY_RA | FNCD | AC_THY_RA | Accelerator Theory Research Associate | 87 | 87 | 89 | 91 | 94 | 96 | 98
FNCD_ACCOUNTANT | FNCD | ACCOUNTANT | Accountant | 115 | 116 | 118 | 121 | 124 | 127 | 131
FNCD_ADMIN_SPPRT | FNCD | ADMIN_SPPRT | Administrative Support | 71 | 71 | 73 | 74 | 76 | 78 | 80
FNCD_APDEV_SYSTMAYST | FNCD | APDEV_SYSTMAYST | Applications Development & Systems Analyst | 131 | 132 | 135 | 138 | 142 | 145 | 149
FNCD_ASIC_DESIGN_EN | FNCD | ASIC_DESIGN_EN | ASIC Design Engineer | 131 | 132 | 135 | 138 | 142 | 145 | 149
FNCD_ASIC_DESIGN_SR | FNCD | ASIC_DESIGN_SR | ASIC Design Engineer Sr | 185 | 186 | 190 | 195 | 199 | 204 | 210
FNCD_CLERICAL | FNCD | CLERICAL | Clerical | 63 | 64 | 65 | 67 | 68 | 70 | 72
FNCD_CM_WB_COORDNATR | FNCD | CM_WB_COORDNATR | Communications Website Coordinator | 129 | 130 | 133 | 136 | 140 | 143 | 147
FNCD_CONST_COORDNATR | FNCD | CONST_COORDNATR | Construction Coordinator | 122 | 123 | 126 | 129 | 132 | 135 | 139
FNCD_CP_PHYCS_DEVLPR | FNCD | CP_PHYCS_DEVLPR | Computational Physics Developer | 119 | 120 | 123 | 126 | 129 | 132 | 135
FNCD_CRYO_EN | FNCD | CRYO_EN | Cryogenics Engineer | 135 | 136 | 139 | 142 | 146 | 150 | 153
FNCD_CRYO_SR | FNCD | CRYO_SR | Cryogenics Engineer Sr | 185 | 187 | 191 | 195 | 200 | 205 | 211
FNCD_CT_SRVCS_SPCLST | FNCD | CT_SRVCS_SPCLST | Computing Services Specialist | 142 | 143 | 146 | 150 | 154 | 158 | 161
FNCD_CTRL_SYSTM_EN | FNCD | CTRL_SYSTM_EN | Control System Engineer | 138 | 139 | 142 | 146 | 149 | 153 | 157
FNCD_CTRL_SYSTM_SR | FNCD | CTRL_SYSTM_SR | Control System Engineer Sr | 169 | 170 | 173 | 178 | 182 | 187 | 191
FNCD_DATABASE_AYST | FNCD | DATABASE_AYST | Database Administration Analyst | 130 | 131 | 133 | 137 | 140 | 144 | 147
FNCD_DT_CNTR_OPERTNS | FNCD | DT_CNTR_OPERTNS | Data Center Facilities Operations | 130 | 131 | 133 | 137 | 140 | 144 | 147
FNCD_ELEC_DESIGN_EN | FNCD | ELEC_DESIGN_EN | Electrical Design Engineer | 131 | 132 | 135 | 138 | 142 | 145 | 149
FNCD_ELEC_DESIGN_SR | FNCD | ELEC_DESIGN_SR | Electrical Design Engineer Sr | 164 | 166 | 169 | 173 | 178 | 182 | 187
FNCD_ELEC_DESIGNER | FNCD | ELEC_DESIGNER | Electrical Designer | 101 | 102 | 104 | 107 | 109 | 112 | 115
FNCD_ELEC_DRAFTER | FNCD | ELEC_DRAFTER | Electrical Drafter | 71 | 71 | 73 | 74 | 76 | 78 | 80
FNCD_ELEC_TECH_MNGR | FNCD | ELEC_TECH_MNGR | Electrical Technical Manager | 199 | 201 | 205 | 210 | 215 | 220 | 226
FNCD_ELTN_DESIGN_EN | FNCD | ELTN_DESIGN_EN | Electronics Design Engineer | 135 | 136 | 138 | 142 | 145 | 149 | 153
FNCD_ELTN_DESIGN_SR | FNCD | ELTN_DESIGN_SR | Electronics Design Engineer Sr | 174 | 175 | 178 | 183 | 187 | 192 | 197
FNCD_ELTN_TECH | FNCD | ELTN_TECH | Electronics Technician | 89 | 90 | 92 | 94 | 96 | 99 | 101
FNCD_ENGNRING_PHYST | FNCD | ENGNRING_PHYST | Engineering Physicist | 144 | 145 | 148 | 151 | 155 | 159 | 163
FNCD_FACILITIES_MGMT | FNCD | FACILITIES_MGMT | Facilities Management | 121 | 122 | 125 | 128 | 131 | 134 | 138
FNCD_FUNCTNAL_AYST | FNCD | FUNCTNAL_AYST | Functional Analyst | 120 | 120 | 123 | 126 | 129 | 132 | 136
FNCD_GENERAL_ADMIN | FNCD | GENERAL_ADMIN | General Administrative | 88 | 89 | 90 | 93 | 95 | 97 | 100
FNCD_GENERAL_ESH | FNCD | GENERAL_ESH | General ES&H | 139 | 140 | 143 | 146 | 150 | 154 | 158
FNCD_INTERLOCK_EN | FNCD | INTERLOCK_EN | Interlock Engineer | 131 | 132 | 135 | 138 | 141 | 145 | 149
FNCD_INTERLOCK_SR | FNCD | INTERLOCK_SR | Interlock Engineer Sr | 163 | 164 | 167 | 171 | 176 | 180 | 185
FNCD_MAGNT_DESIGN_EN | FNCD | MAGNT_DESIGN_EN | Magnet Design Engineer | 152 | 153 | 156 | 160 | 164 | 168 | 173
FNCD_MAGNT_DESIGN_SR | FNCD | MAGNT_DESIGN_SR | Magnet Design Engineer Sr | 167 | 169 | 172 | 176 | 181 | 185 | 190
FNCD_MATRL_EN | FNCD | MATRL_EN | Materials Engineer | 84 | 85 | 86 | 88 | 91 | 93 | 95
FNCD_MATRL_SR | FNCD | MATRL_SR | Materials Engineer Sr | 84 | 85 | 86 | 88 | 91 | 93 | 95
FNCD_MATRL_SRVCS | FNCD | MATRL_SRVCS | Material Services | 77 | 78 | 79 | 81 | 83 | 85 | 87
FNCD_MECH_ANLYSIS_EN | FNCD | MECH_ANLYSIS_EN | Mechanical Analysis Engineer | 128 | 129 | 131 | 135 | 138 | 142 | 145
FNCD_MECH_ANLYSIS_SR | FNCD | MECH_ANLYSIS_SR | Mechanical Analysis Engineer Sr | 161 | 162 | 165 | 169 | 174 | 178 | 182
FNCD_MECH_DESIGN_EN | FNCD | MECH_DESIGN_EN | Mechanical Design Engineer | 133 | 134 | 137 | 140 | 144 | 147 | 151
FNCD_MECH_DESIGN_SR | FNCD | MECH_DESIGN_SR | Mechanical Design Engineer Sr | 168 | 170 | 173 | 177 | 182 | 186 | 191
FNCD_MECH_DESIGNER | FNCD | MECH_DESIGNER | Mechanical Designer | 97 | 98 | 100 | 103 | 105 | 108 | 111
FNCD_MECH_DRAFTER | FNCD | MECH_DRAFTER | Mechanical Drafter | 58 | 58 | 59 | 61 | 62 | 64 | 66
FNCD_MECH_TECH_MNGR | FNCD | MECH_TECH_MNGR | Mechanical Technical Manager | 173 | 175 | 178 | 183 | 187 | 192 | 197
FNCD_NETWORK_AYST | FNCD | NETWORK_AYST | Network Analyst | 134 | 135 | 138 | 141 | 145 | 148 | 152
FNCD_OPERTNS_FINANCE | FNCD | OPERTNS_FINANCE | Operations Finance | 127 | 128 | 130 | 133 | 137 | 140 | 144
FNCD_PA_EXP_PHYST | FNCD | PA_EXP_PHYST | Particle-Astro Physicist Experimental | 135 | 136 | 139 | 142 | 146 | 149 | 153
FNCD_PA_EXP_RA | FNCD | PA_EXP_RA | Particle-Astro Experimental Research Associate | 87 | 87 | 89 | 91 | 94 | 96 | 98
FNCD_PA_THY_RA | FNCD | PA_THY_RA | Particle-Astro Theory Research Associate | 87 | 87 | 89 | 91 | 94 | 96 | 98
FNCD_PC_CUSTM_SPPRT | FNCD | PC_CUSTM_SPPRT | Computer Customer Support | 91 | 92 | 94 | 96 | 99 | 101 | 104
FNCD_PC_SCI_RESRCHER | FNCD | PC_SCI_RESRCHER | Computer Science Researcher | 161 | 162 | 165 | 169 | 174 | 178 | 182
FNCD_PC_SECURTY_AYST | FNCD | PC_SECURTY_AYST | Computer Security Analyst | 151 | 152 | 155 | 159 | 163 | 167 | 171
FNCD_PC_SPPRT_ASSOCT | FNCD | PC_SPPRT_ASSOCT | PC Support Associate | 86 | 86 | 88 | 90 | 92 | 95 | 97
FNCD_PRCESS_CTRL_EN | FNCD | PRCESS_CTRL_EN | Process/Controls Engineer | 104 | 105 | 107 | 110 | 112 | 115 | 118
FNCD_PRCESS_CTRL_SR | FNCD | PRCESS_CTRL_SR | Process/Controls Engineer Sr | 142 | 143 | 146 | 149 | 153 | 157 | 161
FNCD_PRJ_CTRL_LEAD | FNCD | PRJ_CTRL_LEAD | Project Controls Lead | 129 | 131 | 133 | 136 | 140 | 143 | 147
FNCD_PRJ_CTRL_MNGR | FNCD | PRJ_CTRL_MNGR | Project Controls Manager | 176 | 178 | 181 | 186 | 190 | 195 | 200
FNCD_PRJ_CTRL_SPCLST | FNCD | PRJ_CTRL_SPCLST | Project Controls Specialist | 109 | 110 | 112 | 115 | 118 | 121 | 124
FNCD_PRJ_FINANCE | FNCD | PRJ_FINANCE | Project Finance | 125 | 126 | 129 | 132 | 135 | 139 | 142
FNCD_PRJ_MNGR | FNCD | PRJ_MNGR | Project Manager | 148 | 150 | 153 | 156 | 160 | 164 | 168
FNCD_PRJ_MNGR_EXC | FNCD | PRJ_MNGR_EXC | Project Manager Exec | 280 | 282 | 288 | 295 | 302 | 310 | 317
FNCD_PRJ_MNGR_SR | FNCD | PRJ_MNGR_SR | Project Manager Sr | 224 | 226 | 230 | 236 | 242 | 248 | 254
FNCD_PRJ_SPPRT | FNCD | PRJ_SPPRT | Project Support | 130 | 131 | 133 | 137 | 140 | 143 | 147
FNCD_PROCUREMENT | FNCD | PROCUREMENT | Procurement | 107 | 108 | 110 | 113 | 116 | 119 | 122
FNCD_PT_EXP_PHYST | FNCD | PT_EXP_PHYST | Particle Physicist Experimental | 131 | 132 | 135 | 138 | 141 | 145 | 148
FNCD_PT_EXP_RA | FNCD | PT_EXP_RA | Particle Physics Experimental Research Associate | 87 | 87 | 89 | 91 | 94 | 96 | 98
FNCD_PT_THY_PHYST | FNCD | PT_THY_PHYST | Particle Physicist Theory | 155 | 156 | 159 | 163 | 167 | 171 | 176
FNCD_PT_THY_RA | FNCD | PT_THY_RA | Particle Physics Theory Research Associate | 87 | 87 | 89 | 91 | 94 | 96 | 98
FNCD_PUBLIC_RELTIONS | FNCD | PUBLIC_RELTIONS | Public Relations | 98 | 98 | 100 | 103 | 105 | 108 | 111
FNCD_RF_DESIGN_EN | FNCD | RF_DESIGN_EN | RF Design Engineer | 141 | 142 | 145 | 148 | 152 | 156 | 160
FNCD_RF_DESIGN_SR | FNCD | RF_DESIGN_SR | RF Design Engineer Sr | 173 | 175 | 178 | 183 | 187 | 192 | 197
FNCD_SYSTM_ADMIN | FNCD | SYSTM_ADMIN | Systems Administrator | 111 | 112 | 114 | 117 | 120 | 123 | 126
FNCD_TRAINING | FNCD | TRAINING | Training | 116 | 117 | 120 | 123 | 126 | 129 | 132
FNCD_U_GENERAL_ESH | FNCD | U_GENERAL_ESH | General ES&H Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNCD_U_PA_EXP_PHYST | FNCD | U_PA_EXP_PHYST | Particle-Astro Physicist Experimental Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNCD_U_PA_EXP_RA | FNCD | U_PA_EXP_RA | Particle-Astro Experimental Research Associate Uncost | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNCD_U_PA_THY_RA | FNCD | U_PA_THY_RA | Particle-Astro Theory Research Associate Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNCD_U_PROCUREMENT | FNCD | U_PROCUREMENT | Procurement Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNCD_U_PT_EXP_PHYST | FNCD | U_PT_EXP_PHYST | Particle Physicist Experimental Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNCD_U_PT_EXP_RA | FNCD | U_PT_EXP_RA | Particle Physics Experimental Research Associate Unco | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNCD_U_PT_THY_PHYST | FNCD | U_PT_THY_PHYST | Particle Physicist Theory Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNCD_U_PT_THY_RA | FNCD | U_PT_THY_RA | Particle Physics Theory Research Associate Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNCD_WEB_APPS_DEVLPR | FNCD | WEB_APPS_DEVLPR | Web Applications Developer | 90 | 91 | 92 | 95 | 97 | 100 | 102
FNES_ACCOUNTANT | FNES | ACCOUNTANT | Accountant | 104 | 105 | 107 | 110 | 113 | 115 | 118
FNES_ADMIN_SPPRT | FNES | ADMIN_SPPRT | Administrative Support | 64 | 64 | 66 | 67 | 69 | 71 | 72
FNES_CLERICAL | FNES | CLERICAL | Clerical | 57 | 58 | 59 | 60 | 62 | 63 | 65
FNES_CONST_SAFETY | FNES | CONST_SAFETY | Construction Safety | 110 | 111 | 113 | 116 | 119 | 122 | 125
FNES_DATABASE_AYST | FNES | DATABASE_AYST | Database Administration Analyst | 117 | 118 | 121 | 124 | 127 | 130 | 133
FNES_DRIVER | FNES | DRIVER | Driver | 57 | 58 | 59 | 60 | 62 | 63 | 65
FNES_ELEC_DESIGN_EN | FNES | ELEC_DESIGN_EN | Electrical Design Engineer | 119 | 120 | 122 | 125 | 128 | 131 | 135
FNES_ELEC_DESIGN_SR | FNES | ELEC_DESIGN_SR | Electrical Design Engineer Sr | 149 | 150 | 153 | 157 | 161 | 165 | 169
FNES_ELEC_SAFETY | FNES | ELEC_SAFETY | Electrical Safety | 112 | 113 | 115 | 118 | 121 | 124 | 127
FNES_ELTN_DESIGN_EN | FNES | ELTN_DESIGN_EN | Electronics Design Engineer | 122 | 123 | 125 | 128 | 132 | 135 | 138
FNES_ELTN_DESIGN_SR | FNES | ELTN_DESIGN_SR | Electronics Design Engineer Sr | 157 | 158 | 161 | 166 | 170 | 174 | 178
FNES_ELTN_TECH | FNES | ELTN_TECH | Electronics Technician | 81 | 81 | 83 | 85 | 87 | 89 | 92
FNES_EMRGNCY_PLANNER | FNES | EMRGNCY_PLANNER | Emergency Planner | 108 | 109 | 112 | 114 | 117 | 120 | 123
FNES_ENVIRNMENTAL | FNES | ENVIRNMENTAL | Environmental | 113 | 114 | 117 | 119 | 122 | 126 | 129
FNES_FACILITIES_MGMT | FNES | FACILITIES_MGMT | Facilities Management | 110 | 111 | 113 | 116 | 118 | 121 | 124
FNES_GENERAL_ADMIN | FNES | GENERAL_ADMIN | General Administrative | 79 | 80 | 82 | 84 | 86 | 88 | 90
FNES_GENERAL_ESH | FNES | GENERAL_ESH | General ES&H | 126 | 127 | 129 | 132 | 136 | 139 | 143
FNES_INDSTRL_HYGT | FNES | INDSTRL_HYGT | Industrial Hygienist | 111 | 112 | 114 | 117 | 120 | 123 | 126
FNES_LABORTY_ANLYSIS | FNES | LABORTY_ANLYSIS | Laboratory Analysis | 107 | 108 | 110 | 112 | 115 | 118 | 121
FNES_OCCUP_NURSE | FNES | OCCUP_NURSE | Occupational Medicine Nurse | 73 | 73 | 75 | 77 | 79 | 81 | 83
FNES_OCCUP_PHYSICIAN | FNES | OCCUP_PHYSICIAN | Occupational Medicine Physician | 245 | 247 | 252 | 259 | 265 | 272 | 278
FNES_OPERTNS_FINANCE | FNES | OPERTNS_FINANCE | Operations Finance | 115 | 115 | 118 | 121 | 124 | 127 | 130
FNES_PA_EXP_PHYST | FNES | PA_EXP_PHYST | Particle-Astro Physicist Experimental | 122 | 123 | 126 | 129 | 132 | 135 | 139
FNES_RAD_PRTECTON | FNES | RAD_PRTECTON | Radiation Protection | 104 | 105 | 107 | 110 | 112 | 115 | 118
FNES_SAFETY | FNES | SAFETY | Safety | 112 | 113 | 115 | 118 | 121 | 124 | 127
FNES_SYSTM_ADMIN | FNES | SYSTM_ADMIN | Systems Administrator | 101 | 102 | 104 | 106 | 109 | 112 | 114
FNES_TRAINING | FNES | TRAINING | Training | 105 | 106 | 108 | 111 | 114 | 117 | 120
FNES_U_CONST_SAFETY | FNES | U_CONST_SAFETY | Construction Safety Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNES_U_ENVIRNMENTAL | FNES | U_ENVIRNMENTAL | Environmental Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNES_U_GENERAL_ESH | FNES | U_GENERAL_ESH | General ES&H Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNES_U_INDSTRL_HYGT | FNES | U_INDSTRL_HYGT | Industrial Hygienist Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNES_U_RAD_PRTECTON | FNES | U_RAD_PRTECTON | Radiation Protection Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNES_U_SAFETY | FNES | U_SAFETY | Safety Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNES_WASTE_MANAGEMNT | FNES | WASTE_MANAGEMNT | Waste Management | 78 | 78 | 80 | 82 | 84 | 86 | 88
FNFE_CFS_DESIGN_EN | FNFE | CFS_DESIGN_EN | CFS Design Engineer | 141 | 145 | 149 | 153 | 157 | 161 | 165
FNFE_CONST_COORDNATR | FNFE | CONST_COORDNATR | Construction Coordinator | 141 | 145 | 149 | 153 | 157 | 161 | 165
FNOF_ADMIN_SPPRT | FNOF | ADMIN_SPPRT | Administrative Support | 64 | 64 | 66 | 67 | 69 | 71 | 72
FNOF_APDEV_SYSTMAYST | FNOF | APDEV_SYSTMAYST | Applications Development & Systems Analyst | 119 | 120 | 122 | 125 | 128 | 131 | 135
FNOF_CT_SRVCS_SPCLST | FNOF | CT_SRVCS_SPCLST | Computing Services Specialist | 129 | 130 | 132 | 136 | 139 | 143 | 146
FNOF_FUNCTNAL_AYST | FNOF | FUNCTNAL_AYST | Functional Analyst | 108 | 109 | 111 | 114 | 117 | 120 | 123
FNOF_OPERTNS_FINANCE | FNOF | OPERTNS_FINANCE | Operations Finance | 115 | 115 | 118 | 121 | 124 | 127 | 130
FNOF_PC_SCI_RESRCHER | FNOF | PC_SCI_RESRCHER | Computer Science Researcher | 145 | 147 | 149 | 153 | 157 | 161 | 165
FNOF_PC_SECURTY_AYST | FNOF | PC_SECURTY_AYST | Computer Security Analyst | 137 | 138 | 140 | 144 | 148 | 151 | 155
FNOF_PRJ_MNGR | FNOF | PRJ_MNGR | Project Manager | 134 | 135 | 138 | 141 | 145 | 149 | 152
FNOF_PRJ_MNGR_EXC | FNOF | PRJ_MNGR_EXC | Project Manager Exec | 253 | 255 | 260 | 267 | 273 | 280 | 287
FNOF_PRJ_MNGR_SR | FNOF | PRJ_MNGR_SR | Project Manager Sr | 203 | 204 | 208 | 213 | 219 | 224 | 230
FNOF_PT_EXP_PHYST | FNOF | PT_EXP_PHYST | Particle Physicist Experimental | 118 | 119 | 122 | 125 | 128 | 131 | 134
FNOF_PUBLIC_RELTIONS | FNOF | PUBLIC_RELTIONS | Public Relations | 88 | 89 | 91 | 93 | 95 | 98 | 100
FNOF_U_PT_EXP_PHYST | FNOF | U_PT_EXP_PHYST | Particle Physicist Experimental Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNOF_WEB_APPS_DEVLPR | FNOF | WEB_APPS_DEVLPR | Web Applications Developer | 81 | 82 | 84 | 86 | 88 | 90 | 92
FNPD_AC_EXP_RA | FNPD | AC_EXP_RA | Accelerator Experimental Research Associate | 91 | 92 | 93 | 96 | 98 | 101 | 103
FNPD_AC_SYSTM_SPCLST | FNPD | AC_SYSTM_SPCLST | Accelerator Systems Specialist | 127 | 128 | 131 | 134 | 138 | 141 | 145
FNPD_AC_THY_RA | FNPD | AC_THY_RA | Accelerator Theory Research Associate | 91 | 92 | 93 | 96 | 98 | 101 | 103
FNPD_ACCOUNTANT | FNPD | ACCOUNTANT | Accountant | 121 | 122 | 124 | 127 | 130 | 134 | 137
FNPD_ADMIN_SPPRT | FNPD | ADMIN_SPPRT | Administrative Support | 74 | 75 | 76 | 78 | 80 | 82 | 84
FNPD_APDEV_SYSTMAYST | FNPD | APDEV_SYSTMAYST | Applications Development & Systems Analyst | 137 | 138 | 141 | 145 | 148 | 152 | 156
FNPD_ASIC_DESIGN_EN | FNPD | ASIC_DESIGN_EN | ASIC Design Engineer | 138 | 139 | 141 | 145 | 149 | 152 | 156
FNPD_ASIC_DESIGN_SR | FNPD | ASIC_DESIGN_SR | ASIC Design Engineer Sr | 193 | 195 | 199 | 204 | 209 | 214 | 220
FNPD_BUILDING_SRVCS | FNPD | BUILDING_SRVCS | Building Services | 95 | 95 | 97 | 100 | 102 | 105 | 107
FNPD_CHEMIST | FNPD | CHEMIST | Chemist | 100 | 101 | 103 | 106 | 109 | 111 | 114
FNPD_CLERICAL | FNPD | CLERICAL | Clerical | 66 | 67 | 68 | 70 | 72 | 73 | 75
FNPD_CONST_COORDNATR | FNPD | CONST_COORDNATR | Construction Coordinator | 128 | 129 | 132 | 135 | 138 | 142 | 145
FNPD_CP_PHYCS_DEVLPR | FNPD | CP_PHYCS_DEVLPR | Computational Physics Developer | 125 | 126 | 129 | 132 | 135 | 138 | 142
FNPD_CRYO_EN | FNPD | CRYO_EN | Cryogenics Engineer | 142 | 143 | 146 | 149 | 153 | 157 | 161
FNPD_CRYO_SR | FNPD | CRYO_SR | Cryogenics Engineer Sr | 194 | 196 | 200 | 205 | 210 | 215 | 221
FNPD_CRYO_TECH | FNPD | CRYO_TECH | Cryo Technician | 82 | 82 | 84 | 86 | 88 | 91 | 93
FNPD_CT_SRVCS_SPCLST | FNPD | CT_SRVCS_SPCLST | Computing Services Specialist | 149 | 150 | 153 | 157 | 161 | 165 | 169
FNPD_CTRL_SYSTM_EN | FNPD | CTRL_SYSTM_EN | Control System Engineer | 145 | 146 | 149 | 153 | 157 | 160 | 164
FNPD_CTRL_SYSTM_SR | FNPD | CTRL_SYSTM_SR | Control System Engineer Sr | 177 | 178 | 182 | 186 | 191 | 196 | 201
FNPD_DATABASE_AYST | FNPD | DATABASE_AYST | Database Administration Analyst | 136 | 137 | 140 | 143 | 147 | 150 | 154
FNPD_ELEC_ASMBY_TECH | FNPD | ELEC_ASMBY_TECH | Electrical Assembly Technician | 75 | 76 | 78 | 80 | 82 | 84 | 86
FNPD_ELEC_DESIGN_EN | FNPD | ELEC_DESIGN_EN | Electrical Design Engineer | 138 | 139 | 141 | 145 | 149 | 152 | 156
FNPD_ELEC_DESIGN_SR | FNPD | ELEC_DESIGN_SR | Electrical Design Engineer Sr | 172 | 174 | 177 | 182 | 186 | 191 | 195
FNPD_ELEC_DESIGNER | FNPD | ELEC_DESIGNER | Electrical Designer | 106 | 107 | 109 | 112 | 114 | 117 | 120
FNPD_ELEC_DRAFTER | FNPD | ELEC_DRAFTER | Electrical Drafter | 74 | 75 | 76 | 78 | 80 | 82 | 84
FNPD_ELEC_TASK_MNGR | FNPD | ELEC_TASK_MNGR | Electrical Task Manager | 129 | 130 | 132 | 136 | 139 | 143 | 146
FNPD_ELEC_TECH | FNPD | ELEC_TECH | Electrical Technician | 86 | 87 | 89 | 91 | 93 | 96 | 98
FNPD_ELEC_TECH_MNGR | FNPD | ELEC_TECH_MNGR | Electrical Technical Manager | 209 | 210 | 214 | 220 | 225 | 231 | 237
FNPD_ELEC_TECH_SPVSR | FNPD | ELEC_TECH_SPVSR | Electrical Technician Supervisor | 122 | 123 | 125 | 128 | 131 | 135 | 138
FNPD_ELTN_DESIGN_EN | FNPD | ELTN_DESIGN_EN | Electronics Design Engineer | 141 | 142 | 145 | 149 | 152 | 156 | 160
FNPD_ELTN_DESIGN_SR | FNPD | ELTN_DESIGN_SR | Electronics Design Engineer Sr | 182 | 183 | 187 | 192 | 196 | 201 | 206
FNPD_ELTN_TECH | FNPD | ELTN_TECH | Electronics Technician | 94 | 94 | 96 | 99 | 101 | 104 | 106
FNPD_ENGNRING_PHYST | FNPD | ENGNRING_PHYST | Engineering Physicist | 150 | 152 | 155 | 159 | 162 | 167 | 171
FNPD_EXECUTIVE_DIRCT | FNPD | EXECUTIVE_DIRCT | Executive Direction | 385 | 388 | 396 | 406 | 416 | 426 | 437
FNPD_FABRCATN_SPCLST | FNPD | FABRCATN_SPCLST | Fabrication Specialist | 111 | 112 | 114 | 117 | 120 | 123 | 126
FNPD_FACILITIES_MGMT | FNPD | FACILITIES_MGMT | Facilities Management | 127 | 128 | 131 | 134 | 137 | 141 | 144
FNPD_GENERAL_ADMIN | FNPD | GENERAL_ADMIN | General Administrative | 92 | 93 | 95 | 97 | 99 | 102 | 104
FNPD_GENERAL_ESH | FNPD | GENERAL_ESH | General ES&H | 145 | 147 | 150 | 153 | 157 | 161 | 165
FNPD_GEODEIST | FNPD | GEODEIST | Geodesist | 143 | 144 | 147 | 150 | 154 | 158 | 162
FNPD_HIGH_VAC_TECH | FNPD | HIGH_VAC_TECH | High Vac Technician | 83 | 84 | 86 | 88 | 90 | 92 | 95
FNPD_INSTRUMENT_TECH | FNPD | INSTRUMENT_TECH | Mechanical Instrument Technician | 92 | 92 | 94 | 97 | 99 | 102 | 104
FNPD_INTERLOCK_EN | FNPD | INTERLOCK_EN | Interlock Engineer | 137 | 138 | 141 | 145 | 148 | 152 | 156
FNPD_INTERLOCK_SR | FNPD | INTERLOCK_SR | Interlock Engineer Sr | 170 | 172 | 175 | 180 | 184 | 189 | 193
FNPD_MAGNT_DESIGN_EN | FNPD | MAGNT_DESIGN_EN | Magnet Design Engineer | 159 | 161 | 164 | 168 | 172 | 177 | 181
FNPD_MAGNT_DESIGN_SR | FNPD | MAGNT_DESIGN_SR | Magnet Design Engineer Sr | 175 | 177 | 180 | 185 | 190 | 194 | 199
FNPD_MATRL_EN | FNPD | MATRL_EN | Materials Engineer | 88 | 89 | 90 | 93 | 95 | 97 | 100
FNPD_MATRL_SR | FNPD | MATRL_SR | Materials Engineer Sr | 88 | 89 | 90 | 93 | 95 | 97 | 100
FNPD_MECH_ANLYSIS_EN | FNPD | MECH_ANLYSIS_EN | Mechanical Analysis Engineer | 134 | 135 | 138 | 141 | 145 | 148 | 152
FNPD_MECH_ANLYSIS_SR | FNPD | MECH_ANLYSIS_SR | Mechanical Analysis Engineer Sr | 169 | 170 | 173 | 178 | 182 | 187 | 191
FNPD_MECH_ASMBY_TECH | FNPD | MECH_ASMBY_TECH | Mechanical Assembly Technician | 86 | 87 | 88 | 91 | 93 | 95 | 98
FNPD_MECH_DESIGN_EN | FNPD | MECH_DESIGN_EN | Mechanical Design Engineer | 139 | 140 | 143 | 147 | 151 | 154 | 158
FNPD_MECH_DESIGN_SR | FNPD | MECH_DESIGN_SR | Mechanical Design Engineer Sr | 176 | 178 | 181 | 186 | 191 | 195 | 200
FNPD_MECH_DESIGNER | FNPD | MECH_DESIGNER | Mechanical Designer | 102 | 103 | 105 | 108 | 110 | 113 | 116
FNPD_MECH_DRAFTER | FNPD | MECH_DRAFTER | Mechanical Drafter | 60 | 61 | 62 | 64 | 65 | 67 | 69
FNPD_MECH_TECH_MNGR | FNPD | MECH_TECH_MNGR | Mechanical Technical Manager | 182 | 183 | 187 | 192 | 196 | 201 | 206
FNPD_MECH_TECH_SPVSR | FNPD | MECH_TECH_SPVSR | Mechanical Technician Supervisor | 122 | 123 | 125 | 128 | 132 | 135 | 138
FNPD_METROLOGIST | FNPD | METROLOGIST | Metrologist | 92 | 93 | 95 | 97 | 100 | 102 | 105
FNPD_OPERTNS_FINANCE | FNPD | OPERTNS_FINANCE | Operations Finance | 133 | 134 | 136 | 140 | 143 | 147 | 151
FNPD_PA_EXP_PHYST | FNPD | PA_EXP_PHYST | Particle-Astro Physicist Experimental | 141 | 143 | 145 | 149 | 153 | 157 | 161
FNPD_PA_EXP_RA | FNPD | PA_EXP_RA | Particle-Astro Experimental Research Associate | 91 | 92 | 93 | 96 | 98 | 101 | 103
FNPD_PA_THY_PHYST | FNPD | PA_THY_PHYST | Particle-Astro Physicist Theory | 135 | 136 | 139 | 142 | 146 | 150 | 153
FNPD_PA_THY_RA | FNPD | PA_THY_RA | Particle-Astro Theory Research Associate | 91 | 92 | 93 | 96 | 98 | 101 | 103
FNPD_PRCESS_CTRL_EN | FNPD | PRCESS_CTRL_EN | Process/Controls Engineer | 109 | 110 | 112 | 115 | 118 | 121 | 124
FNPD_PRCESS_CTRL_SR | FNPD | PRCESS_CTRL_SR | Process/Controls Engineer Sr | 149 | 150 | 153 | 157 | 160 | 165 | 169
FNPD_PRJ_CTRL_LEAD | FNPD | PRJ_CTRL_LEAD | Project Controls Lead | 136 | 137 | 140 | 143 | 147 | 150 | 154
FNPD_PRJ_CTRL_MNGR | FNPD | PRJ_CTRL_MNGR | Project Controls Manager | 185 | 186 | 190 | 195 | 200 | 204 | 210
FNPD_PRJ_CTRL_SPCLST | FNPD | PRJ_CTRL_SPCLST | Project Controls Specialist | 114 | 115 | 118 | 120 | 124 | 127 | 130
FNPD_PRJ_FINANCE | FNPD | PRJ_FINANCE | Project Finance | 131 | 132 | 135 | 138 | 142 | 145 | 149
FNPD_PRJ_MNGR | FNPD | PRJ_MNGR | Project Manager | 155 | 157 | 160 | 164 | 168 | 172 | 176
FNPD_PRJ_MNGR_EXC | FNPD | PRJ_MNGR_EXC | Project Manager Exec | 293 | 295 | 301 | 309 | 317 | 325 | 333
FNPD_PRJ_MNGR_SR | FNPD | PRJ_MNGR_SR | Project Manager Sr | 235 | 236 | 241 | 247 | 253 | 260 | 266
FNPD_PRJ_SPPRT | FNPD | PRJ_SPPRT | Project Support | 136 | 137 | 140 | 143 | 147 | 150 | 154
FNPD_PROCUREMENT | FNPD | PROCUREMENT | Procurement | 112 | 113 | 115 | 118 | 121 | 124 | 127
FNPD_PT_EXP_PHYST | FNPD | PT_EXP_PHYST | Particle Physicist Experimental | 137 | 138 | 141 | 144 | 148 | 152 | 156
FNPD_PT_EXP_RA | FNPD | PT_EXP_RA | Particle Physics Experimental Research Associate | 91 | 92 | 93 | 96 | 98 | 101 | 103
FNPD_PT_THY_PHYST | FNPD | PT_THY_PHYST | Particle Physicist Theory | 162 | 164 | 167 | 171 | 175 | 180 | 184
FNPD_PT_THY_RA | FNPD | PT_THY_RA | Particle Physics Theory Research Associate | 91 | 92 | 93 | 96 | 98 | 101 | 103
FNPD_RAD_PRTECTON | FNPD | RAD_PRTECTON | Radiation Protection | 120 | 121 | 124 | 127 | 130 | 133 | 137
FNPD_SAFETY | FNPD | SAFETY | Safety | 130 | 131 | 134 | 137 | 140 | 144 | 147
FNPD_SYSTM_ADMIN | FNPD | SYSTM_ADMIN | Systems Administrator | 117 | 118 | 120 | 123 | 126 | 129 | 132
FNPD_TRAINING | FNPD | TRAINING | Training | 122 | 123 | 125 | 129 | 132 | 135 | 138
FNPD_U_GENERAL_ESH | FNPD | U_GENERAL_ESH | General ES&H Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNPD_U_PA_EXP_PHYST | FNPD | U_PA_EXP_PHYST | Particle-Astro Physicist Experimental Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNPD_U_PA_EXP_RA | FNPD | U_PA_EXP_RA | Particle-Astro Experimental Research Associate Uncost | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNPD_U_PA_THY_PHYST | FNPD | U_PA_THY_PHYST | Particle-Astro Physicist Theory Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNPD_U_PA_THY_RA | FNPD | U_PA_THY_RA | Particle-Astro Theory Research Associate Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNPD_U_PROCUREMENT | FNPD | U_PROCUREMENT | Procurement Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNPD_U_PT_EXP_PHYST | FNPD | U_PT_EXP_PHYST | Particle Physicist Experimental Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNPD_U_PT_EXP_RA | FNPD | U_PT_EXP_RA | Particle Physics Experimental Research Associate Unco | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNPD_U_PT_THY_PHYST | FNPD | U_PT_THY_PHYST | Particle Physicist Theory Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNPD_U_PT_THY_RA | FNPD | U_PT_THY_RA | Particle Physics Theory Research Associate Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNPD_U_RAD_PRTECTON | FNPD | U_RAD_PRTECTON | Radiation Protection Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNPD_U_SAFETY | FNPD | U_SAFETY | Safety Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNTD_AC_EXP_PHYST | FNTD | AC_EXP_PHYST | Accelerator Physicist Experimental | 158 | 160 | 163 | 167 | 171 | 175 | 180
FNTD_AC_EXP_RA | FNTD | AC_EXP_RA | Accelerator Experimental Research Associate | 96 | 97 | 99 | 101 | 104 | 106 | 109
FNTD_AC_THY_PHYST | FNTD | AC_THY_PHYST | Accelerator Physicist Theory | 174 | 175 | 179 | 183 | 188 | 192 | 197
FNTD_AC_THY_RA | FNTD | AC_THY_RA | Accelerator Theory Research Associate | 96 | 97 | 99 | 101 | 104 | 106 | 109
FNTD_ACCOUNTANT | FNTD | ACCOUNTANT | Accountant | 128 | 129 | 131 | 134 | 138 | 141 | 145
FNTD_ADMIN_SPPRT | FNTD | ADMIN_SPPRT | Administrative Support | 78 | 79 | 80 | 82 | 85 | 87 | 89
FNTD_APDEV_SYSTMAYST | FNTD | APDEV_SYSTMAYST | Applications Development & Systems Analyst | 145 | 146 | 149 | 153 | 157 | 161 | 165
FNTD_ASIC_DESIGN_EN | FNTD | ASIC_DESIGN_EN | ASIC Design Engineer | 145 | 147 | 150 | 153 | 157 | 161 | 165
FNTD_ASIC_DESIGN_SR | FNTD | ASIC_DESIGN_SR | ASIC Design Engineer Sr | 205 | 206 | 210 | 216 | 221 | 227 | 232
FNTD_CHEMIST | FNTD | CHEMIST | Chemist | 106 | 107 | 109 | 112 | 115 | 118 | 121
FNTD_CLERICAL | FNTD | CLERICAL | Clerical | 70 | 71 | 72 | 74 | 76 | 78 | 80
FNTD_CONST_COORDNATR | FNTD | CONST_COORDNATR | Construction Coordinator | 136 | 137 | 139 | 143 | 146 | 150 | 154
FNTD_CONST_MNGR | FNTD | CONST_MNGR | Construction Manager | 136 | 137 | 139 | 143 | 146 | 150 | 154
FNTD_CRYO_DESIGNER | FNTD | CRYO_DESIGNER | Cryo Designer | 103 | 104 | 106 | 109 | 111 | 114 | 117
FNTD_CRYO_EN | FNTD | CRYO_EN | Cryogenics Engineer | 150 | 151 | 154 | 158 | 162 | 166 | 170
FNTD_CRYO_SR | FNTD | CRYO_SR | Cryogenics Engineer Sr | 206 | 207 | 211 | 217 | 222 | 228 | 233
FNTD_CRYO_TECH | FNTD | CRYO_TECH | Cryo Technician | 86 | 87 | 89 | 91 | 93 | 96 | 98
FNTD_CTRL_SYSTM_EN | FNTD | CTRL_SYSTM_EN | Control System Engineer | 153 | 154 | 158 | 162 | 166 | 170 | 174
FNTD_CTRL_SYSTM_SR | FNTD | CTRL_SYSTM_SR | Control System Engineer Sr | 187 | 189 | 192 | 197 | 202 | 207 | 212
FNTD_ELEC_ASMBY_TECH | FNTD | ELEC_ASMBY_TECH | Electrical Assembly Technician | 80 | 80 | 82 | 84 | 86 | 88 | 91
FNTD_ELEC_DESIGN_EN | FNTD | ELEC_DESIGN_EN | Electrical Design Engineer | 145 | 147 | 150 | 153 | 157 | 161 | 165
FNTD_ELEC_DESIGN_SR | FNTD | ELEC_DESIGN_SR | Electrical Design Engineer Sr | 182 | 184 | 187 | 192 | 197 | 202 | 207
FNTD_ELEC_DESIGNER | FNTD | ELEC_DESIGNER | Electrical Designer | 112 | 113 | 115 | 118 | 121 | 124 | 127
FNTD_ELEC_DRAFTER | FNTD | ELEC_DRAFTER | Electrical Drafter | 78 | 79 | 81 | 83 | 85 | 87 | 89
FNTD_ELEC_TECH | FNTD | ELEC_TECH | Electrical Technician | 91 | 92 | 94 | 96 | 99 | 101 | 104
FNTD_ELEC_TECH_MNGR | FNTD | ELEC_TECH_MNGR | Electrical Technical Manager | 221 | 222 | 227 | 233 | 238 | 244 | 250
FNTD_ELEC_TECH_SPVSR | FNTD | ELEC_TECH_SPVSR | Electrical Technician Supervisor | 129 | 130 | 132 | 135 | 139 | 142 | 146
FNTD_ELTN_DESIGN_EN | FNTD | ELTN_DESIGN_EN | Electronics Design Engineer | 149 | 150 | 153 | 157 | 161 | 165 | 169
FNTD_ELTN_DESIGN_SR | FNTD | ELTN_DESIGN_SR | Electronics Design Engineer Sr | 192 | 194 | 198 | 203 | 208 | 213 | 218
FNTD_ELTN_TECH | FNTD | ELTN_TECH | Electronics Technician | 99 | 100 | 102 | 104 | 107 | 110 | 112
FNTD_ENGNRING_PHYST | FNTD | ENGNRING_PHYST | Engineering Physicist | 159 | 160 | 164 | 168 | 172 | 176 | 181
FNTD_FABRCATN_SPCLST | FNTD | FABRCATN_SPCLST | Fabrication Specialist | 117 | 118 | 121 | 124 | 127 | 130 | 133
FNTD_FACILITIES_MGMT | FNTD | FACILITIES_MGMT | Facilities Management | 134 | 135 | 138 | 142 | 145 | 149 | 152
FNTD_GENERAL_ADMIN | FNTD | GENERAL_ADMIN | General Administrative | 97 | 98 | 100 | 103 | 105 | 108 | 111
FNTD_GENERAL_ESH | FNTD | GENERAL_ESH | General ES&H | 154 | 155 | 158 | 162 | 166 | 170 | 175
FNTD_HIGH_VAC_TECH | FNTD | HIGH_VAC_TECH | High Vac Technician | 88 | 89 | 91 | 93 | 95 | 98 | 100
FNTD_INSTRUMENT_TECH | FNTD | INSTRUMENT_TECH | Mechanical Instrument Technician | 97 | 98 | 100 | 102 | 105 | 107 | 110
FNTD_INTERLOCK_EN | FNTD | INTERLOCK_EN | Interlock Engineer | 145 | 146 | 149 | 153 | 157 | 161 | 165
FNTD_INTERLOCK_SR | FNTD | INTERLOCK_SR | Interlock Engineer Sr | 180 | 182 | 185 | 190 | 195 | 200 | 205
FNTD_MACHINIST | FNTD | MACHINIST | Machinist | 114 | 114 | 117 | 120 | 123 | 126 | 129
FNTD_MAGNT_DESIGN_EN | FNTD | MAGNT_DESIGN_EN | Magnet Design Engineer | 169 | 170 | 173 | 178 | 182 | 187 | 191
FNTD_MAGNT_DESIGN_SR | FNTD | MAGNT_DESIGN_SR | Magnet Design Engineer Sr | 186 | 187 | 191 | 196 | 200 | 206 | 211
FNTD_MAGNT_DESIGNER | FNTD | MAGNT_DESIGNER | Magnet Designer | 109 | 110 | 112 | 115 | 118 | 121 | 124
FNTD_MAGNT_RA | FNTD | MAGNT_RA | Magnet Research Associate | 96 | 97 | 99 | 101 | 104 | 106 | 109
FNTD_MAGNT_SCIENTIST | FNTD | MAGNT_SCIENTIST | Magnet Scientist | 163 | 164 | 167 | 171 | 176 | 180 | 185
FNTD_MATRL_EN | FNTD | MATRL_EN | Materials Engineer | 93 | 94 | 96 | 98 | 101 | 103 | 106
FNTD_MATRL_RA | FNTD | MATRL_RA | Material Research Associate | 96 | 97 | 99 | 101 | 104 | 106 | 109
FNTD_MATRL_SCIENTIST | FNTD | MATRL_SCIENTIST | Material Scientist | 198 | 200 | 204 | 209 | 214 | 219 | 225
FNTD_MATRL_SR | FNTD | MATRL_SR | Materials Engineer Sr | 93 | 94 | 96 | 98 | 101 | 103 | 106
FNTD_MECH_ANLYSIS_EN | FNTD | MECH_ANLYSIS_EN | Mechanical Analysis Engineer | 142 | 143 | 146 | 149 | 153 | 157 | 161
FNTD_MECH_ANLYSIS_SR | FNTD | MECH_ANLYSIS_SR | Mechanical Analysis Engineer Sr | 178 | 180 | 183 | 188 | 193 | 197 | 202
FNTD_MECH_ASMBY_TECH | FNTD | MECH_ASMBY_TECH | Mechanical Assembly Technician | 91 | 92 | 93 | 96 | 98 | 101 | 103
FNTD_MECH_DESIGN_EN | FNTD | MECH_DESIGN_EN | Mechanical Design Engineer | 147 | 149 | 152 | 155 | 159 | 163 | 167
FNTD_MECH_DESIGN_SR | FNTD | MECH_DESIGN_SR | Mechanical Design Engineer Sr | 187 | 188 | 192 | 197 | 202 | 207 | 212
FNTD_MECH_DESIGNER | FNTD | MECH_DESIGNER | Mechanical Designer | 108 | 109 | 111 | 114 | 117 | 120 | 123
FNTD_MECH_DRAFTER | FNTD | MECH_DRAFTER | Mechanical Drafter | 64 | 64 | 66 | 67 | 69 | 71 | 73
FNTD_MECH_SYSTM_TECH | FNTD | MECH_SYSTM_TECH | Mechanical Systems Technician | 79 | 79 | 81 | 83 | 85 | 87 | 89
FNTD_MECH_TECH_MNGR | FNTD | MECH_TECH_MNGR | Mechanical Technical Manager | 192 | 194 | 198 | 203 | 208 | 213 | 218
FNTD_MECH_TECH_SPVSR | FNTD | MECH_TECH_SPVSR | Mechanical Technician Supervisor | 129 | 130 | 133 | 136 | 139 | 143 | 146
FNTD_OPERTNS_FINANCE | FNTD | OPERTNS_FINANCE | Operations Finance | 140 | 141 | 144 | 148 | 152 | 155 | 159
FNTD_PA_EXP_PHYST | FNTD | PA_EXP_PHYST | Particle-Astro Physicist Experimental | 150 | 151 | 154 | 158 | 162 | 166 | 170
FNTD_PA_EXP_RA | FNTD | PA_EXP_RA | Particle-Astro Experimental Research Associate | 96 | 97 | 99 | 101 | 104 | 106 | 109
FNTD_PA_THY_RA | FNTD | PA_THY_RA | Particle-Astro Theory Research Associate | 96 | 97 | 99 | 101 | 104 | 106 | 109
FNTD_PRCESS_CTRL_EN | FNTD | PRCESS_CTRL_EN | Process/Controls Engineer | 115 | 116 | 118 | 121 | 124 | 128 | 131
FNTD_PRCESS_CTRL_SR | FNTD | PRCESS_CTRL_SR | Process/Controls Engineer Sr | 157 | 158 | 162 | 166 | 170 | 174 | 178
FNTD_PRJ_CTRL_LEAD | FNTD | PRJ_CTRL_LEAD | Project Controls Lead | 144 | 145 | 148 | 151 | 155 | 159 | 163
FNTD_PRJ_CTRL_MNGR | FNTD | PRJ_CTRL_MNGR | Project Controls Manager | 195 | 197 | 201 | 206 | 211 | 216 | 222
FNTD_PRJ_CTRL_SPCLST | FNTD | PRJ_CTRL_SPCLST | Project Controls Specialist | 121 | 122 | 124 | 127 | 131 | 134 | 137
FNTD_PRJ_FINANCE | FNTD | PRJ_FINANCE | Project Finance | 139 | 140 | 143 | 146 | 150 | 154 | 158
FNTD_PRJ_MNGR | FNTD | PRJ_MNGR | Project Manager | 164 | 166 | 169 | 173 | 178 | 182 | 187
FNTD_PRJ_MNGR_EXC | FNTD | PRJ_MNGR_EXC | Project Manager Exec | 310 | 313 | 319 | 327 | 335 | 343 | 352
FNTD_PRJ_MNGR_SR | FNTD | PRJ_MNGR_SR | Project Manager Sr | 248 | 250 | 255 | 261 | 268 | 275 | 282
FNTD_PRJ_SPPRT | FNTD | PRJ_SPPRT | Project Support | 144 | 145 | 148 | 151 | 155 | 159 | 163
FNTD_PROCUREMENT | FNTD | PROCUREMENT | Procurement | 119 | 120 | 122 | 125 | 128 | 131 | 135
FNTD_PT_EXP_PHYST | FNTD | PT_EXP_PHYST | Particle Physicist Experimental | 145 | 146 | 149 | 153 | 157 | 161 | 165
FNTD_PT_EXP_RA | FNTD | PT_EXP_RA | Particle Physics Experimental Research Associate | 96 | 97 | 99 | 101 | 104 | 106 | 109
FNTD_PT_THY_RA | FNTD | PT_THY_RA | Particle Physics Theory Research Associate | 96 | 97 | 99 | 101 | 104 | 106 | 109
FNTD_QC_TECHNICAL | FNTD | QC_TECHNICAL | QC Technical | 103 | 104 | 106 | 109 | 112 | 115 | 117
FNTD_QLTY_ASSRANCE | FNTD | QLTY_ASSRANCE | Quality Assurance | 158 | 159 | 163 | 167 | 171 | 175 | 179
FNTD_RF_DESIGN_EN | FNTD | RF_DESIGN_EN | RF Design Engineer | 156 | 157 | 160 | 164 | 169 | 173 | 177
FNTD_RF_DESIGN_SR | FNTD | RF_DESIGN_SR | RF Design Engineer Sr | 192 | 194 | 198 | 203 | 208 | 213 | 218
FNTD_RF_RA | FNTD | RF_RA | RF Research Associate | 96 | 97 | 99 | 101 | 104 | 106 | 109
FNTD_RF_SCIENTIST | FNTD | RF_SCIENTIST | RF Scientist | 179 | 181 | 184 | 189 | 193 | 198 | 203
FNTD_SRF_TECH | FNTD | SRF_TECH | Mechanical SRF Technician | 80 | 81 | 82 | 84 | 86 | 88 | 91
FNTD_TRAINING | FNTD | TRAINING | Training | 129 | 130 | 133 | 136 | 139 | 143 | 146
FNTD_U_GENERAL_ESH | FNTD | U_GENERAL_ESH | General ES&H Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNTD_U_MAG_SCIENTIST | FNTD | U_MAG_SCIENTIST | Magnet Scientist - Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNTD_U_MATRL_RA | FNTD | U_MATRL_RA | Material Research Associate Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNTD_U_PA_EXP_PHYST | FNTD | U_PA_EXP_PHYST | Particle-Astro Physicist Experimental Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNTD_U_PA_EXP_RA | FNTD | U_PA_EXP_RA | Particle-Astro Experimental Research Associate Uncost | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNTD_U_PA_THY_RA | FNTD | U_PA_THY_RA | Particle-Astro Theory Research Associate Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNTD_U_PROCUREMENT | FNTD | U_PROCUREMENT | Procurement Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNTD_U_PT_EXP_PHYST | FNTD | U_PT_EXP_PHYST | Particle Physicist Experimental Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNTD_U_PT_EXP_RA | FNTD | U_PT_EXP_RA | Particle Physics Experimental Research Associate Unco | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNTD_U_PT_THY_RA | FNTD | U_PT_THY_RA | Particle Physics Theory Research Associate Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNTD_U_RF_RA | FNTD | U_RF_RA | RF Research Associate Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNTD_U_RF_SCIENTIST | FNTD | U_RF_SCIENTIST | RF Scientist Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
FNTD_WEB_APPS_DEVLPR | FNTD | WEB_APPS_DEVLPR | Web Applications Developer | 100 | 100 | 102 | 105 | 108 | 110 | 113
FNTD_WELDER | FNTD | WELDER | Welder | 114 | 114 | 117 | 120 | 123 | 126 | 129
GM2ANL_APDEV_SYSTMAYST | GM2ANL | APDEV_SYSTMAYST | Applications Development & Systems Analyst | 137 | 138 | 141 | 145 | 148 | 152 | 156
GM2ANL_CP_PHYCS_DEVLPR | GM2ANL | CP_PHYCS_DEVLPR | Computational Physics Developer | 125 | 126 | 129 | 132 | 135 | 138 | 142
GM2ANL_CT_SRVCS_SPCLST | GM2ANL | CT_SRVCS_SPCLST | Computing Services Specialist | 149 | 150 | 153 | 157 | 161 | 165 | 169
GM2ANL_CTRL_SYSTM_EN | GM2ANL | CTRL_SYSTM_EN | Control System Engineer | 145 | 146 | 149 | 153 | 157 | 160 | 164
GM2ANL_CTRL_SYSTM_SR | GM2ANL | CTRL_SYSTM_SR | Control System Engineer Sr | 177 | 178 | 182 | 186 | 191 | 196 | 201
GM2ANL_ELEC_ASMBY_TECH | GM2ANL | ELEC_ASMBY_TECH | Electrical Assembly Technician | 75 | 76 | 78 | 80 | 82 | 84 | 86
GM2ANL_ELEC_DESIGN_EN | GM2ANL | ELEC_DESIGN_EN | Electrical Design Engineer | 138 | 139 | 141 | 145 | 149 | 152 | 156
GM2ANL_ELEC_DESIGN_SR | GM2ANL | ELEC_DESIGN_SR | Electrical Design Engineer Sr | 172 | 174 | 177 | 182 | 186 | 191 | 195
GM2ANL_ELEC_DESIGNER | GM2ANL | ELEC_DESIGNER | Electrical Designer | 106 | 107 | 109 | 112 | 114 | 117 | 120
GM2ANL_ELEC_DRAFTER | GM2ANL | ELEC_DRAFTER | Electrical Drafter | 74 | 75 | 76 | 78 | 80 | 82 | 84
GM2ANL_ELEC_TECH | GM2ANL | ELEC_TECH | Electrical Technician | 86 | 87 | 89 | 91 | 93 | 96 | 98
GM2ANL_ELEC_TECH_MNGR | GM2ANL | ELEC_TECH_MNGR | Electrical Technical Manager | 209 | 210 | 214 | 220 | 225 | 231 | 237
GM2ANL_ELTN_DESIGN_EN | GM2ANL | ELTN_DESIGN_EN | Electronics Design Engineer | 141 | 142 | 145 | 149 | 152 | 156 | 160
GM2ANL_ELTN_DESIGN_SR | GM2ANL | ELTN_DESIGN_SR | Electronics Design Engineer Sr | 182 | 183 | 187 | 192 | 196 | 201 | 206
GM2ANL_ELTN_TECH | GM2ANL | ELTN_TECH | Electronics Technician | 94 | 94 | 96 | 99 | 101 | 104 | 106
GM2ANL_ENGNRING_PHYST | GM2ANL | ENGNRING_PHYST | Engineering Physicist | 150 | 152 | 155 | 159 | 162 | 167 | 171
GM2ANL_HIGH_VAC_TECH | GM2ANL | HIGH_VAC_TECH | High Vac Technician | 83 | 84 | 86 | 88 | 90 | 92 | 95
GM2ANL_INSTRUMENT_TECH | GM2ANL | INSTRUMENT_TECH | Mechanical Instrument Technician | 92 | 92 | 94 | 97 | 99 | 102 | 104
GM2ANL_MAGNT_DESIGN_EN | GM2ANL | MAGNT_DESIGN_EN | Magnet Design Engineer | 159 | 161 | 164 | 168 | 172 | 177 | 181
GM2ANL_MAGNT_DESIGN_SR | GM2ANL | MAGNT_DESIGN_SR | Magnet Design Engineer Sr | 175 | 177 | 180 | 185 | 190 | 194 | 199
GM2ANL_MECH_ANLYSIS_EN | GM2ANL | MECH_ANLYSIS_EN | Mechanical Analysis Engineer | 134 | 135 | 138 | 141 | 145 | 148 | 152
GM2ANL_MECH_ANLYSIS_SR | GM2ANL | MECH_ANLYSIS_SR | Mechanical Analysis Engineer Sr | 169 | 170 | 173 | 178 | 182 | 187 | 191
GM2ANL_MECH_ASMBY_TECH | GM2ANL | MECH_ASMBY_TECH | Mechanical Assembly Technician | 86 | 87 | 88 | 91 | 93 | 95 | 98
GM2ANL_MECH_DESIGN_EN | GM2ANL | MECH_DESIGN_EN | Mechanical Design Engineer | 139 | 140 | 143 | 147 | 151 | 154 | 158
GM2ANL_MECH_DESIGN_SR | GM2ANL | MECH_DESIGN_SR | Mechanical Design Engineer Sr | 176 | 178 | 181 | 186 | 191 | 195 | 200
GM2ANL_MECH_DESIGNER | GM2ANL | MECH_DESIGNER | Mechanical Designer | 102 | 103 | 105 | 108 | 110 | 113 | 116
GM2ANL_MECH_DRAFTER | GM2ANL | MECH_DRAFTER | Mechanical Drafter | 60 | 61 | 62 | 64 | 65 | 67 | 69
GM2ANL_MECH_TECH_MNGR | GM2ANL | MECH_TECH_MNGR | Mechanical Technical Manager | 182 | 183 | 187 | 192 | 196 | 201 | 206
GM2ANL_MECH_TECH_SPVSR | GM2ANL | MECH_TECH_SPVSR | Mechanical Technician Supervisor | 122 | 123 | 125 | 128 | 132 | 135 | 138
GM2ANL_PRCESS_CTRL_EN | GM2ANL | PRCESS_CTRL_EN | Process/Controls Engineer | 109 | 110 | 112 | 115 | 118 | 121 | 124
GM2ANL_PRCESS_CTRL_SR | GM2ANL | PRCESS_CTRL_SR | Process/Controls Engineer Sr | 149 | 150 | 153 | 157 | 160 | 165 | 169
GM2ANL_PT_EXP_PHYST | GM2ANL | PT_EXP_PHYST | Particle Physicist Experimental | 137 | 138 | 141 | 144 | 148 | 152 | 156
GM2ANL_PT_EXP_RA | GM2ANL | PT_EXP_RA | Particle Physics Experimental Research Associate | 91 | 92 | 93 | 96 | 98 | 101 | 103
GM2ANL_U_PT_EXP_PHYST | GM2ANL | U_PT_EXP_PHYST | Particle Physicist Experimental Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
GM2ANL_U_PT_EXP_RA | GM2ANL | U_PT_EXP_RA | Particle Physics Experimental Research Associate Unco | 0 | 0 | 0 | 0 | 0 | 0 | 0
GM2ANL_U_PT_THY_PHYST | GM2ANL | U_PT_THY_PHYST | Particle Physicist Theory Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
GM2ANL_U_PT_THY_RA | GM2ANL | U_PT_THY_RA | Particle Physics Theory Research Associate Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
GM2BNL_APDEV_SYSTMAYST | GM2BNL | APDEV_SYSTMAYST | Applications Development & Systems Analyst | 137 | 138 | 141 | 145 | 148 | 152 | 156
GM2BNL_CP_PHYCS_DEVLPR | GM2BNL | CP_PHYCS_DEVLPR | Computational Physics Developer | 125 | 126 | 129 | 132 | 135 | 138 | 142
GM2BNL_CT_SRVCS_SPCLST | GM2BNL | CT_SRVCS_SPCLST | Computing Services Specialist | 149 | 150 | 153 | 157 | 161 | 165 | 169
GM2BNL_CTRL_SYSTM_EN | GM2BNL | CTRL_SYSTM_EN | Control System Engineer | 145 | 146 | 149 | 153 | 157 | 160 | 164
GM2BNL_CTRL_SYSTM_SR | GM2BNL | CTRL_SYSTM_SR | Control System Engineer Sr | 177 | 178 | 182 | 186 | 191 | 196 | 201
GM2BNL_ELEC_ASMBY_TECH | GM2BNL | ELEC_ASMBY_TECH | Electrical Assembly Technician | 75 | 76 | 78 | 80 | 82 | 84 | 86
GM2BNL_ELEC_DESIGN_EN | GM2BNL | ELEC_DESIGN_EN | Electrical Design Engineer | 138 | 139 | 141 | 145 | 149 | 152 | 156
GM2BNL_ELEC_DESIGN_SR | GM2BNL | ELEC_DESIGN_SR | Electrical Design Engineer Sr | 172 | 174 | 177 | 182 | 186 | 191 | 195
GM2BNL_ELEC_DESIGNER | GM2BNL | ELEC_DESIGNER | Electrical Designer | 106 | 107 | 109 | 112 | 114 | 117 | 120
GM2BNL_ELEC_DRAFTER | GM2BNL | ELEC_DRAFTER | Electrical Drafter | 74 | 75 | 76 | 78 | 80 | 82 | 84
GM2BNL_ELEC_TECH | GM2BNL | ELEC_TECH | Electrical Technician | 86 | 87 | 89 | 91 | 93 | 96 | 98
GM2BNL_ELEC_TECH_MNGR | GM2BNL | ELEC_TECH_MNGR | Electrical Technical Manager | 209 | 210 | 214 | 220 | 225 | 231 | 237
GM2BNL_ELTN_DESIGN_EN | GM2BNL | ELTN_DESIGN_EN | Electronics Design Engineer | 141 | 142 | 145 | 149 | 152 | 156 | 160
GM2BNL_ELTN_DESIGN_SR | GM2BNL | ELTN_DESIGN_SR | Electronics Design Engineer Sr | 182 | 183 | 187 | 192 | 196 | 201 | 206
GM2BNL_ELTN_TECH | GM2BNL | ELTN_TECH | Electronics Technician | 94 | 94 | 96 | 99 | 101 | 104 | 106
GM2BNL_ENGNRING_PHYST | GM2BNL | ENGNRING_PHYST | Engineering Physicist | 150 | 152 | 155 | 159 | 162 | 167 | 171
GM2BNL_HIGH_VAC_TECH | GM2BNL | HIGH_VAC_TECH | High Vac Technician | 83 | 84 | 86 | 88 | 90 | 92 | 95
GM2BNL_INSTRUMENT_TECH | GM2BNL | INSTRUMENT_TECH | Mechanical Instrument Technician | 92 | 92 | 94 | 97 | 99 | 102 | 104
GM2BNL_MAGNT_DESIGN_EN | GM2BNL | MAGNT_DESIGN_EN | Magnet Design Engineer | 159 | 161 | 164 | 168 | 172 | 177 | 181
GM2BNL_MAGNT_DESIGN_SR | GM2BNL | MAGNT_DESIGN_SR | Magnet Design Engineer Sr | 175 | 177 | 180 | 185 | 190 | 194 | 199
GM2BNL_MECH_ANLYSIS_EN | GM2BNL | MECH_ANLYSIS_EN | Mechanical Analysis Engineer | 134 | 135 | 138 | 141 | 145 | 148 | 152
GM2BNL_MECH_ANLYSIS_SR | GM2BNL | MECH_ANLYSIS_SR | Mechanical Analysis Engineer Sr | 169 | 170 | 173 | 178 | 182 | 187 | 191
GM2BNL_MECH_ASMBY_TECH | GM2BNL | MECH_ASMBY_TECH | Mechanical Assembly Technician | 86 | 87 | 88 | 91 | 93 | 95 | 98
GM2BNL_MECH_DESIGN_EN | GM2BNL | MECH_DESIGN_EN | Mechanical Design Engineer | 139 | 140 | 143 | 147 | 151 | 154 | 158
GM2BNL_MECH_DESIGN_SR | GM2BNL | MECH_DESIGN_SR | Mechanical Design Engineer Sr | 176 | 178 | 181 | 186 | 191 | 195 | 200
GM2BNL_MECH_DESIGNER | GM2BNL | MECH_DESIGNER | Mechanical Designer | 102 | 103 | 105 | 108 | 110 | 113 | 116
GM2BNL_MECH_DRAFTER | GM2BNL | MECH_DRAFTER | Mechanical Drafter | 60 | 61 | 62 | 64 | 65 | 67 | 69
GM2BNL_MECH_TECH_MNGR | GM2BNL | MECH_TECH_MNGR | Mechanical Technical Manager | 182 | 183 | 187 | 192 | 196 | 201 | 206
GM2BNL_MECH_TECH_SPVSR | GM2BNL | MECH_TECH_SPVSR | Mechanical Technician Supervisor | 122 | 123 | 125 | 128 | 132 | 135 | 138
GM2BNL_PRCESS_CTRL_EN | GM2BNL | PRCESS_CTRL_EN | Process/Controls Engineer | 109 | 110 | 112 | 115 | 118 | 121 | 124
GM2BNL_PRCESS_CTRL_SR | GM2BNL | PRCESS_CTRL_SR | Process/Controls Engineer Sr | 149 | 150 | 153 | 157 | 160 | 165 | 169
GM2BNL_PT_EXP_PHYST | GM2BNL | PT_EXP_PHYST | Particle Physicist Experimental | 137 | 138 | 141 | 144 | 148 | 152 | 156
GM2BNL_PT_EXP_RA | GM2BNL | PT_EXP_RA | Particle Physics Experimental Research Associate | 91 | 92 | 93 | 96 | 98 | 101 | 103
GM2BNL_U_PT_EXP_PHYST | GM2BNL | U_PT_EXP_PHYST | Particle Physicist Experimental Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
GM2BNL_U_PT_EXP_RA | GM2BNL | U_PT_EXP_RA | Particle Physics Experimental Research Associate Unco | 0 | 0 | 0 | 0 | 0 | 0 | 0
GM2BNL_U_PT_THY_PHYST | GM2BNL | U_PT_THY_PHYST | Particle Physicist Theory Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
GM2BNL_U_PT_THY_RA | GM2BNL | U_PT_THY_RA | Particle Physics Theory Research Associate Uncosted | 0 | 0 | 0 | 0 | 0 | 0 | 0
GM2UNI_P_ELEC_DESIGNER | GM2UNI | P_ELEC_DESIGNER | Electrical Designer - Generic Univ | 88 | 89 | 90 | 93 | 95 | 97 | 100
GM2UNI_P_ELEC_EN | GM2UNI | P_ELEC_EN | Electrical Engineer - Generic Univ | 123 | 124 | 126 | 130 | 133 | 136 | 140
GM2UNI_P_ELEC_TECH | GM2UNI | P_ELEC_TECH | Electrical Technician - Generic Univ | 43 | 43 | 44 | 45 | 46 | 47 | 49
GM2UNI_P_MECH_DESIGNER | GM2UNI | P_MECH_DESIGNER | Mechanical Designer - Generic Univ | 60 | 60 | 62 | 63 | 65 | 66 | 68
GM2UNI_P_MECH_EN | GM2UNI | P_MECH_EN | Mechanical Engineer - Generic Univ | 123 | 124 | 126 | 130 | 133 | 136 | 140
GM2UNI_P_MECH_TECH | GM2UNI | P_MECH_TECH | Mechanical Technician - Generic Univ | 43 | 43 | 44 | 45 | 46 | 47 | 49
GM2UNI_P_PC_PROF | GM2UNI | P_PC_PROF | Computer Professional - Generic Univ | 123 | 124 | 126 | 130 | 133 | 136 | 140
GM2UNI_P_POSTDOC | GM2UNI | P_POSTDOC | Post Doc - Generic Univ | 65 | 65 | 67 | 68 | 70 | 72 | 73
GM2UNI_P_SCIENTIST | GM2UNI | P_SCIENTIST | Scientist - Generic Univ | 74 | 75 | 76 | 78 | 80 | 82 | 84
GM2UNI_U_ELEC_DESIGNER | GM2UNI | U_ELEC_DESIGNER | Electrical Designer Uncosted - Generic Univ | 0 | 0 | 0 | 0 | 0 | 0 | 0
GM2UNI_U_ELEC_EN | GM2UNI | U_ELEC_EN | Electrical Engineer Uncosted - Generic Univ | 0 | 0 | 0 | 0 | 0 | 0 | 0
GM2UNI_U_ELEC_TECH | GM2UNI | U_ELEC_TECH | Electrical Technician Uncosted - Generic Univ | 0 | 0 | 0 | 0 | 0 | 0 | 0
GM2UNI_U_GRAD_STUDENT | GM2UNI | U_GRAD_STUDENT | Grad Student Uncosted - Generic Univ | 0 | 0 | 0 | 0 | 0 | 0 | 0
GM2UNI_U_MECH_DESIGNER | GM2UNI | U_MECH_DESIGNER | Mechanical Designer Uncosted - Generic Univ | 0 | 0 | 0 | 0 | 0 | 0 | 0
GM2UNI_U_MECH_EN | GM2UNI | U_MECH_EN | Mechanical Engineer Uncosted - Generic Univ | 0 | 0 | 0 | 0 | 0 | 0 | 0
GM2UNI_U_MECH_TECH | GM2UNI | U_MECH_TECH | Mechanical Technician Uncosted - Generic Univ | 0 | 0 | 0 | 0 | 0 | 0 | 0
GM2UNI_U_PC_PROF | GM2UNI | U_PC_PROF | Computer Professional Uncosted - Generic Univ | 0 | 0 | 0 | 0 | 0 | 0 | 0
GM2UNI_U_POSTDOC | GM2UNI | U_POSTDOC | Post Doc Uncosted - Generic Univ | 0 | 0 | 0 | 0 | 0 | 0 | 0
GM2UNI_U_SCIENTIST | GM2UNI | U_SCIENTIST | Scientist Uncosted - Generic Univ | 0 | 0 | 0 | 0 | 0 | 0 | 0
GM2UNI_U_UGRAD_STUDENT | GM2UNI | U_UGRAD_STUDENT | Undergrad Student Uncosted - Generic Univ | 0 | 0 | 0 | 0 | 0 | 0 | 0
TM_BOILER | TM | BOILER | Boiler Maker | 119 | 119 | 119 | 122 | 122 | 125 | 125
TM_CARPENTER | TM | CARPENTER | Carpenter | 105 | 105 | 105 | 108 | 108 | 111 | 111
TM_CEMENT | TM | CEMENT | Cement Mason | 105 | 105 | 105 | 108 | 108 | 111 | 111
TM_DRIVER | TM | DRIVER | Driver And Truck | 114 | 114 | 114 | 117 | 117 | 120 | 120
TM_DRIVER_SEMI | TM | DRIVER_SEMI | Driver And Semi Truck | 132 | 132 | 132 | 135 | 135 | 139 | 139
TM_ELEC | TM | ELEC | Electrician | 119 | 119 | 119 | 122 | 122 | 125 | 125
TM_INSULATOR | TM | INSULATOR | Insulator | 122 | 122 | 122 | 124 | 124 | 128 | 128
TM_IRON | TM | IRON | Iron Worker | 153 | 153 | 153 | 156 | 156 | 161 | 161
TM_LABORER | TM | LABORER | Laborer - General | 119 | 119 | 119 | 122 | 122 | 125 | 125
TM_MILL | TM | MILL | Millwright | 102 | 102 | 102 | 105 | 105 | 107 | 107
TM_OPER_CNST | TM | OPER_CNST | Equipment Operator | 129 | 129 | 129 | 132 | 132 | 135 | 135
TM_PAINT | TM | PAINT | Painter | 102 | 102 | 102 | 105 | 105 | 107 | 107
TM_PLUMB | TM | PLUMB | Plumber | 114 | 114 | 114 | 117 | 117 | 120 | 120
TM_RIGGER | TM | RIGGER | Rigger | 119 | 119 | 119 | 122 | 122 | 125 | 125
TM_ROOF | TM | ROOF | Roofer | 102 | 102 | 102 | 105 | 105 | 107 | 107
TM_SHEET | TM | SHEET | Sheet Metal Worker | 108 | 108 | 108 | 111 | 111 | 114 | 114
TM_SPRINKLER | TM | SPRINKLER | Sprinkler Fitter | 138 | 138 | 138 | 142 | 142 | 145 | 145
TM_WELDER | TM | WELDER | Welder | 138 | 138 | 138 | 142 | 142 | 145 | 145
X_01 | X | 01 | Boston Electronics Design Engineer | 0 | 0 | 0 | 0 | 0 | 0 | 0
X_02 | X | 02 | To be specified | 0 | 0 | 0 | 0 | 0 | 0 | 0
X_03 | X | 03 | To be specified | 0 | 0 | 0 | 0 | 0 | 0 | 0
X_04 | X | 04 | To be specified | 0 | 0 | 0 | 0 | 0 | 0 | 0
X_05 | X | 05 | To be specified | 0 | 0 | 0 | 0 | 0 | 0 | 0
X_06 | X | 06 | To be specified | 0 | 0 | 0 | 0 | 0 | 0 | 0
X_07 | X | 07 | To be specified | 0 | 0 | 0 | 0 | 0 | 0 | 0
X_08 | X | 08 | To be specified | 0 | 0 | 0 | 0 | 0 | 0 | 0
X_09 | X | 09 | To be specified | 0 | 0 | 0 | 0 | 0 | 0 | 0
X_10 | X | 10 | To be specified | 0 | 0 | 0 | 0 | 0 | 0 | 0
X_11 | X | 11 | To be specified | 0 | 0 | 0 | 0 | 0 | 0 | 0
X_12 | X | 12 | To be specified | 0 | 0 | 0 | 0 | 0 | 0 | 0
X_13 | X | 13 | To be specified | 0 | 0 | 0 | 0 | 0 | 0 | 0
X_14 | X | 14 | To be specified | 0 | 0 | 0 | 0 | 0 | 0 | 0
X_15 | X | 15 | To be specified | 0 | 0 | 0 | 0 | 0 | 0 | 0
X_16 | X | 16 | To be specified | 0 | 0 | 0 | 0 | 0 | 0 | 0
X_17 | X | 17 | To be specified | 0 | 0 | 0 | 0 | 0 | 0 | 0
X_18 | X | 18 | To be specified | 0 | 0 | 0 | 0 | 0 | 0 | 0
X_19 | X | 19 | To be specified | 0 | 0 | 0 | 0 | 0 | 0 | 0
X_20 | X | 20 | To be specified | 0 | 0 | 0 | 0 | 0 | 0 | 0
X_21 | X | 21 | To be specified | 0 | 0 | 0 | 0 | 0 | 0 | 0
X_22 | X | 22 | To be specified | 0 | 0 | 0 | 0 | 0 | 0 | 0
X_23 | X | 23 | To be specified | 0 | 0 | 0 | 0 | 0 | 0 | 0
X_24 | X | 24 | To be specified | 0 | 0 | 0 | 0 | 0 | 0 | 0
X_25 | X | 25 | To be specified | 0 | 0 | 0 | 0 | 0 | 0 | 0
X_26 | X | 26 | To be specified | 0 | 0 | 0 | 0 | 0 | 0 | 0
X_27 | X | 27 | To be specified | 0 | 0 | 0 | 0 | 0 | 0 | 0
X_28 | X | 28 | To be specified | 0 | 0 | 0 | 0 | 0 | 0 | 0
X_29 | X | 29 | To be specified | 0 | 0 | 0 | 0 | 0 | 0 | 0
X_30 | X | 30 | To be specified | 0 | 0 | 0 | 0 | 0 | 0 | 0

## ResourceM&S
Resource IDs (M&S) |  |  |  |  | Unique Task Names | Rows | Start Row | End Row | Cell Range | Alternate Funding
M&S Task Code | Prefix | Suffix | Description | Overheads | [5 empty] | NSF
FN_MS_EXMP | FN | MS_EXMP | M&S Exempt | 1 | FN | 5 | 3 | 7 | ResourceM&S!$C$3:$C$7 | Early Career
FN_MS_INKIND | FN | MS_INKIND | M&S Inkind | 0 | [5 empty] | University
FN_MS_PASS | FN | MS_PASS | M&S Pass-Thru | 1.015 | [5 empty] | Intl In-Kind
FN_MS_STND | FN | MS_STND | M&S Standard | 1.23 | [5 empty] | Other (add note)
FN_MS_TRVL | FN | MS_TRVL | M&S Travel | 1.17

## Formula
Formula Names
ActivityNumPrelim= | PreliminaryDesign!$A$8:$A$27
ActivityNumFinal= | FinalDesign!$A$8:$A$27
ActivityNumImplementation= | Implemenation!$A$8:$A$27
ContingencyLists = | Definitions!$A$2:$A$9
ResourceLaborName = | Definitions!$A$72:$A$1073
ResourceLaborPrefix = | Definitions!$B$72:$B$1073
ResourceLaborPrefixUnique = | Definitions!$H$72:$H$92
ResourceLaborSuffix= | Definitions!$C$72:$C$1073
ResourceLaborSuffixPulldown= | OFFSET(ResourceLaborSuffixHeader,MATCH($D32,ResourceLaborPrefix,0),0,COUNTIF(ResourceLaborPrefix,$D32),1)
ResourceMSName = | Definitions!$A$13:$A$67
ResourceMSPrefix = | Definitions!$B$13:$B$67
ResourceMSPrefixUnique= | Definitions!$H$13:$H$17
ResourceMSSuffix = | Definitions!$C$13:$C$67
ResourceMSSuffixPulldown= | OFFSET(ResourceMSSuffixHeader,MATCH($D68,ResourceMSPrefix,0),0,COUNTIF(ResourceMSPrefix,$D68),1)
RiskCategory= | Definitions!$F$2:$F$6
RiskType= | Definitions!$D$2:$D$4
SourceDocumentNum= | CoverSheet!$A$14:$A$23
ResourceIDLaborTable= | Definitions!$A$72:$E$1073
ResourceLaborSuffixHeader= | Definitions$C$71
ResourceMSSuffixHeader= | Definitions!$C$12
ContingencyTable= | Definitions!$A$2:$B$9

## ChangeLog
This BoE template was originall created by Brian Drendel in October 2012. Questions can be directed to drendel@fnal.gov.
2012-10-10 | Brian Drendel | Created Excel BoE template
2012-10-17 | Brian Drendel | Fixed Excel 2007 compatibility issue by referencing pull down menus using NAMES
2012-11-01 | Brian Drendel | Fixed equations being broke when Base Estimate or Estimate Type fields were cut and pasted by using the INDIRECT function in new columns and hiding those columns
2012-11-01 | Brian Drendel | Added more Labor and M&S Rows, increased size of sources cells, unprotected the last two columns in the opportunities/risks workbook.
2012-11-02 | Brian Drendel | Added Resource ID lookup table to allow labor $ calculations. Lookup table has $125/hr for all Resource IDs to start with.
2012-11-02 | Brian Drendel | Added totals table which totals labor and M&S costs across all phases of the project.
2012-11-12 | Brian Drendel | Activities tables changed to include activity name and description, estimate type from pull-down menu, doc source from pull-down menu, sucessor and predessor from pull-down menu
2012-11-12 | Brian Drendel | Costing tables changes to select activity num from pull down menu, auto populate activity name, auto populate estimate type, split Resource ID selection into prefix and suffix.
2012-11-13 | Brian Drendel | Added item column to M&S, required shuffling column position. In activity table, removed successors.
2012-11-14 | Brian Drendel | Fixed bugs with M&S equations. Tested on Excel 2010, 2007 and Mac.
2012-11-15 | Brian Drendel | New ResourceID tables, new Resource ID format, new RiskOpporunity table updates, new RiskMatrix tables, added alternate funding, added M&S overhead multiplier
2012-11-21 | Brian Drendel | New ResourceID labor items for non-Fermilab sources.
2012-11-26 | Brian Drendel | Made error handling more robust
2013-01-06 | Chris Polly | Added change log, changed several description fields to add clarification, added some alternate funding sources, allowed for uncosted technical effort from university grants
2013-01-18 | Chris Polly | Change M&S OH factor for travel to 1.17, fixed a couple of incorrect column references in the M&S table (now total down column correctly), clarified FY13/14/15 dollar headings