## Slide 1: WBS 476.02.03.04.01 – 30 Straight Section Reconfiguration
g-2 Accelerator – 30 Straight Section Reconfiguration
D. Still
Fermilab
Muon g-2 IDR, June 5-7

## Slide 2: WBS Structure
476.02.03.04.01 D30 Straight Section Reconfiguration
Scope: To provide a preliminary and final plan and schedule to implement and coordinate the necessary work to reconfigure the 30 straight section tunnel and service building in order to accept the newly built M3 and M4 beam lines into the Delivery Rings.
Deliverables: A reconfigured 30 straight section tunnel and service building.

## Slide 3: Risks
There are 2 main risks:
This is an intersecting area of many beam lines across multiple projects and AIP’s that interdepend on each other. There are risks for conflicts in planning in the preliminary and final design phases. Additionally, there are risks to schedule and manpower during the implementation phase.
  Mitigation:
  Mitigation of the this risk is good detailed planning in the preliminary and final design phase and good coordination and scheduling during the implementation phase.
2) The design for the Mu2e in tunnel shielding can have great bearing on the plan for reconfiguring the 30 straight section. Demands for shielding can change plans for reconfigurations.
  Mitigation:
  Mitigation of the this risk is track and understand the Mu2e shielding design and plan accordingly for the 30 straight section reconfiguration

## Slide 4: Muon Campus Overview
This the area that will be involved in the reconfiguration.
It is defined as the 30 straight section. (AP30 Service Building)

## Slide 5: Current 30 Tunnel Section Layout
Obsoleted Accumulator
Current Debuncher - Future Delivery Ring
Obsoleted AP3 Line
Remove the AP3 Line.
Store magnets in the tunnel
reuse.
Overview of what needs to be reconfigured

## Slide 6: Remove the AP3 Line
Note: Most AP3 Line components will be reused in the M2,M3,M4 and M5 beam lines.
Elements will need to be stored in the tunnel and categorized.
Remove the Accumulator components
in the 30 straight section.

## Slide 7: Prepare Room for M3 and M4 Installation
Remove and store all DR components
from D3Q11 to D3Q2.
Note: Most Accumulator magnet components will be reused in the M2, M3, M4 and M5 beam lines and stored in the tunnel until installed.
Collider equipment 10 stochastic cooling tanks will be removed from the tunnel.

## Slide 8: Remove the DR M3 Side
Remove and store all DR components
from D2Q4 to D2Q11.
Note: Collider equipment
8 stochastic cooling tanks and DRF3 will be removed from tunnel.

## Slide 9: Remove DR on M4 Side
Install the DR Injection devices and the M3 Beam Line

## Slide 10: Install the M4 Beam Line
Install the DR extraction devices and the M4 Beam Line

## Slide 11: Install M4 Beam Line + DR Extraction Components
Reinstall the DR from D3Q11 to D3Q3
And D2Q4 to D2Q11

## Slide 12: Completed Reconfiguration of 30 Straight Section
New M3 Beam Line
New M4
Beam Line
New Injection Devices
New Extraction Devices
Delivery Ring

## Slide 13: 30 Straight Section Reconfigured
Delivery Ring
M3 Beam Line
M4 Beam Line

## Slide 14: 30 Straight Section Tunnel
All ceiling components
Move or removed
AP3 Line and Accumulator
Removed
Accumulator
M4 Side of
Delivery Ring
AP3 Line
Cable tray moves
M4 Line Installed

## Slide 15: The Reality of Reconfiguring
There are many interferences, obstacles and infrastructure that need to move to prepare for the installation of the M3 and M4 beam lines.
Most or all of these components will need to move:
  cable tray & cables
  cable penetrations (reassigned not moved)
  tunnel lighting
  DR buss work
  LCW headers
  Collider Equipment
Debuncher
AP3 Line
AP3 Line
Debuncher
M3 Line

## Slide 16: Mu2e must transfer magnets to M4

## Slide 17: M4 Tunnel GPP
M4 Diagnostic Absorber get installed
During tunnel GPP but need steel ready before hand
Coordinate Tunnel
Opening

## Slide 18: Cable Trays and Cables
(C. Crowley - Mu2e In-Tunnel Shielding Concept to mitigate skyshine – May 2013 )
The design and relocation of the cable trays is the one of the most challenging items.
All the cable tray must be relocated for 2 reasons:
    M3 and M4 beam lines interfere with current location.
    Mu2e is designing in-tunnel shielding to mitigate skyshine.
All the cables in the tray must be evaluated as to whether to be extended, removed and pull new or removed completely.
Cable penetrations cannot be occluded by shielding.

## Slide 19: Mu2e In Tunnel shielding

## Slide 20: Current Cable Tray Design
Current Cable tray Configuration
Conceptual Design of Cable Tray
All 3 accumulator cable trays will need to be cleaned out to make room for cables servicing M3 and M4 line devices. Additional accumulator side trays may be needed.
Delivery Ring cable trays will move to tunnel center 3 wide to allow for height of fork lift for tunnel shielding.

## Slide 21: M3 Side Cable Tray Reconfigure
Current Tray Configuration
Proposed Tray Reconfiguration

## Slide 22: Interfaces with Beamline AIPs
Recycler RF AIP
g-2
Delivery Ring AIP
Mu2e
Beam Transport AIP
M5
g-2 is responsible for the D30 Straight Section reconfiguration and extraction from the Delivery Ring (different devices used for g-2 and Mu2e)
The Delivery Ring AIP is responsible for Delivery Ring injection devices (common)
D10
D50
D30
(AIP=Accelerator Improvement Project)

## Slide 23: List of Mu2e and AIP Milestones that Coordinate Activities
Mu2e
  Ready to Install In tunnel shielding
  In tunnel Shielding complete
  Ready to remove magnets from Acc. to M4
  Magnet move from Acc. to M4 complete
  Ready to install Mu2e Extraction Device
  Mu2e Extraction device installation complete
AIP
  Ready to Install injection devices
  Injection Devices Installation Complete
GPP
  Ready to install M4 Diagnostic Absorber
  M4 Diag Absorber installation Complete

## Slide 24: Milestones – 476.2 Accelerator
Many important L4/L5 milestones currently fall in the final fiscal year
# | Description | Baseline Date | Float (mos)
1.3 | M4 and M5 Accelerator Lines Operational | 1st Qtr FY18 | 6
2.1 | M1 Line Final Focus complete | 3rd Qtr FY17 | 3
2.2 | M2 Power Supplies Operational | 2nd Qtr FY17 | 3
2.3 | M2 Line Fully Operational | 2nd Qtr FY17 | 3
2.4 | M3 Power Supplies Operational | 2nd Qtr FY17 | 3
2.5 | M3 Line Fully Operational | 2nd Qtr FY17 | 3
2.6 | D30 Straight Section Complete | 1st Qtr FY18 | 3
2.7 | Delivery Ring Power Supplies Operational | 1st Qtr FY18 | 3
2.8 | Delivery Ring Line Fully Operational | 1st Qtr FY18 | 3
2.9 | M4/M5 Lines Fully Operational | 4th Qtr FY17 | 3
2.10 | Ready to Begin Beam Tests of Delivering Muons to g-2 | 1st Qtr FY18 | 3
*L2 milestones held jointly by FPD and PPD Head, L4 PM, L5 Level II Managers
Level | FY13 | FY14 | FY15 | FY16 | FY17 | Tot
4 | 0 | 3 | 0 | 1 | 23 | 27
5 | 5 | 27 | 24 | 10 | 40 | 106
Frequency of L4/L5 Milestones by Fiscal Year

## Slide 25: Interfaces between Muon Campus Projects
Interface milestones are the basis for communicating schedule impacts between the AIP’s, GPP’s, g-2 and Mu2e
Each AIP has a Requirements document
  Signed by AIP manager, g-2 and Mu2e Project Managers, MC Program Coordinator, and lab management
Milestone Name | Responsibility | Impacts | Forecast
MC-1 Bldg Beneficial Occupancy for Cryo | MC-1 Building GPP | Cryo AIP | 1/8/14
MC-1 Bldg Beneficial Occupancy for g-2 Ring | MC-1 Building GPP | g-2 | 2/18/14
Beamline Enclosure Beneficial Occupancy | Beamline Enclosure GPP | g-2 | 6/9/15
Cryo Compressor Cooling Established | MC Infrastructure GPP | Cryo AIP | 9/30/14
MI-52 Bldg Extension Beneficial Occupancy | MC Infrastructure GPP | Beam Transport AIP | 9/30/15
Cryo Ready to Cool g-2 | Cryo AIP | g-2 | 1/2/15
Cryo Ready to Cool Mu2e | Cryo AIP | Mu2e | 10/1/17
Recycler RF Complete | Recycler RF AIP | beam to g-2, Mu2e | 9/30/16
Beam Transport Complete | Beam Transport AIP | beam to g-2, Mu2e | 1/4/16
End of Circulating Beam Studies | g-2, Mu2e | g-2, Mu2e, Delivery Ring AIP | 4/1/14
Delivery Ring Complete | Delivery Ring AIP | beam to g-2, Mu2e | 3/30/17
MC-1 Cryo Room Controls Available | g-2 | Cryo AIP | 9/22/14
D30 Straight Section Ready for New Installation | g-2 | Delivery Ring AIP | 2/3/16

## Slide 26: Muon g-2 Accelerator Schedule
CD-0
CD-4
Forecast
KPPs Satisfied
CD-1
CD-2/3a
CD-3
Conceptual Design
Final Design
Safety system
M4/M5 installation
D30 Straight Section reconfiguration
DR extraction
Target Station
Ctrls to MC-1
Instrumentation
M4/M5 magnet, power supply work
Prelim Design
Final Design Ctrls, D30 Straight
M2/M3 magnet, power supply work
Final focus
AP2/AP3 disassembly
M2/M3 installation
MC-1 cryo room controls available
Beamline enclosure BO
D30 straight ready for new installation
End of circulating beam studies
Beam Transport complete
Recycler RF complete
Delivery Ring complete

## Slide 27: Mu2e Schedule
Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
CD-1
CD-4
FY13 FY14 FY15 FY16 FY17 FY18 FY19 FY20
CD-3
CD-3a
CD-2/3b
Detector Hall Design
Superconductor R&D
Solenoid Infrastructure
Solenoid Installation
Install Detector
KPPs satisfied
Fabricate and QA Superconductor
Engineering Design of Solenoids
Solenoid Fabrication and QA
Site work/Detector Hall Construction
Accelerator and Beamline
Detector Construction
Common Projects
g-2 Commissioning/Running
Field Mapping

## Slide 28
CD-1
CD-4
FY13 FY14 FY15 FY16 FY17 FY18 FY19 FY20
CD-3
CD-3a
CD-2/3b
Detector Hall Design
Superconductor R&D
Solenoid Infrastructure
Solenoid Installation
Install Detector
KPPs satisfied
Fabricate and QA Superconductor
Engineering Design of Solenoids
Solenoid Fabrication and QA
Site work/Detector Hall Construction
Accelerator and Beamline
Detector Construction
Common Projects
g-2 Commissioning/Running
Field Mapping
Forecast
KPPs Satisfied
CD-1
CD-2/3a
CD-3
Conceptual Design
Final Design
Safety system
M4/M5 installation
D30 Straight Section reconfiguration
DR extraction
Target Station
Ctrls to MC-1
Instrumentation
M4/M5 magnet, power supply work
Prelim Design
Final Design Ctrls, D30 Straight
M2/M3 magnet, power supply work
Final focus
AP2/AP3 disassembly
M2/M3 installation
MC-1 cryo room controls available
Beamline enclosure BO
D30 straight ready for new installation
End of circulating beam studies
Beam Transport complete
Recycler RF complete
Delivery Ring complete
28

## Slide 29: List of g-2 Milestone
476.02.03.04.01 | 1 |  | 4 | L4 - Preliminary of Design of D30 Straight Section Reconfiguration Completed
D30 SS reconfig | 2 |  | 4 | L4 - Final Design of D30 Straight Section Reconfiguration Completed
 | 3 |  | 4 | L4 - D30 Straight Section Tunnel Reconfiguration Ready to Begin
 | 4 |  | 4 | L4 - D30 Straight Section Service building Reconfiguration Ready to Begin
 | 5 |  | 4 | L4 - Move DR M3 Side Component Complete
 | 6 |  | 4 | L4 - Move DR M4 Side Component Complete
 | 7 |  | 4 | L4 - Remove Accumulator Component Complete
 | 8 |  | 4 | L4 - Remove DR Cooling Tanks & DRF3 Complete
 | 9 |  | 4 | L4 - Remove AP3 Line Complete
 | 10 |  | 4 | L4 - Remove DR Cable Tray Complete
 | 11 |  | 4 | L4 - Ready to Transfer Magnets to M4/M5 lines
 | 12 |  | 4 | L4 - Transfer Magnets to M4/M5 Complete
 | 13 |  | 4 | L4 - Ready to install M3 Line components
 | 14 |  | 4 | L4 - Ready to install M4 Line components
 | 15 |  | 4 | L4 - Ready to install Injection components
 | 16 |  | 4 | L4 - Ready to install Extraction components
 | 17 |  | 4 | L4 - M3 Line Installation Complete
 | 18 |  | 4 | L4 - M4 Line Installation Complete
 | 19 |  | 4 | L4 - Install Injection components Complete
 | 20 |  | 4 | L4 - Install Extraction Components Complete
 | 21 |  | 4 | L4 - Reinstall DR M3 Side Component Complete
 | 22 |  | 4 | L4 - Reinstall DR M4 Side Component Complete
 | 23 |  | 4 | L4 - DR Cable Tray Installation Complete
 | 24 |  | 4 | L4 - Acc. Cable Tray Installation Complete
 | 25 |  | 4 | L4 - D30 Straight Section Reconfiguration Completed

## Slide 30: D30 SS Schedule

## Slide 31: D30 SS Schedule (2)

## Slide 32: D30 SS schedule (3)