## Slide 1: MICE CC TEST, IN PROGRESS
M. Tartaglia
For the FNAL/LBNL Test Team
9/27/13

## Slide 2: Test Timeline
1st TC in May 2013 – reached 9K; He-> vac leak
Summer 2013:
  re-design/make up He connections
  qualify stand cryogenics (zero magnet) - no leaks!
  shorted bus & power supply endurance test to 220 A
  lead thermal intercept improvements
  Better vacuum gauges, He valve control
  Increased cold surface area for cryo-pumping
2nd TC September 2013
  Cool down 9/09 to 9/13; Rate-of-T-rise Heat Load
  Calc: ~10 W Measurement: ~80 W

## Slide 3: Cool Down, Heat Load
2nd TC September 2013
  Cool down 9/09 to 9/13; Rate-of-T-rise Heat Load
  Calc: ~10 W Measurement: ~80 W

## Slide 4: Temperature Distribution
Surface Temperatures stable since cool down, Even after moving pumps (to get them out of the stray field)
(P ~10-6 now 2 10-5)
My Opinion:
  I believe the sensors !
Strain Gauges:
Nothing unusual

## Slide 5: Test Plan
9/13 All Coils superconducting
  100 mA trickle currrent
  Test Heaters induce quench
150 V to ground Hipot passed
  (<1 uA)
9/16 5A trip; PS checkout
  2  Resistor across leads
9/17 10A trip, 25A trip
  Test Diode Turn-On (50V)

## Slide 6: Test Plan
9/18 DAQ Changes (add DQD signals to QC)
9/19 PS Failed to Ramp
  Replace with T&I Lambda supply, checkout
9/23 Ramp to 46 A, Cartridge Heater-Induced Quench
  Test QD system
9/24 Prepare for “High Field” operation
  Vacuum pumps moved further away
  Interlocked area, Remote operation
  First Ramp to Quench
    Fast Voltage Spike at 62 A, Coils 1,2,3
    Contactors open at 10 ms – don’t know
    If a quench developed, we don’t know

## Slide 7: Test Plan
9/25 Some SC lead resistance and rising T near lead in
  We spend a day calculating
  Still awaiting LBNL thermal model of expected surface T’s
  Assuming our nominal and 5x heat loads
  Limit target current to 100 A (watch the leads!)
9/26 ramp to quench at 62 A (no spike) (2.1T on coil)
9/27 try again, quench at 62 A !
  Are we at the short sample limit? I think so!
  See TD-12-009: Barzi & Turrioni
  7.63 K is extrapolated critical T at 62 A.
  LATER TODAY: Raise T(He) by increasing P (~ 0.2 K)
  If quench current goes down, yes.