## Slide 1
201 MHz cavity
  Installation activities of the MICE prototype cavity at MTA using the single cavity vessel
    Tuner arms installed
    Cavity support assembly (inside the vessel) tested
  Two RF couplers fabrication continues at LBNL
    Parts made
    Outside vendor for TiN coating
  Lucas visited LBNL
    ANSYS simulations of the prototype cavity
  Cryostat fabrication
    Currently on hold due to budget situation
    Four more weeks of work to complete
  Lots progress on the 201-MHz cavity installation
    Tuners and tests
    Cavity support
    Water cooling line connections
    Cavity assembly procedures
Continue the 201 MHz installation at MTA, Fermilab
Complete two RF couplers fabrication at LBNL and deliver to MTA, Fermilab for installation
Resume the cryostat fabrication at LBNL once the funding is in place
Continue update/finalize the design of MICE CC cryostat and accessory components
Continue MP simulation studies of the MICE cavity and coupler with external magnetic fields
Complete fabrication of two 201 MHz RF couplers for the MICE prototype cavity
Support the MICE prototype cavity installation and testing at MTA, Fermilab
Complete cryostat vessel fabrication at LBNL
Continue updating cryostat drawings and cooling circuits
Delivery of the first MICE CC cryostat vessel
EP of the remaining 9 MICE cavities at LBNL
  To be completed in FY14
1st Cryostat fabrication on hold due to budget shortage
Measurements and tuning of all MICE RF cavities
October 25, 2013
05 01: MICE RF Fabrication & Testing
Derun Li

## Slide 2: MICE Construction
First MICE RF cavity installation in a single cavity vessel at Fermilab
Coupler loop fabrication