## Slide 1: OTE Building PMG Report November 11, 2013
Rhonda Merchut

## Slide 2: Agenda
OTE Project:
  Coordination
    Outfitting
    IGPP
    CDF
  Building Construction Status
  State Activities
  Schedule
  Fiscal
  Summary Action Items

## Slide 3: OTE Outfitting GPP G13-211
FY 13: $2M for VoIP/networking & Contingency.
  Continuing layout studies.
    Development of reoccurring module to maximize tenant flexibility & growth.
    Evaluating private office/intellectual property integration impact on building utility systems & LEED credits.
      Re-balancing of building mechanical system will be req’d.
      Relocation & add’l light fixtures & sprinklers will be req’d
      LEED daylighting & views credits are challenging
    Working with vendors to develop details & pricing for Office of IARC concept

## Slide 4: Tenant Module
6-8 private offices, various sizes
4 cubes
2 four-person offices

## Slide 5: OTE Outfitting GPP G13-211
  Evaluating Johnson Controls proposal for building security.
    Planning for future key card needs
  Networking/VoIP planning underway.
    Moving ahead with permanent connection for Metasys to monitor building systems.
    Network & VoIP throughout after substantial completion of OTE Building Construction.

## Slide 6: IASU Update (IGPP)
OTE Construction Project Phase 2 scope approximately 85% complete.
  Add’l scope added for Road B & Road D paving & gas shed removal.
  All work must be fully costed Dec-13

## Slide 7: CDF Coordination
Temporary power disconnect will require shut-down of one CDF panel. (Tentative 11/20/13)

## Slide 8: OTE Project Status:
Construction Coordination
  Pre-punchlist documentation & coordination
  Safety oversight continues
RFI’s continue.
Schedule Oversight on-going.
  Contractor has targeted 11/20/13 Substantial Completion.
  Contractual Substantial Completion 12/09/13.
Financial Oversight on-going.
  Change orders continue
  Retention reduced to 5% ($900K remains)

## Slide 9: OTE Project Status:
LEED
Contractor reporting 97% construction waste has been diverted from landfill.
On track to meet goal of 20% (by cost) of regionally manufactured materials (~37%).
On track to meet goal of 20% (by cost) of recycled content in materials used (~50%).
Commissioning activities well underway. Functional Testing started 11/6/13.
LEED Gold still remains viable.

## Slide 11
West Lobby

## Slide 12: Interior Finish Work

## Slide 13
Lecture Hall

## Slide 14
Interior Finish Work

## Slide 16: State DCEO Activities
DCEO quarterly report to State for quarter ending 11/30/13 to be submitted by 12/31/13.
  Anticipate reporting 99% costed to date.
Project on schedule for grants to be 100% costed by 5/31/14 grant requirement.

## Slide 17: Contractual Schedule Adjustments
Schedule Adjustments per SA 27:
MS 1 Bldg Shell Complete: 6/19/13
MS 2 Substantial Completion: 12/9/13
  (Project is fully costed at MS 2, retention remains)
MS 3, Project Complete: 3/4/14
Anticipated Schedule Adjustment per SA 29:
MS 2 Substantial Completion: 12/27/13
MS 3, Project Complete: 3/21/14

## Slide 18: Oct 2013 BMC Schedule

## Slide 19: Oct 2013 BMC Schedule

## Slide 20: Oct 2013 BMC Schedule
Anticipated change to March 21, 2014
Anticipated change to Dec 27, 2013

## Slide 21
20-30 workers daily
Major categories of work complete subject to final detailing:
Exterior
  East Side grading, paving,
  Native planting beds
  Base flashing, detailing
Interior
  1st floor final finishes
  Mech start-up & testing (underway)
  Fire Rated Glazing at 1st floor stairs
  Millwork & wood panels & doors (underway)
  Hand/guardrail detailing
  Miscellaneous detailing throughout
OTE Construction Status:

## Slide 22: Project Plan Tracking Milestones
Project is fully costed at MS 2, retention remains

## Slide 23
BMC Construction BCWS & ACWP
Based on 9/20/13 Update:
97% Complete based on cost
91% Complete based on time

## Slide 24
BMC Monthly Costing
Monthly Average to date: $1,184,363
Required Monthly Average to complete: $270,000 (MS2: 11/5/2013)

## Slide 25
601 TSR Budget Balance
ALL Grant Costing w/ BMC Projection

## Slide 26: Financial

## Slide 27: Financial – Estimated at Completion 601 + G13221 Funding

## Slide 28: Financial – Available Contingency 601 + G13221 Funding
c

## Slide 29: Supplemental Agreements by Funding
28 SA’s for 200+ EC’s (change orders) = $19.3M Total Construction Contract

## Slide 30: Contingency Management
Sources available to fund change orders:
  IGPP;
  DOE backstop (GPP Outfitting project);

## Slide 31: Summary Action Items
Building Construction:
  shop drawing & change order review, RFI responses
  construction coordination & oversight.
    Safety & SWPPP
    Punch List
    Commissioning
  LEED Documentation – receive BMC final doc’s, upload to USGBC
  schedule oversight
  financial oversight
  Landline phones
Programing & Space Layouts
  Finalize typical office layouts
  Identify Scope Contingency Items
  Finalize Office of IARC
    Details
    Utility Impact
    Design document development
    Costs
VoIP, networking
  Space Layouts needed
Security
  Finalize requirements
  Procure
IGPP
  Finalize