## Slide 1: Muon Campus Program RR to P1 Transfer Line Cons Gattuso 8/28/13

## Slide 2: RR to P1 Transfer Line
2014 shutdown will only deal with the Recycler
portion of the beam line

## Slide 3: RR to P1 line update
Stand Modification
  Lambertson stands
    Drawings are complete
    Assembly/installation drawing underway
  Kicker stands
    Drawing are underway
Vacuum Rework
  General layout sketches complete
    Drafting switching over form IDEALS to VX
  Issues not resolved
    Pump placement, Beam box, Beam Pipe supports
Cable pulls
  Preliminary list generated
Interferences mitigation
  looking for MI access time to identify issues
Lattice updates
  Correction elements added
  Beam line instrumentation updated

## Slide 4: Mile Stones
Task codes open 10/1/2013
Vacuum design should be finalized by 11/4/13
  Pumps/Gauges/valves order should be placed by 12/2/13
    EE support should receive the vacuum layout/configure at this time to layout the CIA crate
Stand Designs
  Lambertson/Kickers/Differential pumping should be done by 12/9/13
  Stand parts should be ordered by 12/16/13
Shut down Readiness (Last Week of May)
  ALL stand components in hand and staged at MI-60
    Installation drawings/procedures ready and signed off
  ALL Vacuum Components ready for installation
  ALL Cabling in hand and ready for installation
Shutdown Begins ( 4th Qtr.. of 2014 FY, July/Aug/Sept)
2/15/14
2/7/14
9/1/14
2/12/14
2/9/14

## Slide 5: Schedule for the Fall 2014 shutdown
Start of the shut down September 1 2014 (tentative)
Driven by Com Ed
  Main 345KV line maintenance
Duration
  6-8 Weeks Driven by the RR to P1 line Recycler modification
Other shutdown Work
  MI/RR
    Replace 3 sets of Lambertson flanges
    Install 3rd RF cavity
    Install 2 IPMS
    Remove 201 electron cloud experiment
    Open up aperture in the RR to MI extraction line
  Techs will be a premium
    May not get much done during this time period in Muon rings

## Slide 6
First Access Monday/Tuesday access period
Mech Support Tunnel
  Prepping Storage areas
    Converting over the E760 pit
  General house keeping
  Procedures requested from Mechanical support
    Beam pipe processing
    Water system
    Stand inspections
    Magnet inspections
Alignment
  Network
    Ceiling monuments installed (~100 monuments installed)
    Floor monuments(~45 of the 110 installed)
    Wall monuments
  Delivery Ring Referencing and As-founds

## Slide 7: Weeks to Come……..
Tunnel clean up
  Prepping Storage areas
    Lots of misc cables/ pipe and other hardware in the tunnel
      Some in short straight section
      Some in storage bins/fenced in areas
Alignment
  Network
    Ceiling monuments installed
    Floor monuments
    Wall monuments
  Delivery Ring Referencing and As-founds
Tunnel component tagging
  What stays
  What goes
    Storage
    New location
    Waste

## Slide 8: Documenting Our access period work
We will be tagging our entries using the ”Subject” (studies title page).
Looking for suggest as to how to title them…