## Summary
FULL FUNCTION DELIVERABLE - HIGH BANDWIDTH INTRA-BUNCH INSTABILITY FEEDBACK SYSTEMS Full function deliverable available for test after LS2 - FY2104 - FY2016 Revision #1.5 J. Cesaratto, J. Fox, C. Rivetta , based on 1 full function deliverable and "supplied" SLAC labor rates Revision Date: 07/02/2013
Brief Scope Description and Assumptions.
|  |  |  | LS1 | LS1 |  |  |  | LS2 |  |  |  | LS3
| FTE | FY12 BASE | FY12 BASE w/ Overhead | FY13 | FY14 | FY15 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21 | FY22 | Total w/o Contingency | Contingency % | Total incl. Contingency
M&S Escalation |  |  |  | 2.7% | 5.47% | 8.32% | 11.24% | 14.24% | 17.32% | 20.49% | 23.74% | 27.08% | 30.51%
Labor Escalation |  |  |  | 0.8% | 2.82% | 5.39% | 8.02% | 10.72% | 13.49% | 16.33% | 19.24% | 22.16% | 25.27%
DEVELOPMENT/EXPANSION of DEMONSTRATION PROCESSING SYSTEM
M&S |  | 247500 | 378675 | LS1 FY13: 20540; LS1 FY14: 306601.29; LS1 FY15: 145013.4 | 472154.69 |  | 626534.6809
Synchronization function for energy ramp |  | 25000 | 38250 | LS1 FY13: 0; LS1 FY14: 40342.275; LS1 FY15: 41432.4 | 81774.675 | 32.5% | 108351.4444
Reciever channel development, prototype |  | 25000 | 38250 | LS1 FY13: 0; LS1 FY14: 40342.275; LS1 FY15: 41432.4 | 81774.675 | 32.5% | 108351.4444
High bandwidth kicker power amplifiers,splitters/combiners |  | 75000 | 114750 | LS1 FY13: 0; LS1 FY14: 60513.4125; LS1 FY15: 62148.6 | 122662.0125 | 32.5% | 162527.1666
Test laboratory equipment (e.g., high power loads, FPGA software, signal processing D/A eval.) |  | 22500 | 34425 | LS1 FY13: 0; LS1 FY14: 36308.0475; LS1 FY15: 0 | 36308.0475 | 33% | 48289.7032
Wideband slotline kicker prototype |  | 100000 | 153000 | LS1 FY13: 20540; LS1 FY14: 129095.28; LS1 FY15: 0 | 149635.28 | 33% | 199014.9224
LABOR |  | 658000 | 1250200 | LS1 FY13: 1260201.6; LS1 FY14: 1285455.64 | 2545657.24 |  | 2545657.24
Staff Scientist, 1.7 FTE | 1.7 | 268600 | 510340 | LS1 FY13: 514422.72; LS1 FY14: 524731.588 | 1039154.308 | 0% | 1039154.308
Staff Engineer, 0.7 FTE | 0.7 | 102900 | 195510 | LS1 FY13: 197074.08; LS1 FY14: 201023.382 | 398097.462 | 0% | 398097.462
Toohig Fellow (potential 1 FTE) | 0 | 0 | 0 | LS1 FY13: 0; LS1 FY14: 0 | 0 | 0% | 0
Graduate Student, 2 FTE (50% LARP) | 2 | 50000 | 95000 | LS1 FY13: 95760; LS1 FY14: 97679 | 193439 | 0% | 193439
Staff Scientist, 0.3 FTE | 0.3 | 47400 | 90060 | LS1 FY13: 90780.48; LS1 FY14: 92599.692 | 183380.172 | 0% | 183380.172
Staff Engineer, 0.3 FTE | 0.3 | 44100 | 83790 | LS1 FY13: 84460.32; LS1 FY14: 86152.878 | 170613.198 | 0% | 170613.198
SLAC Fellow/Postdoc (potential 1 FTE) | 0 | 0 | 0 | LS1 FY13: 0; LS1 FY14: 0 | 0 | 0% | 0
Graduate Student, 2 FTE (50% SLAC) | 2 | 50000 | 95000 | LS1 FY13: 95760; LS1 FY14: 97679 | 193439 | 0% | 193439
Fellow/Postdoc/Staff, 1 FTE | 1 | 95000 | 180500 | LS1 FY13: 181944; LS1 FY14: 185590.1 | 367534.1 | 0% | 367534.1
DESIGN STUDIES OF FULL-FUNCTION PROTOTYPE, SIMULATIONS, MDs with 1 bunch Demo
M&S |  | 175000 | 267750 | LS1 FY13: 0; LS1 FY14: 0; LS1 FY15: 165729.6; LS1 FY16: 127647.9 | 293377.5 |  | 388725.1875
High power amplifiers for SPS MD evaluation |  | 75000 | 114750 | LS1 FY15: 124297.2; LS1 FY16: 0 | 124297.2 | 32.5% | 164693.79
RF components, control equipment for kicker and power amplifiers |  | 25000 | 38250 | LS1 FY15: 41432.4; LS1 FY16: 0 | 41432.4 | 32.5% | 54897.93
High capacity processing channel development, 2nd FPGA platform for development |  | 75000 | 114750 | LS1 FY15: 0; LS1 FY16: 127647.9 | 127647.9 | 32.5% | 169133.4675
LABOR |  | 781750 | 1485325 | LS1 FY13: 0; LS1 FY14: 0; LS1 FY15: 1565384.0175; LS1 FY16: 1604448.065 | 3169832.0825 |  | 3803798.499
Staff Scientist, 2 FTE | 2 | 316000 | 600400 | LS1 FY15: 632761.56; LS1 FY16: 648552.08 | 1281313.64 | 20% | 1537576.368
Staff Engineer, 1 FTE | 1 | 147000 | 279300 | LS1 FY15: 294354.27; LS1 FY16: 301699.86 | 596054.13 | 20% | 715264.956
Toohig Fellow (potential 1 FTE) | 0 | 0 | 0 | LS1 FY15: 0; LS1 FY16: 0 | 0 | 20% | 0
Graduate Student, 2 FTE (50% LARP) | 2 | 50000 | 95000 | LS1 FY15: 100120.5; LS1 FY16: 102619 | 202739.5 | 20% | 243287.4
Staff Scientist, 0.25 FTE | 0.25 | 39500 | 75050 | LS1 FY15: 79095.195; LS1 FY16: 81069.01 | 160164.205 | 20% | 192197.046
Staff Engineer, 0.25 FTE | 0.25 | 36750 | 69825 | LS1 FY15: 73588.5675; LS1 FY16: 75424.965 | 149013.5325 | 20% | 178816.239
SLAC Fellow/Postdoc (potential 1 FTE) | 0 | 0 | 0 | LS1 FY15: 0; LS1 FY16: 0 | 0 | 20% | 0
Graduate Student, 2 FTE (50% SLAC) | 2 | 50000 | 95000 | LS1 FY15: 100120.5; LS1 FY16: 102619 | 202739.5 | 20% | 243287.4
Fellow/Postdoc/Staff, 1.5 FTE | 1.5 | 142500 | 270750 | LS1 FY15: 285343.425; LS1 FY16: 292464.15 | 577807.575 | 20% | 693369.09
TRAVEL |  | 42500 | 65025 | LS1 FY13: 65545.2; LS1 FY14: 66858.705; LS1 FY15: 102794.7713; LS1 FY16: 105360.0075 | 340558.6838 |  | 340558.6838
Subtotal LARP |  | 1177000 | 2146575 | LS1 FY13: 872802; LS1 FY14: 1031490.6375; LS1 FY15: 1275044.5012; LS1 FY16: 1285878.8475 | 4465215.9863 |  | 4853214.534
Subtotal SLAC -GARD |  | 290250 | 543150 | LS1 FY13: 271000.8; LS1 FY14: 312739.6175; LS1 FY15: 252804.2625; LS1 FY16: 259112.975 | 1095657.655 |  | 1161733.055
Subtotal LARP/CERN (potential cost share) |  | 100000 | 153000 | LS1 FY13: 0; LS1 FY14: 0; LS1 FY15: 165729.6; LS1 FY16: 0 | 165729.6 |  | 382118.8866
Subtotal CERN |  | 337500 | 604250 | LS1 FY13: 202484; LS1 FY14: 314685.38; LS1 FY15: 285343.425; LS1 FY16: 292464.15 | 1094976.955 |  | 1259918.1124
Total LARP+SLAC (green + blue) |  |  |  | LS1 FY13: 1143802.8; LS1 FY14: 1344230.255; LS1 FY15: 1527848.7637; LS1 FY16: 1544991.8225 | 5560873.6412 |  | 6014947.589
Total LARP+SLAC+CERN (green + blue + orange + green dot) |  |  |  | LS1 FY13: 1346286.8; LS1 FY14: 1658915.635; LS1 FY15: 1978921.7888; LS1 FY16: 1837455.9725 | 6821580.1963 |  | 7656984.588
LABOR RATES: |  |  | NOTES:
Staff Scientist | 158000 |  | Contingency catagories listed in proposal document, % here are averaged over assigned line tasks
Staff Engineer | 147000 |  | Travel costs burdoned with G&A labor rate, and escalated with labor by year
Postdoc | 95000 |  | CERN costs estimated using typical US Lab costs.
Graduate Student (50% LARP, 50% SLAC ARD support) | 50000 |  | CERN Fellow/Postdoc/Staff (E.g., K. Li) works on mix of simulation and hardware development
Graduate students fully costed. (Both SLAC and LARP support)
M&S overhead rate 7.65% per Cole Carter | 7.65%
G&A labor rate of 53% | 53% |  | Color code:
Benefits rate 37% | 37% |  |  | LS1 FY13: LARP Contribution
CERN Contribution
SLAC - GARD Contribution
Potential LARP/CERN split cost
Note on B12: John Cesaratto: expand to 16-32 bunch control MAX! Not full ring.
Note on B34: John Cesaratto: Second system should have capacity to handle full loaded SPS (4-6x 72 bunches)