## Slide 1: QXF Plans and Preparation for Project
G. Ambrosio
2/17/14

## Slide 2: Outline
Overview
Short models plan
Long models plan
Schedule and budget
Preparation for Project

## Slide 3: LARP-CERN Integrated Plan
LARP and CERN are working closely together for developing and demonstrating the MQXF design:
Requirements from Hi-Lumi LHC WP3
  With strong LARP participation
Shared work for the design (single design)
  Working groups with representatives from 4 labs
Shared effort for the 1st short model (SQXF1)
Work in parallel for subsequent short models (SQXF)
LARP/CERN full-length (4m/6m) prototypes (LQXF)

## Slide 4: Plan Overview
Short model program: 2014-2016
  Fabrication of practice coils is starting this month
    According to schedule presented at CM20 (4/13)
  First SQXF coil test (Mirror structure) in Dec. 2014
  First magnet test (SQXF1) in May 2015
  2 (LARP) + 3 (CERN) short models + reassembly (~4)
Long model program: 2015-2017
  Coil winding starts in 2015: Jan. (LARP), Sept. (CERN)
  First LQXF coil test (Mirror structure) in Dec. 2015
  First model test in Oct. 2016 (LARP) and July 2017 (CERN)
  3 (LARP) + 2 (CERN) models in total
Series production: 2018-2022

## Slide 5: SQXF plan and schedule: Coil fabrication
CERN
  Number of coils
    First set
      2 practice coils
      1 mirror coil
      5 RRP coils
    Second set
      6 PIT coils
      5 RRP coils
  Fabrication steps
    Winding + curing + reaction + impregnation
  Fabrication time
    ~100 days (5 months) per coil
    1 coil produced
      every 2 months in the 1st year
      every 1.5 months in the 2st year
      every 1 months in the 3st year
LARP
  Number of coils
    First set
      2 practice coils
      1 mirror coil
      5 RRP coils
    Second set
      5 RRP coils
  Fabrication steps
    First set
      FNAL: winding + curing
      BNL, FNAL, LBNL : reaction + impregnation
    Second set
      FNAL: winding + curing
      LBNL: reaction + impregnation
  Fabrication time
    ~100 days (5 months) per coil
    1 coil produced every month
      Budget limited

## Slide 6: SQXF plan and schedule: Tests
From assembly to test and disassembly: ~5 months; Test by LARP or CERN
1st generation coils
  First LARP coil test in 12/2014 (mirror structure)
  First CERN coil test in 04/2015 (SQXF structure with practice coils or LARP mirror structure)
  First magnet test (SQXF1) in 05/2015
      Assembled ad tested by LARP with 3 LARP coils and 1 CERN coil
  Then SQXF1b (prestress optimization)
  First magnet test by CERN (SQXF2), then SQXF2b (test of LHe containment)
2nd generation coils
  LARP RRP: SQXF3 (04/2016) and SQXF3b (11/2016)
  CERN PIT: SQXF4 (2016-2017)
  CERN RRP: SQXF5 (2017)
Test of 2-magnets in 1-cold-mass: SQXF5+SQXF3b (2017)

## Slide 7: SQXF Schedule
| 2014 | 2015 | 2016 | 2017
Practice coils
Coil for mirror test
SQXF1
SQXF3
SQXF2 2b 4 3b+5

## Slide 8: Long model program Plan and schedule
CERN
Number of coils
  3 practice
  1 coil for mirror test
  11 coils (5 RRP + 6 PIT)
  Coil winding starts 09/2015
Models/tests
  2 models, 3 tests
  Horiz. “simplified” tests
  Mirror test in 11/2016
  First model test in 07/2017
  Last test 10/2018
LARP
Number of coils
  2 practice (1 FNAL & 1 BNL)
  1 coil for mirror test
  15 RRP coils
  Coil winding starts 01/2015
Models/tests
  3 models, 3 tests + mirror
  2 structures
  Vertical tests (BNL)
  Mirror test in 12/2015
  First model test in 10/2016
  Last test 04/2018

## Slide 9: LQXF Schedule
| 2015 | 2016 | 2017 | 2018
Coil for mirror test
LQXF1
LQXF2
LQXF3
Practice coils
Project
NOT in plan
SQXF1 test
SQXF mirror test
SQXF1b test
SQXF3 test
“In preparing for battle, I have always found that plans are useless but planning is indispensable.”
DWIGHT D. EISENHOWER
LARP only

## Slide 10: Planning - I
Nb3Sn magnets have never been used in any particle accelerator yet!
Short models (SQXF):
  2new + 2re (LARP)
    Minimum for quench performance and prestress range
  2new + 2re (LARP, RRP) + 2new + 1re (CERN, RRP)
    OK for understanding He-shell impact and 2-in-1 He-vessel
    Minimum for field quality
  1mirror (LARP)
    Very minimum (HQ had 3)
    Provides test bed in case of issues
Minimal program.
Having LARP & CERN in parallel provides risk mitigation

## Slide 11: Planning - II
Long models (LQXF):
  3new (LARP)
    Almost minimum for demonstration of reproducibility
  0re (LARP)
    This is a risk, LQS01b was very useful for LQ development
  1mirror (LARP)
    Minimum: if we have limited performance in LQXF1 the mirror test will help understanding cause btw coil/structure
    Provides test bed in case of issues
CERN will start after LARP and will develop 6.8m long magnets.
 We count only on LARP for this.

## Slide 12: QXF Schedule
From strand procurement to test analysis
Durations based on input from task leaders and L3s
Schedule is budget limited (scenario #1)
Resource loading is in progress
  Started with this FY in order to compare RLS estimate with LARP-style estimate
  Already providing useful feedback

## Slide 13: LARP MS Budget Request
M&S drivers:
  Conductor (S/LQXF coils): $2.5 M
    Assuming $1.2 M CDP contribution
  QXF coil tooling: ~$1.5 M
  LQXF structures (2): $0.8 M
  BNL vert. test facility upgr.: $0.7 M
Unit: M$ | FY14 | FY15 | FY16 | FY17 | FY18
Labor | 6.1 | 5.8 | 5.7 | 6.9 | 0.2
M&S | 1.4 | 2.8 | 2.8 | 1.3 | 0.1
TOTAL | 7.5* | 8.6 | 8.5 | 8.2 | 0.3
*Assuming $0.3M from APUL contingency
Need some trimming to fit into Scenarios #1,2
In order to fit into Scenario #3 we have to remove the LQXF mirror ($1.5M):
Strand, Cable, Coil fabrication, Structure procurement, Assembly, Test.
 high risk in case of limited performance of LQXF1

## Slide 14: Preparation for Project
Each lab is focusing and starting/strengthening its contributions to the Construction Project
  Starting wind&cure line for LQXF coils at BNL
  Strengthening QC and QA in all areas
  Setting up a test facility for L/MQXF magnets
  Building documentation and process
    Conductor specs
    Functional test requirements
    SQXF1 design report

## Slide 15: Monitoring Expenses
For all major tasks we plan to monitor expenses vs. estimates on a monthly base
  Both Labor and M&S
  Work performed vs. work scheduled is already monitored separately
  Previously done for some LQ tasks
  First step toward EVMS

## Slide 16: Conclusions
In HiLumi, for the 1st time ever, Nb3Sn magnets are a critical component of a particle accelerator
  There is an intrinsic risk … unknown unknowns
LARP in collaboration with CERN has developed a plan adequate to this challenge
We can make it successful with the best resources at all labs and sufficient support from the funding agency.