## Magnet StandSupport
|  |  | FY14 |  |  |  | FY15 |  |  |  | FY16 |  |  |  | FY17 |  |  | FY18
|  |  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Recycler RF AIP | bar: FY14 Q2 to FY16 Q4
Build cavities | bar: FY15 Q1 to FY16 Q3
Install RF | bar: FY16 Q4
| Design cavities | May | FY14 Q2: 0.2; FY14 Q3: 0.2; FY14 Q4: 0.2; FY14 Q1: 0.2; FY15 Q2: 0.2; FY15 Q3: 0.2; FY15 Q4: 0.2; FY15 Q1: 0.2
| Analysis on cooling design | May | FY14 Q2: 0.2; FY14 Q3: 0.2; FY14 Q4: 0.2
| Test cavity | Slabaugh | FY15 Q1: 0.2; FY16 Q2: 0.2; FY16 Q3: 0.2
| Design & write eng not for stands | Slabaugh | FY15 Q4: 0.15; FY15 Q1: 0.15; FY16 Q2: 0.15; FY16 Q3: 0.15
| Write procedures for installation & HA | Slabaugh | FY16 Q3: 0.2
| Installation oversight | Slabaugh | FY16 Q4: 0.3
Beam Transport AIP | bar: FY14 Q2 to FY15 Q1
Install extraction magnets | bar: FY14 Q4
Install RR to P1 line | bar: FY15 Q4
Install P1, P2, M1 aperture improvements | bar: FY15 Q4
| Design Lam stand & write note | Reilly | FY14 Q2: 0.15; FY14 Q3: 0.15
| Design RKB magnet stands & write note | Reilly | FY14 Q2: 0.15; FY14 Q3: 0.15
| V714 B2 magnet stand, vacuum and layout | Reilly | FY14 Q3: 0.05; FY14 Q4: 0.05; FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05
| Tevatron F0 Lambertson removal and vacuum pipe | Reilly | FY14 Q3: 0.05; FY14 Q4: 0.05; FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05
| F0 quadrupole stand | Reilly | FY14 Q3: 0.05; FY14 Q4: 0.05; FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05
| F17 C-Magnet removal and CDA stands | Reilly | FY14 Q3: 0.05; FY14 Q4: 0.05; FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05
| HV100 2 MDC for 4 EPB’s: stand | Reilly | FY14 Q3: 0.05; FY14 Q4: 0.05; FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05
| HV102 2 MDC for 4 EPB’s: stand | Reilly | FY14 Q3: 0.05; FY14 Q4: 0.05; FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05
| AP-1 trim relocation (2) stand | Reilly | FY14 Q3: 0.05; FY14 Q4: 0.05; FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05
| Write procedures for installation & HA | Reilly | FY14 Q3: 0.15; FY15 Q3: 0.2
| Installation oversight | Reilly | FY14 Q4: 0.6; FY15 Q4: 0.6
Delivery Ring AIP | bar: FY14 Q2 to FY16 Q4
Collider equipment removal | bar: FY14 Q2 to FY15 Q3
Tunnel installation | bar: FY15 Q3 to FY16 Q4
| Sort/inventory beam pipe & vacuum components | Le Beau | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Identify magnet lifting equipment, write Lifting Fixture Eng Notes | Reilly | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Write procedure to inspect & categorize stands | Reilly | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Oversight of removal of stands | Reilly | 0.03 | 0.03 | 0.03 | 0.03 | 0.03 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Oversight of installation of components | Reilly | FY15 Q3: 0.7; FY15 Q4: 0.7; FY15 Q1: 0.7; FY16 Q2: 0.7; FY16 Q3: 0.7; FY16 Q4: 0.7
g-2 | bar: FY14 Q2 to FY16 Q1
| Preliminary design |  | FY14 Q3: CD2
| Final design Delivery Ring |  | FY14 Q3: CD3a
Prep for beam studies
| Final design |  | FY14 Q1: CD3
Install M2/M3 beamline | bar: FY15 Q4; FY16 Q4
D30 Straight Section reconfig | bar: FY14 Q4 to FY16 Q1
Install pre-vault final focus quads | bar: FY15 Q1
Install Delivery Ring extraction | bar: FY16 Q2
Install M4/M5 beamline to g-2 | bar: FY16 Q3 to FY16 Q1
Build and install new target station dump | bar: FY15 Q1 to FY16 Q3
| M2 and M3 supports/stands | Despande | FY14 Q2: 0.4; FY14 Q3: 0.4; FY14 Q4: 0.4; FY14 Q1: 0.4; FY15 Q2: 0.4; FY15 Q3: 0.4
| M5 supports/stands | Reilly | FY14 Q2: 0.4; FY14 Q3: 0.4; FY14 Q4: 0.4; FY14 Q1: 0.4; FY15 Q2: 0.4; FY15 Q3: 0.4
| Extraction Kicker stand (reuse D:EKIK stand) | Ader | FY14 Q2: 0.2; FY14 Q3: 0.2; FY14 Q4: 0.2; FY14 Q1: 0.2; FY15 Q2: 0.2; FY15 Q3: 0.2
| Lambertson stand (motorized, two plane, US and DS motion) | new person | FY14 Q2: 0.1; FY14 Q3: 0.1; FY14 Q4: 0.1; FY14 Q1: 0.1; FY15 Q2: 0.1; FY15 Q3: 0.1
| 8Q32 stand (stationary) | Reilly | FY14 Q2: 0.1; FY14 Q3: 0.1; FY14 Q4: 0.1; FY14 Q1: 0.1; FY15 Q2: 0.1; FY15 Q3: 0.1
| C-Magnet stand (stationary) | Reilly | FY14 Q2: 0.1; FY14 Q3: 0.1; FY14 Q4: 0.1; FY14 Q1: 0.1; FY15 Q2: 0.1; FY15 Q3: 0.1
| V907 motorized stand | new person | FY14 Q2: 0.1
| Write procedures for installation & HA | Reilly | FY14 Q3: 0.15; FY15 Q3: 0.15; FY16 Q3: 0.15
| Oversee installation | Reilly | FY14 Q4: 0.3; FY14 Q1: 0.3; FY15 Q2: 0.3; FY15 Q3: 0.3; FY15 Q4: 0.8; FY16 Q4: 0.8
Mu2e
| Preliminary design |  | FY14 Q3: CD2/3
| Final design Beamline, Res Extr |  | FY14 Q4: CD3
| Final design Target Station |  | FY14 Q1: CD3
Install M4 beamline | bar: FY15 Q3 to FY18 Q1
Install DR RF and resonant extraction | bar: FY17 Q3
| Install target station | [18 empty] | ® | bar: FY18 Q1 to FY18 Q2
| TDR and BOE’s | Reilly/Ader | FY14 Q2: 0.2
| M4 Magnet Support Designs | Reilly | FY14 Q2: 0.2; FY14 Q3: 0.2; FY14 Q4: 0.2; FY14 Q1: 0.2; FY15 Q2: 0.3
| Write procedures for installation & HA |  | FY15 Q2: 0.3
| Oversee installation | [6 empty] | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9
Total |  |  | 2.62 | 2.97 | 3.27 | 2.47 | 2.87 | 4.5 | 3.75 | 2.55 | 2.35 | 2.7 | 3.1 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9

## Vacuum Eng
C. Ader
2014-01-27
|  |  | FY14 |  |  |  | FY15 |  |  |  | FY16 |  |  |  | FY17 |  |  | FY18
|  |  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Recycler RF AIP | bar: FY14 Q2 to FY16 Q4
Build cavities | bar: FY15 Q1 to FY16 Q3
Install RF | bar: FY16 Q4
| Review cavities for vacuum impact and analysis | Chen | FY14 Q2: 0.05; FY14 Q3: 0.05; FY14 Q4: 0.05; FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05; FY15 Q4: 0.05; FY15 Q1: 0.05; FY16 Q2: 0.05; FY16 Q3: 0.05
| Installation vacuum oversight | Slabaugh | FY16 Q4: 0.15
Beam Transport AIP | bar: FY14 Q2 to FY15 Q1
Install extraction magnets | bar: FY14 Q4
Install RR to P1 line | bar: FY15 Q4
Install P1, P2, M1 aperture improvements | bar: FY15 Q4
| Review Lam impact on vacuum/analysis | Chen | FY14 Q2: 0.05; FY14 Q3: 0.05
| Review RKB magnet impact on vacuum/analysis | Chen | FY14 Q2: 0.05; FY14 Q3: 0.05
| RR52 vacuum analysis and layout for differential pumping | Chen | FY14 Q2: 0.3; FY14 Q3: 0.1; FY14 Q4: 0.1
| V714 B2 vacuum and layout | Chen | FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05
| Tevatron F0 Lambertson vacuum pipe | Chen | FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05
| F0 quadrupole vacuum | Chen | FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05
| F17 C-Magnet and CDA vacuum | Chen | FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05
| HV100 2 MDC for 4 EPB’s: vacuum | Chen | FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05
| HV102 2 MDC for 4 EPB’s: vacuum | Chen | FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05
| AP-1 trim relocation (2) vacuum | Chen | FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05
| Write procedures for installation | Chen | FY14 Q3: 0.15; FY15 Q3: 0.2
| Installation vacuum oversight | Chen | FY14 Q4: 0.6; FY15 Q4: 0.6
Delivery Ring AIP | bar: FY14 Q2 to FY16 Q4
Collider equipment removal | bar: FY15 Q3
Tunnel installation | bar: FY15 Q3 to FY16 Q4
| Sort/inventory beam pipe & vacuum components | Le Beau | 0.033 | 0.033 | 0.033 | 0.033 | 0.033 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Write procedure to inspect & categorize vacuum hardware | Le Beau | 0.033 | 0.033 | 0.033 | 0.033 | 0.033 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Oversight of removal of vacuum components | Le Beau | 0.033 | 0.033 | 0.033 | 0.033 | 0.033 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1 | 0.1
| Oversight of installation of vacuum components | Le Beau | FY15 Q3: 0.7; FY15 Q4: 0.7; FY15 Q1: 0.7; FY16 Q2: 0.7; FY16 Q3: 0.7; FY16 Q4: 0.7
g-2 | bar: FY14 Q2 to FY16 Q1
| Preliminary design |  | FY14 Q3: CD2
| Final design Delivery Ring |  | FY14 Q3: CD3a
Prep for beam studies
| Final design |  | FY14 Q1: CD3
Install M2/M3 beamline | bar: FY15 Q4; FY16 Q4
D30 Straight Section reconfig | bar: FY14 Q4 to FY16 Q1
Install pre-vault final focus quads | bar: FY15 Q1
Install Delivery Ring extraction | bar: FY16 Q2
Install M4/M5 beamline to g-2 | bar: FY16 Q3 to FY16 Q1
Build and install new target station dump | bar: FY15 Q1 to FY16 Q3
| M2 and M3 vacuum design/analysis | Le Beau | FY14 Q2: 0.2; FY14 Q3: 0.2; FY14 Q4: 0.2; FY14 Q1: 0.2; FY15 Q2: 0.2; FY15 Q3: 0.2
| M5 vacuum design/analysis | Le Beau | FY14 Q2: 0.2; FY14 Q3: 0.2; FY14 Q4: 0.2; FY14 Q1: 0.2; FY15 Q2: 0.2; FY15 Q3: 0.2
| Extraction Kicker analysis | Le Beau | FY14 Q2: 0.05; FY14 Q3: 0.05; FY14 Q4: 0.05; FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05
| Lambertson stand vacuum | Le Beau | FY14 Q2: 0.15; FY14 Q3: 0.05; FY14 Q4: 0.05; FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05
| 8Q32 stand vacuum | Le Beau | FY14 Q2: 0.1; FY14 Q3: 0.1; FY14 Q4: 0.05; FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05
| C-Magnet vacuum | Le Beau | FY14 Q2: 0.1; FY14 Q3: 0.1; FY14 Q4: 0.05; FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05
| Write procedures for installation & design note | Le Beau | FY14 Q3: 0.15; FY15 Q3: 0.15; FY16 Q3: 0.15
| Oversee installation | Le Beau | FY14 Q4: 0.3; FY15 Q4: 0.8; FY16 Q4: 0.8
Mu2e
| Preliminary design |  | FY14 Q3: CD2/3
| Final design Beamline, Res Extr |  | FY14 Q4: CD3
| Final design Target Station |  | FY14 Q1: CD3
Install M4 beamline | bar: FY15 Q3 to FY18 Q1
Install DR RF and resonant extraction | bar: FY17 Q3
| Install target station | [18 empty] | ® | bar: FY18 Q1 to FY18 Q2
| TDR and BOE’s | Le Beau | FY14 Q2: 0.2
| M4 vacuum design/analysis | Le Beau | FY14 Q2: 0.3; FY14 Q3: 0.3; FY14 Q4: 0.3; FY14 Q1: 0.3; FY15 Q2: 0.3
| Write procedures for installation & design note | Le Beau | FY15 Q2: 0.3
| Oversee installation | Le Beau | [5 empty] | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4
Total |  |  | 1.849 | 1.649 | 2.049 | 1.399 | 1.699 | 2.75 | 2.85 | 1.45 | 1.45 | 1.6 | 2.35 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4 | 0.4

## Fluids Eng
|  |  | FY14 |  |  |  | FY15 |  |  |  | FY16 |  |  |  | FY17 |  |  | FY18
|  |  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Recycler RF AIP | bar: FY14 Q2 to FY16 Q4
Build cavities | bar: FY15 Q1 to FY16 Q3
Install RF | bar: FY16 Q4
Preliminary Design
| Design Cooling skid concept |  | FY14 Q3: 0.1
| Drawing layout coordination with overall project design. Assist Drafter. | Hixson | FY14 Q3: 0.2
Final Design
| Drafting detail piping installation drawings and piping scope layout, materials list | Hixson | FY14 Q4: 0.15
| Skid Design/Procure | Hixson | FY14 Q4: 0.35
| Author Engineering specification. | Hixson | FY14 Q4: 0.1
| Specify cooling skid | Hixson | FY14 Q1: 0.05
| Procure materials for skid/procure skid assembly | Hixson | FY15 Q2: 0.05
| Procure piping materials/hardware for piping to RF cavities | Hixson | FY15 Q2: 0.05
Installation/Assembly
| Assemble skid | Hixson | FY15 Q3: 0.1
| Install cooling Skid and piping network to RF Cavities | Hixson | FY15 Q4: 0.1; FY15 Q1: 0.1; FY16 Q2: 0.1; FY16 Q3: 0.1
| Installation Oversight | Hixson | FY15 Q4: 0.05; FY15 Q1: 0.05; FY16 Q2: 0.05; FY16 Q3: 0.05; FY16 Q4: 0.05
Beam Transport AIP | bar: FY14 Q2 to FY15 Q1
Install extraction magnets | bar: FY14 Q4
Install RR to P1 line | bar: FY15 Q4
Install P1, P2, M1 aperture improvements | bar: FY15 Q4
Preliminary Design - MI and P150 LCW systems
| Inspect the current RR/MI-52 area piping layout and design tunnel decommissioning strategy | Hixson | FY14 Q2: 0.1; FY14 Q3: 0.05; FY14 Q4: 0.05; FY14 Q1: 0.05; FY15 Q2: 0.05
| Inspect the current P150 layout and design tunnel decommissioning strategy | Hixson | FY14 Q2: 0.1; FY14 Q3: 0.05; FY14 Q4: 0.05; FY14 Q1: 0.05; FY15 Q2: 0.05
| Drawing layout coordination with overall project design | Hixson | FY14 Q2: 0.1; FY14 Q3: 0.1; FY14 Q4: 0.2; FY14 Q1: 0.2; FY15 Q2: 0.2
Final Design - MI and P150 LCW systems
| Drafting detail piping installation drawings and piping scope layout, materials list | Hixson | FY15 Q2: 0.2; FY15 Q3: 0.2
| Author/revise existing engineering specification | Hixson | FY15 Q2: 0.1; FY15 Q3: 0.1
| Decommission activities | Hixson | FY15 Q2: 0.1; FY15 Q3: 0.1
| Begin M&S Procurement | Hixson | FY15 Q2: 0.1; FY15 Q3: 0.1
Installation - MI and P150 LCW systems
| Install piping modification in MI/P150 | Hixson | FY15 Q4: 0.15
| Installation Engineering Oversight | Hixson | FY15 Q4: 0.05
| Fill Test and Commission | Hixson | FY15 Q4: 0.01
Delivery Ring AIP | bar: FY14 Q2 to FY16 Q4
Collider equipment removal | bar: FY14 Q2 to FY15 Q3
Tunnel installation | bar: FY15 Q3 to FY16 Q4
| Inspect the current layout and design tunnel decommissioning strategy |  | FY14 Q2: 0.05; FY14 Q3: 0.05; FY14 Q4: 0.05
| Compressed area system overview & design |  | FY14 Q2: 0.05; FY14 Q3: 0.05; FY14 Q4: 0.05; FY14 Q1: 0.05; FY15 Q2: 0.05
| Engineering specs & notes |  | FY14 Q2: 0.05; FY14 Q3: 0.05; FY14 Q4: 0.05; FY14 Q1: 0.05; FY15 Q2: 0.05
| Decommission activities |  | FY14 Q3: 0.05; FY14 Q4: 0.05; FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05; FY15 Q4: 0.05; FY15 Q1: 0.05; FY16 Q2: 0.05; FY16 Q3: 0.05; FY16 Q4: 0.05
g-2 | bar: FY14 Q2 to FY16 Q1
| Preliminary design |  | FY14 Q3: CD2
| Final design Delivery Ring |  | FY14 Q3: CD3a
Prep for beam studies
| Final design |  | FY14 Q1: CD3
Install M2/M3 beamline | bar: FY15 Q4; FY16 Q4
D30 Straight Section reconfig | bar: FY14 Q4 to FY16 Q1
Install pre-vault final focus quads | bar: FY15 Q1
Install Delivery Ring extraction | bar: FY16 Q2
Install M4/M5 beamline to g-2 | bar: FY16 Q3 to FY16 Q1
Build and install new target station dump | bar: FY15 Q1 to FY16 Q3
| M2/M3 piping installation drawings & piping scope layout, BOM | Ball | FY14 Q2: 0.15; FY14 Q3: 0.05; FY14 Q4: 0.05; FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05
| M5 piping installation drawings and piping scope layout, BOM | Ball | FY14 Q2: 0.1; FY14 Q3: 0.1; FY14 Q4: 0.1; FY14 Q1: 0.1; FY15 Q2: 0.1; FY15 Q3: 0.1
| D30 piping installation drawings and piping scope layout, BOM | Despande | FY14 Q2: 0.05; FY14 Q3: 0.05; FY14 Q4: 0.05
| MC-1 Hall piping installation & BOM | Ball
| Compressed area system to MC-1 Hall | Despande | FY14 Q2: 0.05; FY14 Q3: 0.05; FY14 Q4: 0.05; FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05
| Engineering specs & notes | Despande/Ball | FY14 Q2: 0.05; FY14 Q3: 0.05; FY14 Q4: 0.05; FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05; FY15 Q4: 0.05
| Oversee installation | Despande/Ball | FY14 Q4: 0.1; FY14 Q1: 0.1; FY15 Q2: 0.1; FY15 Q3: 0.1; FY15 Q4: 0.8; FY15 Q1: 0.2; FY16 Q2: 0.2; FY16 Q3: 0.2; FY16 Q4: 0.8
Mu2e
| Preliminary design |  | FY14 Q3: CD2/3
| Final design Beamline, Res Extr |  | FY14 Q4: CD3
| Final design Target Station |  | FY14 Q1: CD3
Install M4 beamline | bar: FY15 Q3 to FY18 Q1
Install DR RF and resonant extraction | bar: FY17 Q3
| Install target station | [18 empty] | ® | bar: FY18 Q1 to FY18 Q2
| M4 piping installation drawings and piping scope layout, BOM | Deshpande | FY14 Q2: 0.15; FY14 Q3: 0.1; FY14 Q4: 0.1; FY14 Q1: 0.1; FY15 Q2: 0.1; FY15 Q3: 0.1
| Mu2e Hall pipping installation & area | Ball
| Compressed area system in M4 lines & Mu2e Halls design | Deshpande | FY14 Q2: 0.1; FY14 Q3: 0.05; FY14 Q4: 0.05; FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05
| DR RF & resonant extraction piping installation drawings & piping scope layout, BOM | Ball | FY14 Q4: 0.05; FY14 Q1: 0.05; FY15 Q2: 0.05
| Engineering specs & notes | Ball | FY14 Q2: 0.1; FY14 Q3: 0.05; FY14 Q4: 0.05; FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05; FY15 Q4: 0.05
| Oversee installation | Ball/Despande | [5 empty] | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Total |  | 0 | 1.2 | 1.2 | 1.75 | 1.1 | 1.65 | 1.7 | 1.81 | 0.9 | 0.9 | 0.9 | 1.4 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0

## Project Eng
|  |  | FY14 |  |  |  | FY15 |  |  |  | FY16 |  |  |  | FY17 |  |  | FY18
|  |  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Recycler RF AIP | bar: FY14 Q2 to FY16 Q4
Build cavities | bar: FY15 Q1 to FY16 Q3
Install RF | bar: FY16 Q4
| Project Oversight | Ader | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05
Beam Transport AIP | bar: FY14 Q2 to FY15 Q1
Install extraction magnets | bar: FY14 Q4
Install RR to P1 line | bar: FY15 Q4
Install P1, P2, M1 aperture improvements | bar: FY15 Q4
| Project Oversight | Ader | FY14 Q2: 0.2; FY14 Q3: 0.2; FY14 Q4: 0.2; FY14 Q1: 0.2; FY15 Q2: 0.2; FY15 Q3: 0.2; FY15 Q4: 0.2; FY15 Q1: 0.2
Delivery Ring AIP | bar: FY14 Q2 to FY16 Q4
Collider equipment removal | bar: FY15 Q3
Tunnel installation | bar: FY15 Q3 to FY16 Q4
| Project Oversight | Ader | FY14 Q2: 0.2; FY14 Q3: 0.2; FY14 Q4: 0.2; FY14 Q1: 0.2; FY15 Q2: 0.2; FY15 Q3: 0.2; FY15 Q4: 0.2; FY15 Q1: 0.2
g-2 | bar: FY14 Q2 to FY16 Q1
| Preliminary design |  | FY14 Q3: CD2
| Final design Delivery Ring |  | FY14 Q3: CD3a
Prep for beam studies
| Final design |  | FY14 Q1: CD3
Install M2/M3 beamline | bar: FY15 Q4; FY16 Q4
D30 Straight Section reconfig | bar: FY14 Q4 to FY16 Q1
Install pre-vault final focus quads | bar: FY15 Q1
Install Delivery Ring extraction | bar: FY16 Q2
Install M4/M5 beamline to g-2 | bar: FY16 Q3 to FY16 Q1
Build and install new target station dump | bar: FY15 Q1 to FY16 Q3
| Project Oversight | Ader | FY14 Q2: 0.2; FY14 Q3: 0.2; FY14 Q4: 0.2; FY14 Q1: 0.2; FY15 Q2: 0.2; FY15 Q3: 0.2; FY15 Q4: 0.2; FY15 Q1: 0.2
Mu2e
| Preliminary design |  | FY14 Q3: CD2/3
| Final design Beamline, Res Extr |  | FY14 Q4: CD3
| Final design Target Station |  | FY14 Q1: CD3
Install M4 beamline | bar: FY15 Q3 to FY18 Q1
Install DR RF and resonant extraction | bar: FY17 Q3
| Install target station | [18 empty] | ® | bar: FY18 Q1 to FY18 Q2
| Project Oversight | Ader | FY14 Q2: 0.2; FY14 Q3: 0.2; FY14 Q4: 0.2; FY14 Q1: 0.2; FY15 Q2: 0.2; FY15 Q3: 0.2; FY15 Q4: 0.2; FY15 Q1: 0.2
Total |  | 0 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.85 | 0.05 | 0.05 | 0.05 | 0 | 0 | 0 | 0 | 0 | 0

## Drafter
|  |  | FY14 |  |  |  | FY15 |  |  |  | FY16 |  |  |  | FY17 |  |  | FY18
|  |  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Recycler RF AIP | bar: FY14 Q2 to FY16 Q4
Build cavities | bar: FY15 Q1 to FY16 Q3
Install RF | bar: FY16 Q4
| Design cavities | Popper | FY14 Q2: 0.05; FY14 Q3: 0.05; FY14 Q4: 0.05; FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05; FY15 Q4: 0.05; FY15 Q1: 0.05
| Cooling design | Popper | FY14 Q2: 0.05; FY14 Q3: 0.05; FY14 Q4: 0.05; FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05; FY15 Q4: 0.05
| Tunnel and as-built work | Popper | FY15 Q1: 0.1; FY16 Q2: 0.1; FY16 Q3: 0.1; FY16 Q4: 0.1
Beam Transport AIP | bar: FY14 Q2 to FY15 Q1
Install extraction magnets | bar: FY14 Q4
Install RR to P1 line | bar: FY15 Q4
Install P1, P2, M1 aperture improvements | bar: FY15 Q4
| Lam stand | Popper | FY14 Q2: 0.1; FY14 Q3: 0.1; FY14 Q4: 0.1
| RKB magnet stands | Popper | FY14 Q2: 0.1; FY14 Q3: 0.1; FY14 Q4: 0.1
| RR52 Vacuum Pipe | Popper | FY14 Q2: 0.1; FY14 Q3: 0.1; FY14 Q4: 0.1
| V714 B2 magnet stand, vacuum and layout | Popper | FY14 Q2: 0.05; FY14 Q3: 0.05; FY14 Q4: 0.05; FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05
| Tevatron F0 Lambertson removal and vacuum pipe | Popper | FY14 Q2: 0.05; FY14 Q3: 0.05; FY14 Q4: 0.05; FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05
| F0 quadrupole stand and vacuum | Popper | FY14 Q2: 0.05; FY14 Q3: 0.05; FY14 Q4: 0.05; FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05
| F17 C-Magnet removal and CDA stands and vacuum | Popper | FY14 Q2: 0.05; FY14 Q3: 0.05; FY14 Q4: 0.05; FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05
| HV100 2 MDC for 4 EPB’s: stand and vacuum | Popper | FY14 Q2: 0.05; FY14 Q3: 0.05; FY14 Q4: 0.05; FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05
| HV102 2 MDC for 4 EPB’s: stand and vacuum | Popper | FY14 Q2: 0.05; FY14 Q3: 0.05; FY14 Q4: 0.05; FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05
| AP-1 trim relocation (2) stand and vacuum | Popper | FY14 Q2: 0.05; FY14 Q3: 0.05; FY14 Q4: 0.05; FY14 Q1: 0.05; FY15 Q2: 0.05; FY15 Q3: 0.05
| Tunnel and as-built work | Popper | FY14 Q4: 0.6; FY15 Q4: 0.6
Delivery Ring AIP | bar: FY14 Q2 to FY16 Q4
Collider equipment removal | bar: FY14 Q2 to FY15 Q3
Tunnel installation | bar: FY15 Q3 to FY16 Q4
| Preliminary tunnel prep/overview |  | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.1
| Tunnel and as-built work |  | FY15 Q3: 0.1; FY15 Q4: 0.1; FY15 Q1: 0.1; FY16 Q2: 0.1; FY16 Q3: 0.1; FY16 Q4: 0.7
g-2 | bar: FY14 Q2 to FY16 Q1
| Preliminary design |  | FY14 Q3: CD2
| Final design Delivery Ring |  | FY14 Q3: CD3a
Prep for beam studies
| Final design |  | FY14 Q1: CD3
Install M2/M3 beamline | bar: FY15 Q4; FY16 Q4
D30 Straight Section reconfig | bar: FY14 Q4 to FY16 Q1
Install pre-vault final focus quads | bar: FY15 Q1
Install Delivery Ring extraction | bar: FY16 Q2
Install M4/M5 beamline to g-2 | bar: FY16 Q3 to FY16 Q1
Build and install new target station dump | bar: FY15 Q1 to FY16 Q3
| M2 and M3 supports/stands |  | FY14 Q2: 0.4; FY14 Q3: 0.4; FY14 Q4: 0.4; FY14 Q1: 0.2; FY15 Q2: 0.2; FY15 Q3: 0.2; FY15 Q4: 0.2
| M2/M3 vacuum layout |  | FY14 Q2: 0.4; FY14 Q3: 0.4; FY14 Q4: 0.4; FY14 Q1: 0.2; FY15 Q2: 0.2; FY15 Q3: 0.2; FY15 Q4: 0.2
| M5 supports/stands | Hurd | FY14 Q2: 0.2; FY14 Q3: 0.2; FY14 Q4: 0.2; FY14 Q1: 0.2; FY15 Q2: 0.2; FY15 Q3: 0.2; FY15 Q4: 0.2
| M5 vacuum layout |  | FY14 Q2: 0.2; FY14 Q3: 0.2; FY14 Q4: 0.2; FY14 Q1: 0.2; FY15 Q2: 0.2; FY15 Q3: 0.2; FY15 Q4: 0.2
| Extraction Kicker reconfig & stand (reuse D:EKIK stand) | Beleski | FY14 Q2: 0.2; FY14 Q3: 0.2; FY14 Q4: 0.2; FY14 Q1: 0.2; FY15 Q2: 0.2; FY15 Q3: 0.2
| Lambertson stand (motorized, two plane, US and DS motion) | Beleski | FY14 Q2: 0.2; FY14 Q3: 0.2; FY14 Q4: 0.1; FY14 Q1: 0.1; FY15 Q2: 0.1; FY15 Q3: 0.1
| 8Q32 magnet & stand (stationary) | Beleski | FY14 Q2: 0.1; FY14 Q3: 0.1; FY14 Q4: 0.1; FY14 Q1: 0.1; FY15 Q2: 0.1; FY15 Q3: 0.1
| C-Magnet stand (stationary) | Beleski | FY14 Q2: 0.1; FY14 Q3: 0.1; FY14 Q4: 0.1; FY14 Q1: 0.1; FY15 Q2: 0.1; FY15 Q3: 0.1
| Tunnel and as-built work | Beleski | FY14 Q4: 0.3; FY14 Q1: 0.3; FY15 Q2: 0.3; FY15 Q3: 0.3; FY15 Q4: 0.8; FY16 Q4: 0.8
Mu2e
| Preliminary design |  | FY14 Q3: CD2/3
| Final design Beamline, Res Extr |  | FY14 Q4: CD3
| Final design Target Station |  | FY14 Q1: CD3
Install M4 beamline | bar: FY15 Q3 to FY18 Q1
Install DR RF and resonant extraction | bar: FY17 Q3
| Install target station | [18 empty] | ® | bar: FY18 Q1 to FY18 Q2
| M4 Magnet stands/supports | Hurd | FY14 Q2: 0.4; FY14 Q3: 0.4; FY14 Q4: 0.4; FY14 Q1: 0.4; FY15 Q2: 0.4
| M4 vacuum layout | Hurd | FY14 Q2: 0.4; FY14 Q3: 0.4; FY14 Q4: 0.4; FY14 Q1: 0.4; FY15 Q2: 0.4
| Tunnel and as-built work | Hurd | [5 empty] | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9
Total |  |  | 3.4 | 3.4 | 4.2 | 2.9 | 2.9 | 3.1 | 3.35 | 1.2 | 1.15 | 1.15 | 2.6 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9

## Technician
|  |  | FY14 |  |  |  | FY15 |  |  |  | FY16 |  |  |  | FY17 |  |  | FY18
|  |  | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Recycler RF AIP | bar: FY14 Q2 to FY16 Q4
Build cavities | bar: FY15 Q1 to FY16 Q3
Install RF | bar: FY16 Q4
| Cooling test skid at MI-60 |  | FY14 Q2: 0.2; FY14 Q3: 0.2; FY14 Q4: 0.2; FY14 Q1: 0.2; FY15 Q2: 0.2; FY15 Q3: 0.2; FY15 Q4: 0.2; FY15 Q1: 0.2; FY16 Q2: 0.2; FY16 Q3: 0.2
| Installation LCW skid work |  | FY16 Q3: 0.5; FY16 Q4: 0.7
Beam Transport AIP | bar: FY14 Q2 to FY15 Q1
Install extraction magnets | bar: FY14 Q4
Install RR to P1 line | bar: FY15 Q4
Install P1, P2, M1 aperture improvements | bar: FY15 Q4
| Write procedures for QC installation checklist & HA | Vrbos | FY14 Q3: 0.1; FY15 Q3: 0.1
| Build RKB ceramic tubes | Vrbos | FY14 Q2: 0.5; FY14 Q3: 1
| Install LAM & 2 RKB's magnets and stands | Vrbos | FY14 Q4: 4
| RR52 vacuum work | Vrbos | FY14 Q4: 2
| Installation LCW work |  | FY14 Q4: 2
Install RR to P1 line water | bar: FY14 Q4; FY15 Q4
| Install RR to P1 line task manager |  | FY14 Q4: 0.75; FY15 Q4: 1
| Install RR to P1 line vacuum |  | FY14 Q4: 1.25; FY15 Q4: 3
| Install P1, P2, M1 aperture improvements water |  | FY15 Q4: 2
| Install P1, P2, M1 aperture improvements task manager |  | FY15 Q4: 1.5
| Install P1, P2, M1 aperture improvements vacuum |  | FY15 Q4: 2
Delivery Ring AIP | bar: FY14 Q2 to FY16 Q4
Collider equipment removal | bar: FY14 Q2 to FY15 Q3
Tunnel installation | bar: FY15 Q3 to FY16 Q4
| Sort/clean-up hoses and parts in tunnel | Vrbos | FY14 Q2: 0.2; FY14 Q3: 0.2; FY14 Q4: 0.2; FY14 Q1: 0.2; FY15 Q2: 0.2; FY16 Q4: 0.1
| Main header & magnet hose work | Slazyk | 0.3 | 0.3 | 0.3 | 0.3 | 0.3 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.7
| Build Kicker Flourinert Skid in AP30 for loads | Slazyk | bar: FY14 Q1 to FY15 Q2
| Stands/supports and move magnets |  | FY14 Q3: 1; FY14 Q4: 2; FY14 Q1: 2; FY15 Q2: 2
| Remove vacuum components, pumps, gauges, etc. |  | FY14 Q3: 2; FY14 Q4: 2; FY14 Q1: 2; FY15 Q2: 2
| Inspect ion pumps & do QC |  | FY14 Q4: 0.5; FY14 Q1: 0.5; FY15 Q2: 0.5
| Blow magnets out in accumulator (100 hours total) |  | FY14 Q3: 0.2
g-2 | bar: FY14 Q2 to FY16 Q1
| Preliminary design |  | FY14 Q3: CD2
| Final design Delivery Ring |  | FY14 Q3: CD3a
Prep for beam studies
| Final design |  | FY14 Q1: CD3
Install M2/M3 beamline | bar: FY15 Q4; FY16 Q4
D30 Straight Section reconfig | bar: FY14 Q4 to FY16 Q1
Install pre-vault final focus quads | bar: FY15 Q1
Install Delivery Ring extraction | bar: FY16 Q2
Install M4/M5 beamline to g-2 | bar: FY16 Q3 to FY16 Q1
Build and install new target station dump | bar: FY15 Q1 to FY16 Q3
| Fabricate M2/M3 hoses upstairs (65 quads and 9 trims) | Slazyk | bar: FY15 Q3; FY15 Q1 to FY16 Q3
| Install M2/M3 beamline Main header & magnet hose work (65 quads and 32 trims) | Slazyk | FY15 Q4: 4; FY16 Q4: 4
| Install M2/M3 beamline Magnet & stand installation task manager (65 quads and 32 trims) | Vrbos | FY15 Q4: 2; FY16 Q4: 2
| Install M2/M3 beamline Vacuum work (65 quads and 32 trims) | Vrbos | FY15 Q4: 3; FY16 Q4: 3
| D30 Straight Section (& D/A) reconfig Main header & magnet hose work | Slazyk |  | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| D30 Straight Section (& D/A) reconfig Magnet & stand installation task manager | Vrbos | bar: FY14 Q3 to FY16 Q1
| D30 Straight Section (& D/A) reconfig Vacuum work | Vrbos | bar: FY14 Q3 to FY16 Q1
| M4/M5 fabricate hoses (M5 line has 41 magnets: 27 quads & 14 trims) | Slazyk | bar: FY16 Q2
| Install M4/M5 beamline to g-2 water (M5 line has 41 magnets: 27 quads & 14 trims) | Slazyk | FY16 Q3: 2; FY16 Q4: 2; FY16 Q1: 2
| Install M4/M5 beamline to g-2 task manager (M5 line has 41 magnets: 27 quads & 14 trims) | Vrbos | bar: FY16 Q3 to FY16 Q1
| Install M4/M5 beamline to g-2 vacuum (M5 line has 41 magnets: 27 quads & 14 trims) | Vrbos | FY16 Q3: 3; FY16 Q4: 2; FY16 Q1: 2
| Write procedures for QC installation checklist & HA | Vrbos | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05 | 0.05
Mu2e
| Preliminary design |  | FY14 Q3: CD2/3
| Final design Beamline, Res Extr |  | FY14 Q4: CD3
| Final design Target Station |  | FY14 Q1: CD3
Install M4 beamline | bar: FY15 Q3 to FY18 Q1
Install DR RF and resonant extraction | bar: FY17 Q3
| Install target station | [18 empty] | ® | bar: FY18 Q1 to FY18 Q2
| Write procedures for QC installation checklist & HA | Vrobs | FY14 Q1: 0.2; FY15 Q2: 0.2
| M4 fabricate hoses upstairs (101 magnets: 55 quads & 23 trims) | Slazyk | FY15 Q2: 0.25
| M4 Main header & magnet hose work (101 magnets: 55 quads & 23 trims) | Vrbos | [5 empty] | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2 | 2
| M4 Magnet & stand installation task manager (101 magnets: 55 quads & 23 trims) | Vrbos | bar: FY15 Q3 to FY18 Q2
| M4 Vacuum work | Vrobs | [5 empty] | 1 | 1 | 1 | 1 | 1 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5 | 0.5
Total |  |  | 1.25 | 9.05 | 20.25 | 10.45 | 10.7 | 5.85 | 26.25 | 6.75 | 7.75 | 13.25 | 21.55 | 11 | 2 | 2 | 2 | 2 | 2

## Totals
| FY14 |  |  |  | FY15 |  |  |  | FY16 |  |  |  | FY17 |  |  | FY18
| Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Engineer | 6.519 | 6.669 | 7.919 | 5.819 | 7.069 | 9.8 | 9.26 | 5.75 | 4.75 | 5.25 | 6.9 | 1.8 | 1.8 | 1.8 | 1.8 | 1.8 | 1.3
Drafting | 3.4 | 3.4 | 4.2 | 2.9 | 2.9 | 3.1 | 3.35 | 1.2 | 1.15 | 2.6 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0.9 | 0
Technican | 1.25 | 9.05 | 20.25 | 10.45 | 10.7 | 5.85 | 26.25 | 6.75 | 7.75 | 13.25 | 21.55 | 11 | 2 | 2 | 2 | 2 | 2

## Convery
|  |  | FY14 |  |  |  | FY15 |  |  |  | FY16 |  |  |  | FY17 |  |  | FY18
|  | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2
Recycler RF AIP | bar: Q1 to FY16 Q4
Build cavities | bar: FY15 Q1 to FY16 Q3
Install RF | bar: FY16 Q4
Beam Transport AIP | bar: Q1 to FY15 Q1
Install extraction magnets | bar: FY14 Q4
Install RR to P1 line | bar: FY15 Q4
Install P1, P2, M1 aperture improvements | bar: FY15 Q4
Delivery Ring AIP | bar: Q1 to FY16 Q4
Collider equipment removal | bar: FY15 Q3
Tunnel installation | bar: FY15 Q3 to FY16 Q4
g-2 | bar: Q1 to FY16 Q1
| Preliminary design | FY14 Q3: CD2
| Final design Delivery Ring | FY14 Q3: CD3a
Prep for beam studies | bar: Q1
| Final design | FY14 Q1: CD3
Install M2/M3 beamline | bar: FY15 Q4; FY16 Q4
D30 Straight Section reconfig | bar: FY14 Q4 to FY16 Q1
Install pre-vault final focus quads | bar: FY15 Q1
Install Delivery Ring extraction | bar: FY16 Q2
Install M4/M5 beamline to g-2 | bar: FY16 Q3 to FY16 Q1
Build and install new target station dump | bar: FY15 Q1 to FY16 Q3
Mu2e
| Preliminary design | FY14 Q3: CD2/3
| Final design Beamline, Res Extr | FY14 Q4: CD3
| Final design Target Station | FY14 Q1: CD3
Install M4 beamline | bar: FY15 Q3 to FY18 Q1
Install DR RF and resonant extraction | bar: FY17 Q3
| Install target station | [18 empty] | ® | bar: FY18 Q1 to FY18 Q2
shutdown activity