## Slide 1: LCLS II FNAL Niobium Pre-Procurement Review - Overview
Camille M. Ginsburg, FNAL
April 17, 2014

## Slide 2: Scope and Charge for the Meeting
Review the technical specification and plan toward procurement of the niobium and other materials for LCLS-II SRF cavities
  schedule
  materials specifications
  drawing readiness
  cost estimates, including contingency
  QA/QC plan
Technical and procurement experts have been invited to form a review team
Outcome: a set of action items to lead us to the procurement readiness (gate) review prior to procurement

## Slide 3: Review Team
Many thanks to:
Allan Rowe (Chair) – FNAL
Gigi Ciovati – JLab
Marc Ross – SLAC
Barry Miller – SLAC
John Zweibohmer – FNAL

## Slide 4: Procurement Readiness Review – the next step!
Source: “Project Design and Milestone Review Procedure,” LCLSII-1.1-QA-0009-R0
Confirm necessary staffing, procurement plan/procedures, requisite drawings in place
Identify equipment/systems with safety importance, ensure compliant with Hazard Analysis Report
Identify procedures necessary for safety, ensure developed, reviewed, verified, approved
Review topics: objectives, schedule, issues and concerns, documentation status, QA and safety, residual risk items, open items and plans for closeout
Please discuss and collect the action items needed for a successful PRR!

## Slide 5: Future LCLS-II Review Committee Charge: Niobium Raw Material Procurement Readiness Review
From Greg Hays (deputy systems manager):
The review committee is charged to evaluate the readiness of the LCLS-II Cryogenic Systems Niobium material procurement. The review committee should evaluate by responding to the following questions:
Technical Scope and Schedule
  Has the responsibility for fabrication, inspection, test, and acceptance for the material flow through each participating party been defined?
  Have all participating partner laboratories agreed to the procurement schedule and timeline?
Procurement Team Roles and Responsibilities
  Have all key project team members been identified with roles and responsibilities defined?
Procurement Package Documentation Status
  Are the material specifications defined and agreed upon by all participating parties?
  Has the relevant procurement documentation been approved formally by all parties?
Procurement Acquisition Strategy
  Does the procurement strategy as presented provide confidence from fabrication, inspection, test and final delivery that schedule, budget and quality will be achieved?
  Has the proposal evaluation process been developed and approved by affected stakeholders?
Cost Estimate
  Is the cost estimate basis defined and valid for the requisition?
  Are the costs reported from the RFI responses within budget?
Quality Assurance
  Have all inspection and test plans with clearly defined acceptance criteria been developed, reviewed and approved?
  Are all approved specifications and drawings under configuration control and are they available to partner laboratories?
  Has the nonconformance reporting and problem disposition process been defined and agreed upon by partner laboratories?
  Has the inspection/test records archive plan been clearly defined and is the information available to affected stakeholders?
  Has the supplier surveillance plan, including any required pre-award surveys, mandatory inspection points, or production/inspection readiness reviews been developed and vetted with affected project stakeholders?
Lessons Learned
  Have lessons learned from similar procurements and/or other laboratories been reviewed and applied?
Risks, Issues, and Concerns
  Are there any risks, issues, or other concerns?

## Slide 6: General Considerations
Project schedule is aggressive; cost is tightly constrained
Niobium procurement schedule is driven by the overall project plan
Niobium procurement is technically complex and has a long lead time
FNAL has extensive previous experience and familiarity with material vendors
For this large project, we are working closely with SLAC and JLab, including adopting the JLab SOTR model
  SOTR=Subcontracting Officer Technical Representative
  FNAL responsible for niobium procurements; JLab technical experts to be critically involved in vendor visits, all agreements

## Slide 7: Presentations
Welcome and Logistics – Rich Stanek (Senior Team Lead)
Review Overview – Camille Ginsburg (CAM, Deputy Team Lead)
Schedule – Marc Kaducak (Project Engineer – Cost/Schedule)
Advance Acquisition Plan – Bob Cibic (Procurement Officer)
Materials Specification – Lance Cooley (SC Materials Dept Head)
Fabrication Drawings – Mike Foley (Niobium SOTR)
Request for Proposal – Mike
QA/QC plans – Camille
Review Team Discussion
Closeout