## Slide 1: LCLS-II Cavity Schedule
Tom Peterson for the cryomodule team
15 April 2014

## Slide 2: Schedule comments
Since procurement of niobium and fabrication of new cavities will take about 2 years until delivery of first new cavities, the first cryomodule to be built at Jlab and first at Fermilab will incorporate ILC cavities.
The main activities to prepare those ILC cavities for the prototype cryomodules are:
  Helium vessel
  End lever tuner
  Magnetic shielding
  Input coupler (not part of the scope of this review)
  HOM couplers (not part of the scope of this review)

## Slide 3: HTS tests
Horizontal testing of dressed cavities drives the schedule for the first few dressed cavities
Goal to verify retention of high Q0 with new N2 doping process in HTS test of dressed cavities
Not all cavities for the prototype cryomodule (nor for production cryomodules) will be HTS tested
Next slide shows HTS plan

## Slide 4
Test, goal | Start 2014 | Cav. type | Helium Vessel | HOM antenna | Couple (cold) | Coupler (warm) | Magn shield | Tuner | RF
1: high-Q perform. HTS commissioning | Apr.01 | #1 | ILC | None | variable | None | 1-layer +Coil | None | 50W
2: HOM feedthru | Apr.20 | #1 | ILC | XFEL | variable | None | 1L+coil | None | 50W
3: FPC cold modif, μ-phonics study | May.20 | #1 | ILC | XFEL | FPC modif | FPC He cooled | 1L+coil | blade | IOT
4: FPC modified; μ-phonics study | Jul.12 | #1 | ILC | JLAB | FPC modif | FPC#1 modif | 1L+coil | blade | IOT
5: High-Q cav. #2 FPC#1 | Aug.15 | #2 | LCLS-II | XFEL | FPC modif | FPC#1 modif | 1L+coil | No tuner | IOT
6:High-Q#3 integrated FPC#2 | Sep.15 | #3 | LCLS-II | JLAB | FPC modif | FPC#2 modif | 2-layer | Lever tuner | IOT
7: high-Q#2 integrated Tuner reliability | Oct.15 | #2 | LCLS-II | XFEL | FPC modif | FPC#1 modif | 2-layer | lever tuner | IOT
HTS tests of N2 doped short-short Cavities to Qualify
Dress Cavity Performance
Cavity #1: high-Q0 cavity dressed in ILC type vessel (Test 1-4) – can be non high-Q0
High-Q cav. #2 and #3 will qualify for installation to pre-production CM: (tests 5-7)

## Slide 5: Prototype cavity dressing (from an unofficial working schedule)