## Slide 1: ASTA Commissioning & Status
Elvin Harms
ASTA Users Meeting
9 June 2014

## Slide 2: Introduction
Recap where we were last year and goals
Accomplishment in past 12 months
What’s on the horizon
Summary
E. Harms 2nd ASTA USers Meeting 9-10 June 2014

## Slide 3: CY13 - 50 MeV Injector + 1 Cryomodule
Goal: installation complete and beam commissioning started by end of CY13
  RF gun + RF system and photocathode laser system
  2 SRF booster cavities (CC1 and CC2) + RF systems
  50 MeV beam line elements and instrumentation to the low energy dump
  Low energy beam dump
  SRF cryomodule (RFCA002/CM2)
Installation of 1st AARD experiment (high brightness X-ray channeling source)
3
electron gun
booster cavities
flat beam transform
chicane
beam dump
1st cryomodule
test beamlines
beam dump
spectrometer magnet
50 MeV Beam Energy
ASTA Photoinjector
22 meters
To be installed
in CY13
E. Harms 2nd ASTA USers Meeting 9-10 June 2014

## Slide 4: Accomplishments in 2013 - Recap
4
Laser installed/UV to ASTA cave
CM-2 Installed and nearly ready for cooldown
Warm Coupler Conditioning completed
Gun installed and first phase of conditioning complete
9-way diagnostic cross installed and operational
Electrons!
  Beam sensed on Faraday cup, Loss Monitor, Wall Current Monitor, and now BPM’s
  Calibration in progress
E. Harms 2nd ASTA USers Meeting 9-10 June 2014

## Slide 5: Short-term Future Activities - Recap
5
Continue conditioning the RF gun (goal is 45 MV/m, currently at 32 MV/m)
Complete installation of RFCA002/CM2
Complete upgrade and install CC1
Cool down and commission CM2, CC1; recommission CC2
Continue gun photoelectron studies @ 3 - 5 MeV
Continue installation of 50 MeV beam line components
Start commissioning 50 MeV injector into beam dump in the Fall
E. Harms 2nd ASTA USers Meeting 9-10 June 2014

## Slide 6: Accomplishments in 2014 so far
6
Continue conditioning the RF gun (goal is 45 MV/m, currently at 32 MV/m)
Complete installation of RFCA002/CM2
Complete upgrade and install CC1
Cool down and commission CM2, CC1; recommission CC2
Continue gun photoelectron studies @ 3 - 5 MeV
Continue installation of 50 MeV beam line components
Start commissioning 50 MeV injector into beam dump in the Fall
E. Harms 2nd ASTA USers Meeting 9-10 June 2014

## Slide 7: 2014 Achievements: Laser & Gun
7
See Jinhao’s talk at 1040 - Laser
See Giulio’s talk at 13:50 - electron measurements
7 March 2014: Gun cavity was operated at 3.48 MW (GCVTPM), 1 ms pulse width, 1 Hz for 1.5 hours and 2.25 hours separately. 45 MV/m achieved!
18 March 2014: New (Cs2Te) cathode installed and electrons produced
4 June 2014: 3000 Electron Bunches from the ASTA Photoelectron Gun
E. Harms 2nd ASTA USers Meeting 9-10 June 2014
3000 bunches on Faraday cup
YaG screen image of first electrons from Cs2Te cathode

## Slide 8: 2014 Achievements: Cryomodules
8
See Elvin’s talk at 13:30
CM-2 cooled to 2 K and has stayed there with excellent reliability
  Individual cavity testing essentially complete – good results
  Fewer problems as compared to CM-1
  Begin full cryomodule powering this summer
CC2 re-commissioned in late 2013
  on-resonance conditioning
  peak gradient reduced (<21 MV/m)
  should attempt higher power conditioning as conditions allow
  updated ESECON LLRF and calibration factors
CC1 upgrade continues
  replacing a piezo tuner which failed during final checkout
  HLRF (klystron) commissioning begun
  support systems in place and checkout in progress
E. Harms 2nd ASTA USers Meeting 9-10 June 2014

## Slide 9: 2014 Achievements: CM-2
CM2 installed at ASTA
ILC Milestone
31.5 MV/m
E. Harms 2nd ASTA USers Meeting 9-10 June 2014

## Slide 10: 2014 Achievements: CC-1
E. Harms 2nd ASTA USers Meeting 9-10 June 2014
Buttoning up CC-1
Failed Piezo tuner
Cavity removal

## Slide 11: 2014 Achievements: 50 MeV beam-line
11
See Curtis’s talk at 11:00
Third Girder (of 3) installed this week
Dump and shielding in place
Components necessary for first beam to dump identified
Priority installation and hook-up for those devices
Careful and extensive check-out
Machine Protection System development & installation proceeding
E. Harms 2nd ASTA USers Meeting 9-10 June 2014

## Slide 12: 2014 Achievements: Guests & Users
12
See Auralee’s talk at 14:10
Visitors from KEK: CM-2
Jun Zhu: Guest from Batelle
  RTFB development and SRF commissioning
(at least) three Summer interns assigned to ASTA activities
E. Harms 2nd ASTA USers Meeting 9-10 June 2014
Ayaka & Mathieu

## Slide 13: Summary of 2014 Achievements
13
RF gun has reached goal of 45 MV/m, 1ms, 1 Hz
  Increase repetition rate to 5 Hz
RFCA002/CM-2 works in the cold
  full cryomodule powering and other testing to follow
CC1 upgrade nearly complete
  (cryo) installation will take time
CC2 cooled back down and operation verified
  reduced gradient will require attention
Beam-line installation well along
  vacuum, cabling etc. still a significant effort
Pressing for 20 MeV electrons this summer
50 MeV this FY
Balancing installation, Cryomodule commissioning, electron operation requires careful coordination and flexibility
E. Harms 2nd ASTA USers Meeting 9-10 June 2014

## Slide 14: Summary
Progress on virtually every front
  notable achievements
This summer will be busy and hopefully exciting
Looking forward to hosting first experiments
An extremely dedicated and capable ASTA staff
  KUDO’s to them!
E. Harms 2nd ASTA USers Meeting 9-10 June 2014

## Slide 15: Thank you for your attention
E. Harms 2nd ASTA USers Meeting 9-10 June 2014