## Slide 1: CM-2 Commissioning
Elvin Harms
ASTA Users Meeting
9 June 2014

## Slide 2: Introduction
CM-2 is
  Type 3+ ILC type Cryomodule
  8 cavities (1.3 GHz) built by industry
  Vertical and Horizontal tests at JLab & Fermilab (good to 35 MV/m)
  Cryomodule assembled at Fermilab
  first ILC type cryomodule which may(?) reach average gradient specification of 31.5 MV/m
  Designed for pulsed operation
Main accelerating device for ASTA
Expect beam tests in FY2015
E. Harms AWLC14/SRF Technology WG 14 May 2014

## Slide 3: Commissioning Process
Prerequisites
  cryomodule installed
  pipes welded and certified leak tight
  pressure tests successful
  vacuum circuits leak tight (beam tube, coupler, insulating vacuum)
  instrumentation, tuners verified operational
  warm conditioning completed
  cooldown
Measure frequency spectra both warm and cold
Single cavity powering
Power all cavities together, characterize system performance
Follow-on studies
E. Harms AWLC14/SRF Technology WG 14 May 2014

## Slide 4: Single Cavity
Tune cavity to resonance
Map out and set QL
System calibrations, calculate gradient, k
On-resonance conditioning
Determine peak performance
Final (high power) LLRF calibration
Lorentz Force Detuning Compensation set-up
Document dark current, x-rays vs. gradient
Dynamic Heat Load measurements (Q0)
E. Harms APT Seminar 14 January 2014
E. Harms AWLC14/SRF Technology WG 14 May 2014

## Slide 5: Commissioning Process
E. Harms APT Seminar 14 January 2014
E. Harms AWLC14/SRF Technology WG 14 May 2014

## Slide 6: Tuning to resonance
E. Harms APT Seminar 14 January 2014
Start here
Goal
1.30 GHz
Df ~ 240 MHz
Motor steps
Motor temperature
E. Harms AWLC14/SRF Technology WG 14 May 2014
Dt ~ 25K

## Slide 7: Setting QL
E. Harms APT Seminar 14 January 2014
E. Harms AWLC14/SRF Technology WG 14 May 2014
3 – 3.5 E6

## Slide 8: Low Level RF
Labview vi with all parameters available in ACNET
E. Harms APT Seminar 14 January 2014
E. Harms AWLC14/SRF Technology WG 14 May 2014

## Slide 9: On-resonance conditioning
20 ms to 1.3 ms pulse width (500 ms fill time)
1-2 Hz repetition rate
Peak power 1 MW (narrow pulse width) or < 25 MV/m
Monitor
  Vacuum
  Field Emission (3 points)
  PMT
  Coupler window temperatures
Automated process (mostly)
E. Harms APT Seminar 14 January 2014
Conditioning Sequencer
Cavity #6 Conditioning
E. Harms AWLC14/SRF Technology WG 14 May 2014

## Slide 10: Peak Gradient
E. Harms APT Seminar 14 January 2014
27 February 2014:
CM-2 Cavity 3 achieves 31.5 MV/m (Administrative limit)
5 Hz, 1.6 ms pulse width, LFDC Active
E. Harms AWLC14/SRF Technology WG 14 May 2014

## Slide 11: Lorentz Force Detuning
E. Harms APT Seminar 14 January 2014
Off
On
E. Harms AWLC14/SRF Technology WG 14 May 2014

## Slide 12: Dark Current/X-rays
E. Harms APT Seminar 14 January 2014
Threshold ≥ 20 MV/m
E. Harms AWLC14/SRF Technology WG 14 May 2014
courtesy Andy Hocker, TD

## Slide 13: Dark Current/X-rays
E. Harms APT Seminar 14 January 2014
Threshold ≥ 20 MV/m
E. Harms AWLC14/SRF Technology WG 14 May 2014
response from
Upstream
Faraday cup
courtesy Andy Hocker, TD

## Slide 14: Dark Current/X-rays
E. Harms APT Seminar 14 January 2014
E. Harms AWLC14/SRF Technology WG 14 May 2014
X-ray threshold
= 19 MV/m

## Slide 15: Performance to Date - Gradient
CM2 installed at ASTA
ILC Milestone
31.5 MV/m
E. Harms AWLC14/SRF Technology WG 14 May 2014

## Slide 16: Performance to Date – Q0
E. Harms AWLC14/SRF Technology WG 14 May 2014
courtesy Andy Hocker, TD

## Slide 17: Timeline
Cryomodule installed in NML/ASTA – April 2013,
Warm coupler conditioning (one cavity at a time) – 9 May to 18 June 2013
Cooldown – 23 October to 11 November 2013
Begin cold operation, Cavity 1 only – 13 November 2013
Cavity 1 complete (13 November - 30 January)
Cavity 2 complete ( 31 January - 15 February, 16 days)
Cavity 3 complete ( 24 February – 4 March, 9 days)
Cavity 4 complete ( 4 – 10 March, 6 days)
Cavity 5 complete ( 18 - 26 March, 9 days)
Cavity 6 complete ( 28 March - 3 April, 7 days )
Cavity 7 complete (4 April – 7 May, mostly done by 8 April, coupler vacuum)
Cavity 8 complete (23 May – 6 June) warm coupler vacuum issue
E. Harms APT Seminar 14 January 2014
E. Harms AWLC14/SRF Technology WG 14 May 2014

## Slide 18: Cavity 8 Vacuum
Warm coupler vacuum issues on cavity #8
  the only significant hiccup
E. Harms AWLC14/SRF Technology WG 14 May 2014

## Slide 19: Cavity 8 Vacuum
Warm coupler vacuum issues on cavity #8
  Unable to localize leak
  Isolated C8 from coupler system and pumped independently with 20 l/s ion pump backed by a turbo
  Success!
E. Harms AWLC14/SRF Technology WG 14 May 2014
Coupler 8 Ion pump
(2.8 E-09)
Coupler space Ion pump
1E-06
1E-10

## Slide 20: Students
E. Harms AWLC14/SRF Technology WG 14 May 2014
In addition to ongoing studies by Auralee Morin from CSU
Visit in March by 2 PhD students from KEK
  Ayaka Kuramot
    supervised by Hitoshi Hayano
    HOM spectra characterization
    comparison with other Tesla style 9-cell cavities at DESY and KEK
  Mathieu Omet
    supervised by Shinichiro Michizono
    extensive measurements of the klystron driving CM2
    developed an algorithm in firmware to cancel the klystron nonlinearities in both amplitude and phase
  Additional visitors welcome!

## Slide 21: On the horizon
Revisit selected cavities (8, 6, 1)
Install waveguide distribution system
Power all cavities together
Additional studies
  LLRF
  LFDC
  Long pulse
  thermal cycling/Q0
  others as requested
Beam in 2015
E. Harms AWLC14/SRF Technology WG 14 May 2014

## Slide 22: Summary
CM2 cold commissioning since December
8/8 of the Cavities are now characterized
  Average Gradient = 31.375 MV/m
Estimated ~2 weeks/cavity, 1 week achievable
Performance almost as hoped for so far
Fewer problems than with CM1
Full cryomodule testing in this summer
  anxious for results!
Welcome visitors and additional studies requests
Collaborative effort by MANY people, especially TD & AD
E. Harms AWLC14/SRF Technology WG 14 May 2014

## Slide 23: Thank you for your attention
E. Harms AWLC14/SRF Technology WG 14 May 2014