## Slide 1: Muon Campus Shutdown Cons Gattuso 5/01/14

## Slide 2: Tunnel Access Status
Supervised Access
  Tunnel Key have been recored to Shutdown key set (Rings only)
    Permenant key system has been set up
  Items being worked
    RWP
      Currently your signature is required every 30 days
        Trying to get this waved for 1/Shut down time frame (Rings only)
  Human factor
    Tunnel relamping
    At the 10 and 30 Service buildings
      Port-a-pods ($50/month/unit
      Water stations
        I have acquired 2 units will acquire bottle water in the same way

## Slide 3: Tunnel work status
Alignment work
  Network
  Referencing
  Other issues
Work areas
  D/A
  30 straight section
  E760 Pit
  50 straight section
  Ring in general
Component tagging
  Start the program next week
  Need clear direction as to the final distances of some components

## Slide 4: Alignment work
Network monuments are all in…
  Rings/Transport to the Gates
    Complete
  Label control and painting done
    Complete
Vertical network
  Complete
Horizontal Network will follow
  ~35% Complete, On hold due to MC-1 Network installation
Refereeing and as founding ( ~1 hour per magnet)
  D/A line
    Complete
  30 Straight section
    Accumulator Ring 95% Complete
    Delivery Ring 90% complete
      ~4-5 magnets have issue with Shuts that are in the way and can't be reference until they are removed.

## Slide 6: Work areas
DR1-1 and DR-8
  Removed and Spool piece put in there place
    Area has been pump down and leak checked
E760 pit area
  The 4-8 Ghz Core Momentum kicker tanks 1 and 2 next the AP50 pit should be ready to be moved to the 40 jump point.
    This will give us access to the Crane within the pit to raise and lower components as needed.
      Crane will most likely need service.
D/A line
  Vacuum components between magnets have been removed
  Power leads and Klixon cabling have been disconnected
  Water lines will be valved out and capped
  Magnets will be moved to jump point (40 hatch) starting today
  Working on the process of moving magnets

## Slide 7: Work areas
30 straight sections
  ICW system removal
    95% of the pipe is down from the ceiling
    ~350-400 Ft of piping will be cut to 4 FT lengths for disposal
      Brown Rad box will be delivered to AP-30
  Power Cable Disconnections/Removal/Booting
    Accumulator Ring
      Will start Monday
    Delivery Ring
      Will start Today
    AP3 line
      Will start Today
  Delivery Ring
    Vented
      Cooling Tanks being prepped for removal
        Shipped to B0 compressor building

## Slide 8: Bumps In The Road
D3Q8 location in the 30 straight section

## Slide 9: ICW removal

## Slide 10: D/A Line Removal

## Slide 11: Component Tagging
Three Classes
  Red: Components to be removed from tunnel
    Either Storage
    Rad waste
  Blue: Components to removed from current location and installed back to there original location.
    Magnet in the Delivery ring 30 section for example
  Green: Components to removed from current location and store at its jump point prior to being re installed else ware.
    Magnet being moved the Accumulator to the M3/M4 or M5 lines
Overall Going Well Need to
remind Techs to do it.

## Slide 12: Plan for the next few weeks
D/A
  Complete removal and relocation of element
  Review the removal process and look into additional hardware to move magnets
10 straight section
  Remove cooling tanks and insert spool pieces.
    Waiting 6-8 weeks for there fabrications
30 Straight section
  Removal of the Delivery Ring Cooling tanks
  Removal of the Accumulator Cooling tanks
  Strip beam pipe and vacuum components in both machines
  Disconnect cabling to magnets
    Boot or Cut depending on type and magnet location

## Slide 13: Plan for the next few weeks
Prepare for AP0 Pulling
  Stage cooling tanks/RF tanks in AP3 line for pulling
  Finalize how we will be keeping the AP0 hatch
    One row of blocks
    Fencing
    Ok keep it just we have it, fully blocked
Prepare for Pulling the AP40 hatch
  ¾ inch plywood will be needed purchased and staged
  Electric forklift will need to be readied
  What ever equipment we have that still needs to be pulled staged
10 straight section
  Pull tanks and replace with spools
    Waiting fabrication