## Slide 1: Mu2e CD-2 Review Template
U.S. DEPARTMENT OF
ENEGY
Office of
Science
A. Mukherjee
Tracker L2 Manager Acting Assembly & Installation L3 manager
7/8/2014

## Slide 2: Survey
This covers survey (optical) and checkout of the tracker after moving the mu2e building
All institutions working on the tracker are assumed to send students or postdocs for the checkout
Costed labor is surveyors

## Slide 3: Cost Distribution by Resource Type
Base Cost (AY $k)
Chart: 
| L Labor
Total | 68104.4006

## Slide 4: Quality of Estimate
Base Cost by Estimate Type (AY$k)
Chart: 
| L5 / M5 Conceptual | L7 / M7 Rough Estimate Pre-Conceptual - Uncommon Work
Total | 63659.8097 | 4444.5909

## Slide 5: Labor Resources
FTEs by Discipline
Chart: Annual FTE's
| FY15 | FY16 | FY17 | FY18 | FY19 | FY20 | FY21
EN Engineering | 0.1404 | 0 | 0
FM Facilities Management | 0.0023 | 0 | 0
SC Scientific | 0.0906 | 0.6211 | 0.1045
TE Technical | 0.0475 | 0.1449 | 0
Cumulative | 0.2808 | 1.0468 | 1.1513

## Slide 6: Cost Table
Costs are fully burdened in AY $k
 | Base Cost (AY k$) |  |  |  |  | 
 | M&S | Labor | Total | Estimate Uncertainty (on remaining costs) | % Contingency on ETC | Total Cost
475.06.06 Detector Assembly & Installation Actuals | 0 | 0 | 0 |  |  | 0
475.06.06 Detector Assembly & Installation |  | 68 | 68 | 36 | 53% | 104
Grand Total |  | 68 | 68 | 36 | 53% | 104