## Slide 1: Mu2e Accelerator Installation & Commissioning
Steve Werkema
Mu2e Accelerator Level 2 Manager
10/22/2014

## Slide 2: Scheduling Constraints
Mu2e Funding Profile
  Relatively light funding in FY15 and FY16 has forced us to defer implementation activities to FY17 and later
  Causes long delays between completion of design and beginning of implementation
Mu2e tailoring strategy
  Final design is complete in many sub-projects well before CD-3c (early-mid FY16)
  Note: this is of very small consequence since the funds to begin implementation will not be available until later
g-2 run
  g-2 beam operations are expected to begin early-mid calendar 2017
  External beamline installation requires magnet moves from beam enclosures that will be inaccessible during g-2 running – magnet moves must be scheduled to occur during Accelerator Shutdowns

## Slide 3: Scheduling Constraints (continued)
Fermilab resource availability
  Mu2e Accelerator will be making a heavy demand on Fermilab (particularly AD) engineering and technical resources in FY17 and FY18
  AD senior management and Mu2e project management are engaged in planning to meet this demand
  Bi-weekly meetings with AD Division Head Muon Department Head and Mu2e Accelerator L2
Solenoid field mapping
  Field mapping of the Mu2e solenoids is a task undertaken by the Mu2e collaboration (off-project) that will require an undetermined amount of time
  The proton target cannot be installed in the Production Solenoid until this activity is complete. Therefore the installation of the target is off-project

## Slide 4: Scheduling Constraints (continued)
Beam availability
  The external beamline is expected to be complete to the diagnostic absorber early in calendar year 2020.
  The actual commissioning of the beamline to the diagnostic absorber will be performed by the Muon Department (off-project) with single-turn extracted protons from the Delivery Ring.
  Installation of the Resonant Extraction Electro-Static Septum (ESS) precludes single turn extraction from the Delivery Ring
  ESS installation must follow commissioning of the beamline with single-turn protons
  Once the ESS is installed, only resonantly extracted beam will be possible in the external beamline.

## Slide 5: General Installation Sequence
Begin limited procurements after CD-3c
Before g-2 beam ops, install temp. shield wall downstream of M4/M5 split
Magnet moves during shutdown
  Extinction & M4DA (M4 Diagnostic Absorber) in SD 2017
  Hbend section in SD 2018
Move shield wall to DA
Ready for beam to DA ~Spring 2020
Resonant Extraction magnets, RF cavity, Delivery Ring instrumentation and controls installation during shutdowns
Installation work proceeds between shutdowns downstream of shield wall
Shield wall in this position allows low power beam to the Diagnostic Absorber while Mu2e installation work proceeds in the Mu2e Building
Commission with single turn protons to DA
Install ESS
Commission Resonant extraction

## Slide 6: Schedule
M4 Enclosure
BO
Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
FY14 FY15 FY16 FY17 FY18 FY19 FY20 FY21
CD-3c
CD-2/3b
Resonant Extraction Design
g-2 Beam Operations
Extinction Design
AC Dipole, Pwr Supply & Collimator Procurement, Fabrication & Install
External (M4) Beamline Design
Target Station Design
HRS Procurement & Fabrication
Instrumentation & Controls Implementation
Delivery Ring RF Procurements, Fabrication & Installation
PS Arrives @ Mu2e Bldg
Fabrication & Installation of Resonant Extr. Magnets, Power Supplies, & Electronics
Fabricate ESS
Target Fabrication
Instrumentation & Controls Design
Radiation Safety Design
Delivery Ring RF Design
Beam to Diagnostic Absorber
CD-4
M4 Commissioning with single turn Beam
Extinction Monitor Procurement, Assembly & Install
HRS Installation
Final Focus Section Installation
Hbend Section Installation
Extinction & M4DA Section Installation
Install ESS
Radiation Safety Procurements, Fabrication & Installation
Commission Res. Extr.
Beam Operations:
Notes: Notes:
No Muon Campus beam between Spring 2014 and Winter 2017
ESS Installation depicted here is not what is in the P6 schedule. P6 does not account for the fact that the beamline must be commissioned with single turn extracted beam before the ESS can be installed.
The ESS replaces a Delivery Ring extraction kicker module. Therefore, ESS installation precludes further single turn extracted beam to the M4 beamline.
HRS installation takes 10 days (box on schedule is over-sized)
Target installation is off-project and estimated to occur in Dec. 2021.
Beam commissioning is off-project