## Slide 1: Mu2e Tracker
Aseet Mukherjee
Tracker L2 Manager
21 Oct 14

## Slide 2: Tracker Team
Aseet Mukherjee – L2 Manager
  Started work at Fermilab in 1986 working on CDF’s Run-I tracker (CTC), a ~3m×3m cylindrical drift chamber.
  Co-leader with Bob Wagner for construction of CDF’s Run-II tracker (COT), a ~3m×3m cylindrical drift chamber.
  Worked on pattern recognition and fitting software for CTC; slow controls, calibration, monitoring, and maintenance for both trackers.
Bob Wagner – Deputy Manager
  Worked on design and construction of CTC
  Co-leader for construction of COT.
  Leader for construction of vertex drift chamber (VTX) for CDF Run-I
  Worked on calibration, monitoring, and maintenance of all three drift chambers.

## Slide 3: Organization
475.6.1 Project Management
L3: A. Mukherjee
CAM: A. Mukherjee
475.6.4 Front End Electronics
L3: V. Rusu (FNAL)
CAM: V. Rusu (FNAL)
475.6.2 Straws
L3: C. Wang (Duke)
CAM: R. Wagner (FNAL)
475.6.5 Infrastructure
L3: A. Mukherjee
CAM: A. Mukherjee
475.6.3 Straw Assemblies
L3: M. Corcoran (Rice)
CAM: R. Wagner (FNAL)
475.6.6 Installation
L3: A. Mukherjee
CAM: A. Mukherjee
475.6
Tracker
A. Mukherjee (FNAL)

## Slide 4: Requirements
 | Mu2e Document
Science Driven Requirements | 4381
Requirements for the mu2e Tracker Front End Electronics | 3879
Tracker Requirements Document | 732

## Slide 5: Requirements
Blind to low energy background electrons
Adequate resolution
Efficient for signal
r<380mm “No” mass (vacuum)
380<r<700mm Low mass detector
r>700mm Support structure
For:
3.6·1020 POT
6.7·1017 m- stops
Rme = 10-16
Signal yield = 3.5 evt
DIO yield = 0.20 evt

## Slide 6: Straw Tubes: 475.06.02 $1,697K
L3: C. Wang (Duke) CAM: R. Wagner (FNAL)
5 mm OD metalized Mylar® straws, 15µm wall
  Mylar for higher yield and modulus (compared to Kapton)
  Aluminum on inner and outer surface
  Gold on inner surface
25 µm gold plated tungsten sense wire

## Slide 7: Straw Assemblies: 475.06.03 $5,012K
L3: M. Corcoran (Rice) CAM: R. Wagner (FNAL)
96 straws form a panel (120°arc)
6 panels form a self supporting ring called a plane
Two planes, with a small gap, form a station 12 rotations, pattern set to optimize stereo reconstruction
18 stations form the tracker

## Slide 8: Panel
96 straws of varying length form a panel
  Staggered pattern to improve efficiency and resolve left/right ambiguity
  Gap between straws to allow for expansion when operating in vacuum
Panel frame encloses front end electronics

## Slide 9: Gas Manifold
Changed since CD1 (was all metal)
3D printed plastic with holes for straws: cyan. 2 pieces
Stainless steel reinforcement: magenta. 3 pieces
Everything else aluminum: grey. 6 pieces
Panel with covers removed

## Slide 10: Front End Electronics: 475.06.04 $2,910k
Discrete
Commercial Analog ICs
FPGA
FPGA
ADC
TDC
TDC
PCB transmission line
Preamp
Preamp
Readout Controller
DAQ
Straw
Output Control & Buffer
∑
L3 & CAM: V. Rusu (FNAL)

## Slide 11: Digitizers
Change since CD1: All commercial, off the shelf parts
Tight fit, but it does fit
Design complete (subject to value engineering as new parts become available)
Quotes for parts, boards, assembly
Digitizers and ROC (inner ring suppressed)
Edge view of digitizer boards with overlapping

## Slide 12: Readout Controller
Work is being done by Fermilab and U. of Houston
Preliminary designs exist.
  1st iteration: Over-size boards with many test features
  Next iteration: Reduce size. Conceptual layout exists
FPGA
Memory
MB Connectors

## Slide 13: Infrastructure: 475.06.05 $1,293K
Communication
Power
Gas
High Voltage
L3 & CAM: A. Mukherjee (FNAL)
Utilities run along support beams
Cooling runs around each plane

## Slide 14: Support Structure
Preliminary design complete
All aluminum gives acceptable deflection (were considering stainless steel at CD1)
~110μm sag

## Slide 15: Installation: 475.06.06 $106K
L3 & CAM: A. Mukherjee (FNAL)
Work with muon beamline (475.05) to install detector on rails
Post-installation optical survey
Route cables through DS
Test connections
Proton Absorber
Tracker
Calorimeter
Muon Beam Stop
Detector Solenoid
Instrumention Feedthrough Bulkhead
External Rail System
Notes: Add picture(s)

## Slide 16: Parts Flow
Duke
Rice U. Houston
York
PPG
U. Minnesota
Straws
Termination
Vacuum Feedthrus
Panels
Vender Oversight
PPG wind straws
York Straw ends Vacuum feedthroughs
Vacuum test straws
U. Mn Straw QC Cut and terminate straws
Rice, U. H. assemble panels
Panel QC
Duke Work with PPG
Locate wires (x-ray)
Fermilab Assemble planes Assemble tracker

## Slide 17: Improvements Since CD-1
Composite gas manifold using 3D printing technology
  Lower cost than drilling holes in metal
  Insulating… don’t need to add Kapton sleeves
  Special features can be added at no added cost
    Simplify preamp connection
    Build in epoxy application features
Digitizers with all off-the-shelf parts
All-aluminum support structure
More details in breakout talks

## Slide 18: Integration and Interfaces
External Interfaces
Internal Interfaces
  Straws ↔ FEE, Straw Assemblies
  FEE, Straw Assemblies ↔ Infrastructure
  Straw Assemblies, Infrastructure ↔ Installation
Documented in docdb-1562 and 3545
Participation in bi-weekly integration meetings
Formal sign-off between owners of all external interfaces as part of final design requirements
Interfaces understood and under control.
  Muon Beamline
  Conventional Construction
  Calorimeter
  DAQ

## Slide 19: Quality Assurance
Straw material tested by supplier for conductivity and adhesion of metal to Mylar®
100% testing of straws for leak rate and electrical conductivity before being assembled into panels
Tension measurement of straws and wires during panel assembly and before panels are assembled into planes
X-ray scan of wire positions within panel
Vacuum testing of panels before assembly into planes
Work in progress on database, bar coding, etc.

## Slide 20: Risks and Opportunities
10 current risks in risk registry
  8 threats, all mitigated to the extent possible
    2 Very Low probability
    4 Low probability
    2 Medium probability
  2 opportunities
    1 Medium probability
    1 High probability
Detailed mitigation plans documented and linked from Risk Register (docdb-4320)
All risks understood and under control

## Slide 21: ES&H
X-ray machine at Duke
  Procedures in place from ATLAS TRT construction
Gas (Ar:CO2) is non-flammable and non-toxic. Tracker volume less than one compressed gas cylinder.
Radioactive sources are widely used at Fermilab. All applicable saftey rules will be followed.
High voltage is moderate by Fermilab standards: 1500V, <1mA and ~10mJ stored energy on any one line
Power is from 48V supplies which have passive (limited capacity) and active (monitor and trip) current limit
No unusual toxic or hazardous materials used
  Extensive experience with epoxy at all participating institutions

## Slide 22: Cost Table
 | Base Cost (AY K$) |  |  | Estimate Uncertainty (on remaining costs) | % Contingency on ETC | Total Cost
 | M&S | Labor | Total |  |  | 
475.06 Tracker |  |  |  |  |  | 
475.06.01 Tracker Project Management | 28 | 1,779 | 1,807 | 250 | 20% | 2,057
475.06.02 Straws | 1,200 | 69 | 1,268 | 429 | 38% | 1,697
475.06.03 Straw Assemblies | 2,708 | 811 | 3,519 | 1,493 | 47% | 5,012
475.06.04 Tracker Front End Electronics | 1,676 | 591 | 2,267 | 643 | 32% | 2,910
475.06.05 Tracker Infrastructure | 374 | 567 | 941 | 352 | 38% | 1,293
475.06.06 Detector Assembly & Installation |  | 70 | 69 | 37 | 53% | 106
475.06.07 Tracker Conceptual Design/R&D | 999 | 654 | 1,653 |  |  | 1,653
475.06.99 Risk Based Contingency |  |  |  | 556 | - | 556
Grand Total | 6,983 | 4,540 | 11,523 | 3,760 | 44% | 15,283

## Slide 23: Cost Breakdown
Chart: 
| 475.06.01 Tracker Project Management | 475.06.02 Straws | 475.06.03 Straw Assemblies | 475.06.04 Tracker Front End Electronics | 475.06.05 Tracker Infrastructure | 475.06.06 Detector Assembly & Installation | 475.06.07 Tracker Conceptual Design/R&D
Total | 1806989.7832 | 1268420.9575 | 3518678.5089 | 2266897.382 | 940676.0942 | 69203.2772 | 1652604.7396
Chart: 
| L Labor | M Material | N Non-Fermi Labor
Total | 4540078.6321 | 5864494.8103 | 1118897.3002
Base Cost AY K$

## Slide 24: Quality of Estimate
Chart: 
| L1 Actual / M1 Existing P.O. | L2 LOE Task / M2 Procurements for LOE/Oversight Work | L3 / M3 Advanced | L4 / M4 Preliminary | L5 / M5 Conceptual | L6 / M6 Pre-Conceptual | L7 / M7 Rough Estimate Pre-Conceptual - Uncommon Work
Total | 2679060.2921 | 1306392.9966 | 945667.612 | 1662079.8742 | 4831086.8065 | 0.01 | 99183.2212
Base Cost AY K$

## Slide 25: Labor & Material by FY
Chart: Annual Cost $K
| 42277 | 42643 | 43008 | 43373 | 43738 | 44104 | 44469
L Labor | 676505.2056 | 370843.427 | 279170.3578 | 228034.8671 | 801310.364 | 258910.1166 | 1319.703
M Material | 320995.8817 | 96437.4813 | 2385493.1207 | 1785295.1645 | 13271.5394 | 2291.3214 | 223.6874
Non-Fermi Labor | 37277.5952 | 107449.0559 | 272626.9682 | 586579.2497 | 61542.238 | 0 | 0
Cumulative Total | 4272672.0806 | 4847402.0448 | 7784692.4915 | 10384601.7728 | 11260725.9142 | 11521927.3522 | 11523470.7426
Base Cost AY K$

## Slide 26: Labor Resources by FY
Chart: Annual FTE's
| 42277 | 42643 | 43008 | 43373 | 43738 | 44104 | 44469
AD Administrative | 0.3899 | 0.3688 | 0.5862 | 0.3406 | 0.3061 | 0.2444 | 0.0016
EN Engineering | 1.4827 | 1.0555 | 0.798 | 0.566 | 1.1116 | 0.6113 | 0.0032
ES Environmental, Safety & Health | 0 | 0 | 0 | 0 | 0 | 0 | 0
FM Facilities Management | 0 | 0 | 0 | 0 | 0 | 0.0023 | 0
IT Information Technology | 0.0453 | 0 | 0 | 0 | 0 | 0 | 0
SC Scientific | 1.0938 | 0.5478 | 5.672 | 8.0863 | 0.353 | 1.3233 | 0
TE Technical | 1.7595 | 1.2564 | 0.7617 | 2.8155 | 3.1849 | 0.1924 | 0
Cumulative | 4.7712 | 7.9997 | 15.8176 | 27.626 | 32.5816 | 34.9553 | 34.9601
FTEs by Discipline

## Slide 27: Milestones
L4 and L5 with corrections that were not noticed in time for this review
7/20/15 Single Panel Prototype Evaluation Complete (formerly said “Plane”)
10/1/16 Single Plane Prototype Evaluation Complete
6/5/17 Production Straws ready for assembly
6/13/17 LV power supplies received
7/13/17 Production preamps tested
10/30/17 All panels complete and tested
5/23/18 Straw Assemblies Complete
7/6/18 LV System installed
7/20/18 Cooling system installed and tested
7/24/18 Gas System Installed and Tested
8/31/18 HV system installed
2/25/19 Electronic Installation Complete
2/25/19 Implementation Tasks Complete (Ready for Verification that Key Performance Criteria are met)
4/10/20 Ready for Cosmic Ray Test
10/15/20 Ready for Operations

## Slide 28: Schedule
FY14 FY15 FY16 FY17 FY18 FY19 FY20 FY21
CD-3a
CD-2/3b
CD-4
KPPs Satisfied
CD-3c
Cosmic Ray Test
Single Panel
Single Plane
Panels
Planes
Digitizer
Readout Controller
Preamps
Install Cabling, Electronics
Tracker Move and Install
Front End Electronics
Straws
Pre-production
Production
Final Assembly
L5 Milestone
L4 Milestone

## Slide 29: Critical Path
FY14 FY15 FY16 FY17 FY18 FY19 FY20 FY21
Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
Panel Design, Assemble, Test
Single Plane Construction & Test
Single plane Evaluation Complete
Straw Production
Panel Production
KPPs Satisfied
All Panels Complete
Install electronics in panels
Tracker Assembly
Post-move tests

## Slide 30: Summary
Design satisfies requirements: resolution, efficiency, and reliability
Cost estimates complete
  99% is at Conceptual or higher
  57% is at Preliminary or higher
  Risks are understood and mitigated to the extent possible
Interfaces have been identified and defined
Needed resources identified, within Fermilab and from collaborating institutions
ES&H incorporated into the plans
Tracker is ready for CD-2