## Slide 1: Mu2e DOE CD-2 Review: Resonant Extraction L3
Vladimir Nagaslaev
Resonant Extraction L3 Manager
10/22/2014

## Slide 2: WBS 475.02.05 Resonant Extraction System
The scope of the Resonant Extraction Systems includes:
Development of the physics model
Design, fabrication and installation of:
  Tune quad magnets (3)
  Sextupole magnets (6)
  Dynamic bump correctors (4)
  Skew quad magnets (2)
  Electro static septa (2)
  Spill Monitor (1)
  RFKO system (1)
  Spill regulation electronics (1)
Map of Resonant Extraction elements in the Delivery Ring (L=505m)

## Slide 3: Requirements
Mu2e Proton Beam Requirements (doc-1105)
Parameter | Design | Limit
Length of slow spill period | 54 ms | >20 ms
Average intensity per pulse on target | 31 Mp | <50 Mp
Maximum variation of pulse intensity on target | ±50% | ±50%
Slow extraction preserves the time structure of the proton beam circulating in the Delivery Ring
Time structure of the proton beam on target

## Slide 4: Design: Delivery Ring Spill Parameters
Parameter | Value | Units
MI Cycle time | 1.333 | sec
Number of spills per MI cycle | 8 | 
Number of protons per micro-pulse | 3.1×107 | protons
Maximum Delivery Ring Beam Intensity | 1.0×1012 | protons
Instantaneous spill rate | 18.5×1012 | protons/sec
Average spill rate | 6.0×1012 | protons/sec
Duty Factor (Total Spill Time ÷ MI Cycle Length) | 32 | %
Duration of each spill | 54 | msec
Spill On Time per MI cycle | 497 | msec
Spill Off Time per MI cycle | 836 | msec
Time Gap between 1st set of 4 and 2nd set of 4 spills | 36 | msec
Time Gap between spills | 5 | msec
Pulse-to-pulse intensity variation | 50 | %
Extraction efficiency | 98 | %

## Slide 5
Design

## Slide 6: Design: Main Magnets and Power Supplies
Magnet | Quantity | Integrated gradient excursion | Base* Current, [A] | Max Current Excursion, [A] | Max supply Current [A] | Max dI/dt [A/sec] | Regulation accuracy, % | Regulation stability | Curve accuracy | Ripple, %
Tune Quad | 3 | 0.2 T | 0 | 80 | 100 | 16,000 | <0.5% | <0.5% | <0.5% | <0.05%
Sextupoles | 6 | 32 T/m | 200 | +-80 | 300 | 16,000 | <0.5% | <0.5% | <0.5% | <1%
DEX trims | 4 | 0.014 Tm | ND | 14 | +-40 | 2,800 | <1% | <1% | <1% | <1%
Tune quad ramp curve I(t)
Sextupole ramp curve I(t)
DEX bump ramp curve I(t)
Derived requirements/specs for
3 families of specialized magnets to drive the slow extraction
Sextupole magnets
Tune ramp quad magnets
DEX – dynamic bump correctors

## Slide 7: Design: Solution for Magnets and PS
Tune quad magnets : CQA | Sextupole magnets : ISA | Dynamic bump trims: NDB
Cooling Ring magnets, available in abundance. Some refurbishing may be needed. | Existing design of Main Injector sextupoles. Spare magnets are not available – will be built. | Debuncher style correctors. Available in working conditions
Power supplies for all magnet types will be built on the basis of the Booster switch-mode 65A 180 V units |  | 
2 units in parallel 3 independent bulk supplies; | 6 units in parallel to provide 300A current for each circuit | Split magnet coils in 2; Upgrade bulk supply to 350V with higher voltage FETs and filter module
Status: building PS prototypes and testing magnets with representative ramps will complete the Final design for magnets and their power supplies. |  | 

## Slide 8: Design: Electrostatic Septa
Design considerations for ESS:
Foils instead of wires (advantages!)
Rad levels  Minimize service time in tunnel and maximize septa lifetime
2 septa straddle the focusing quad Q203
Main technical challenge:
Strive to achieve HV>100kV
Vacuum conditions in Delivery Ring
Using prior experience:
Building ESS for MI at FNAL
Building ES Separators for Tevatron
Other labs experience with ESS

## Slide 9: Design: Spill Monitoring
Fast spill rate monitoring is required for effective regulation. A WCM Spill Monitor prototype has been built and tested.
This device will be used as a working module - no new fabrication is needed.

## Slide 10: Design: RF Knock-Out
Fast ripples on the spill rate will be regulated with the RF Knock-Out method that employs transverse heating of the beam.
Kicker waveform is FM-ed to cover the beam betatron frequency spread.
AM is provided by the regulation logic
Reuse old Tevatron damper kicker as the RFKO device.
RFKO beam heating rates have been measured with beam
The kicker has been identified, prepped and tested with the beam: Ready for use.

## Slide 11: Design: Spill regulation electronics
Regulation logic is realized in the MVME5500 processor
Slow regulation (feedforward) to the tune quad ramp
Fast regulation (feedback) to the RFKO kicker
Currently we are doing prototyping in order to validate design solutions.
This will complete the Final Design of Spill Regulation Electronics

## Slide 12
Performance
    Physics Design
    ESS R&D

## Slide 13: Performance: Synergia tracking simulations
Synergia – state of the art tool
  Model improved since CD1
  All features: DEX, RF, RFKO, aperture, ramping
  Full spill
  Substantially sped up
Main results:
  Main parameters verified and optimized through the entire spill
  Performance consistent with earlier ORBIT simulations and physics model; no showstoppers within known physics
  RFKO process - heating rates consistent with expected
Status: Complete
Extracted beam footprint, DEX bump off
Extracted beam footprint, DEX bump on

## Slide 14: Performance: MARS tracking simulations
Main outcomes include:
  Wires do not have advantage over foils in terms of losses
  Fine alignment is important
  Performance can be improved by making septa asymmetric
  Using a pre-scattering diffuser reduces losses further
Red- 100m wires; Green- 50m foils
Tracking extracted beam with MARS code:
  Tracking particles in media and DC fields
  Detailed calculations of interaction with materials
  Radiation levels, Residual activation, Energy deposition, etc
  Essential for beam loss calculations and geometry optimization
Losses vs beam angle.
Status: Complete

## Slide 15: Performance: ESS studies
FEA field calculations:
  Determined optimal geometries with foils and electrodes
Prototype-I:
  Built a prototype to study mechanical properties, techniques for clamping, stretching, measuring.
  Developed a strategy to achieve good performance
Prototype-II for HV testing in vacuum:
  Testing cave is made available and ready
  Old Tevatron separator vessel reused to house the structure
  Stage-0 prototype structure fabricated and tests are in progress
Status: in progress

## Slide 16
Essential Project information

## Slide 17: Changes since CD-1
Magnetic septa have been moved out from our scope as a synergy with g-2 project
Added new scope to improve performance:
  Dynamic bump
  Skew quadrupole magnets
Change in the extraction geometry: flipped direction as part of integration plan with the Muon Campus

## Slide 18: Value Engineering since CD-1
Used synergy with Main Injector operations in preparations of the septa testing cave at the NWA building.
Use the prototype WCM as a working instrument
Reuse existing hardware:
  Old style Tevatron damper kicker as RFKO kicker
  CQA magnets for tune ramping
  NDB magnets for Dynamic Bump
  TeV separators for the HV/vac prototyping

## Slide 19: Downselects
The choice of the machine resonance for the slow extraction has been finalized in favor of the third integer one.
Selection has been made for use of foils in the ESS instead of wires. Milestone has been met.

## Slide 20: Remaining work before CD-3
Complete ESS prototyping studies with HV in vacuum
Fabricate prototypes of power supplies for each type of ramped magnets and complete magnet testing with representative ramps
Develop a prototype of the timing module for spill regulation and complete its testing.

## Slide 21: Quality Assurance
QA standards and guidelines
  Fermilab Integrated QA Program – esh-docdb#2469
  Fermilab Engineering Manual
  QA Management Plan for Mu2e Experiment - mu2e-docdb# 677
Design Level QA
  Design analysis tools (simulations, FEA)
  Prototyping, performance tests
  Beam studies
  Reviews, reports, communications
Fabrication and installation QA
  Built in process QA (written procedures, travelers)
  Personnel training

## Slide 22: Risks
6 risk items considered:
  1 absorbed in the BL
  1 realized
  1 mitigated by an external project (AIP)
  2 risks transferred to operations
Presently only one item in the Risk Registry (opportunity)
RR index | Risk/ Opportunity | Impact | Probability | Point estimate | Status
203 | Opportunity to reuse existing spare sextupoles | Cost | L | $164k | Current

## Slide 23: ES&H
Radiation hazard during operations and service
Tunnel hazards during installation
Specific hazards in the prototype testing area (UV and HV):
  Testing cave is interlocked and operation protocol is included in the AD operations procedures.
  LOTO procedure has been written and approved with AD ES&H
Fermilab Environment, Safety and Health Manual (FESHM)
Safety practices discussed in the Mu2e Hazard Analysis Report (Mu2e-doc-675).

## Slide 24
Cost & Schedule

## Slide 25: Cost Distribution by L4
Base Cost by L4 (AY $k)

## Slide 26: Cost Distribution by Resource Type
Base Cost (AY $k)

## Slide 27: Quality of Estimate
Base Cost by Estimate Type (AY$k)
99% of estimate is at Preliminary level or better

## Slide 28: Labor Resources
FTEs by Discipline
Labor/Material breakdown

## Slide 29: Cost Table
WBS 2.5 Accelerator Resonant Extraction System
Costs are fully burdened in AY $k
 | Base Cost (AY K$) |  |  |  |  | 
 | M&S | Labor | Total | Estimate Uncertainty (on remaining budget) | % Contingency on (on remaining budget) | Total Cost
475.02.05.01 General Design |  | 403 | 403 | 15 | 143% | 418
475.02.05.02 Electrostatic septum (Mechanical) | 528 | 1,999 | 2,527 | 939 | 41% | 3,466
475.02.05.03 Magnets | 594 | 320 | 914 | 237 | 26% | 1,152
475.02.05.04 Fast Feedback Devices (aka: Spill Monitor) | 15 | 65 | 79 | 14 | 30% | 93
475.02.05.05 Fast Feedback | 40 | 233 | 273 | 81 | 41% | 354
475.02.05.06 RF Knockout Kicker | 143 | 29 | 172 | 60 | 35% | 232
475.02.05.07 Magnet Power Supplies | 317 | 232 | 550 | 132 | 26% | 682
475.02.05.08 Technical Documentation |  | 610 | 610 | 137 | 30% | 747
Grand Total | 1,638 | 3,889 | 5,527 | 1,616 | 35% | 7,143

## Slide 30: Major Milestones
47502.05.001020 | T5 - Septum Technology Choice Complete | 12-Dec-12
47502.05.03.000500 | T5 - Resonant Extraction Magnet Design Complete | 26-Feb-14
47502.05.01.001070 | T5 - Milestone: Beamline Studies Complete | 18-Apr-14
47502.05.05.001105 | T5 - Resonant Extraction Fast Feedback Electronics Design Complete | 24-Nov-14
47502.05.07.000500 | T5 - Resonant Extraction Magnet Power Supply Design Complete | 27-Feb-15
47502.05.02.001215 | T5 - Resonant Extraction Electro-Static Septum Design Complete | 22-May-15
47502.05.001050 | T5 - DOE CD-3c Accelerator Resonant Extraction Approval | 24-Feb-16
47502.05.03.2.001020 | T5 - Start of Resonant Extraction Harmonic Sextupole Magnet Fabrication | 3-Oct-16
47502.05.03.2.001095 | T5 - Resonant Extraction Harmonic Sextupole Magnet Fabrication Complete | 29-Jan-18
47502.05.03.001000 | T5 - Resonant Extraction Magnet Installation Complete | 30-Oct-18
47502.05.07.001000 | T5 - Resonant Extraction Magnet Power Supply Installation Complete | 13-Dec-18
47502.05.02.001315 | T5 - Resonant Extraction Electro-Static Septum Assembly Complete | 11-Jul-19
47502.05.02.001318 | T5 - Start Resonant Extraction Electro-static Septum Installation | 12-Jul-19
47502.05.02.001350 | T5 - Installation of Electrostatic Septum Modules Complete | 13-Sep-19
Total 53 tier-5 milestones in the MS dictionary
14 most significant in the table below

## Slide 31: Schedule
Beam to Diagnostic Absorber
FY14 FY15 FY16 FY17 FY18 FY19 FY20 FY21
Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 | Q2 | Q3 | Q4
CD-3c
CD-2
g-2 Beam Operations
ES Septum R&D and prototyping
Commissioning with single turn Beam
Commission Res Extr
Development of the Spill Regulation
General Design
Magnet Design
Spill Mon Design
Spill Regulation Design
Magnet PS Design
Beam Studies
In
Development of the ES Septa
In
Magnet Fabrication
Magnet PS Fabrication
In
In
Installation
Design
Fabrication
Installation
Off project
KPP
Beam Line Implementation
Notes: Notes:
ESS Installation depicted here is not what is in the P6 schedule. P6 does not account yet for the fact that the beamline must be commissioned with single turn extracted beam before the ESS can be installed.
The ESS replaces a Delivery Ring extraction kicker module. Therefore, ESS installation precludes further single turn extracted beam to the M4 beamline.
Res. Extr. beam commissioning is off-project

## Slide 32: Summary
Resonant Extraction Systems Preliminary Design is complete
Design of the Resonant Extraction meets the requirements
The final studies are underway with the high confidence of success
Cost and schedule estimates are well understood and ready to establish the baseline

## Slide 33: Backup slides

## Slide 34: Organizational Breakdown
Key people in the subproject:
  V. Nagaslaev, AD, L3 Manager
  C. S. Park, CD, L3 Deputy Manager, Synergia
  D. Tinsley, AD, Sr. Mechanical Engineer, ESS design
  P. Prieto, AD, Sr. Electronics Engineer, Spill Controls
  G. Krafczyk, AD, Sr. Electrical Engineer, Power Supplies
  TJ Gardner, TD, liaison for magnet production

## Slide 35: Phase space diagrams

## Slide 36: Extracted beam footprint

## Slide 37: Optics of the Debuncher: chromaticity
f
Chromaticity:
Large momentum spread
2 families of sextupoles in arcs
Tunes vs Dp/p
Fit: 6- and 10-pole harmonics in dipoles
Included in the model
Chromaticity of functions
No problem for injection matching
No dynamic aperture limitation

## Slide 38: Risks
RR index | Risk/ Opportunity | Impact | Probability | Point estimate | Status
203 | Opportunity to reuse existing spare sextupoles | Cost | L | $164k | Current
025 | Need to ramp Delivery Ring sextupoles | Technical | M | -- | Mitigated in BL
024 | Inability to locate and reuse tooling for ESS | Cost | M | ND | Realized
023 | Inacceptable amount of beam left in the DR | Technical | L | -- | Mitigated by AIP
022 | High Beam Loss | Technical, Schedule | M | -- | Transferred
012 | Mu2e beam commissioning delayed. | Schedule | L | -- | Transferred
Presently only one item in the Risk Registry (opportunity)

## Slide 39: Tune space
nx=9.61
nx=9.62
nx=9.63
nx=9.64
nx=9.65
nx=9.67